## Sheet1
CBETA Milestones
R. Michnoff 3/29/2017, Last modified: 09/15/18
Per NYSERDA contract
|  |  | 2016 |  | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
Milestone | Description |  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
| month number |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
1 | Complete Engineering Design Documentation | bar: 2016 Nov 1 to 2017 Jan 3
Task goal: Complete documentation of the engineering design of the project.
1.1 | Drawings and specifications of the overall system as well as all technical sub-systems
1.2 | Baseline lattice layout of the accelerator and the baseline parameters
2 | Assemble Prototype Girder | bar: 2017 Feb 4 to 2017 Apr 6
Task goal: Assemble and test the prototype girder using 8 FFAG magnets | bar: 2017 Apr 6
2.1 | An assembled prototype girder to be used in the acclerator circumference made of 8 FAG magnets | bar: 2017 Apr 6
2.2 | Perform rigorous magnetic, mechanical, alignment and thermal tests on the prototype and document the results of the tests | bar: 2017 Apr 6
3 | Approve Magnet Production | bar: 2017 May 7 to 2017 Jun 8
Task goal: Successful approval of the production of all magnets to be used in the accelerator
3.1 | Assemble conventional electromagnets in the two combiner-separator regions of the accelerator | This will not be complete until the four-turn configuration
3.2 | Assemble relatively weak electromagnet corrector magnets with FFAG magnets on the arc girders and assemble the strong electromagnets on the combiner-separator tables. |  | 2017 Mar 5: correctors on FFAG magnets ->; 2017 Apr 6: X; 2017 Nov 13: X; 2017 Dec 14: <- first splitter magnets installed for FAT
3.3 | Perform rigorous magnetic, mechanical, alignment and thermal tests on the full assembly. |  | 2017 Mar 5: preproduction FFAG magnets ->; 2017 Apr 6: X; 2017 Nov 13: X; 2017 Dec 14: <- first splitter magnets installed for FAT
3.4 | Analyze the test results and if successful approve the production of all magnets |  | 2017 Mar 5: preproduction FFAG magnets ->; 2017 Apr 6: X
[7 empty] | X | <- Production of splitter magnets approved (no preproduction units required)
4 | Beam thrugh Main Linac Cryomodule (MLC) | bar: 2017 Jul 9 to 2017 Aug 10
Task goal: Successfully pass a small beam current through the Main Linac Cryomodule
4.1 | Move the Main Linac Cryomodule unit which accelerates the beam to the test site | bar: 2017 Mar 5
4.2 | Move the supported infrastructure including RF power and cryogenics to the test site | bar: 2017 Mar 5
4.3 | Integrate the MLC and the supporting infrastructure for beam testing | bar: 2017 Apr 6
4.4 | Pass the small beam current once through the MLC and capture it by a beam stop. The return arc will not be in place at this time. |  | 2017 Jun 8: X; 2017 Jul 9: <- must be completed by 6/30/2017 due to water shutdown
In order to progress to Milestone 5, the contractor must demonstrate to NYSERDA success, …
5 | Test Production FFAG Magnets | bar: 2017 Sep 11 to 2017 Dec 14
Task goal: Successfully test first production FFAG magnet
-- | Place procurement for FFAG permanent magnet material (PMM) | bar: 2017 Apr 6
-- | PMM material received | bar: 2017 Aug 10
-- | PMM material measured | bar: 2017 Sep 11
-- | PMM material shipped to vendor for magnet fabrication | bar: 2017 Sep 11
5.1 | Select a single vendor for the production of FFAG magnet | bar: 2017 May 7
5.2 | Transfer production technology and assembly skills from the project team to the vendor.
5.3 | Monitor the production throughout the process.
-- | Receive first set of production FFAG magnets (qty: 10) | bar: 2017 Oct 12
5.4 | Test every FFAG magnet before assembly onto magnet girders |  | 2017 Nov 13: X; 2017 Dec 14: <- First production magnet(s)
6 | Perform Fractional Arc Test: Beam through MLC and Prototype Girder | bar: 2018 Jan 15 to 2018 Apr 18
Task goal: Successfully perform fractional arc test
FAT assembly complete | bar: 2018 Jan 15
6.1 | Pass the beam through the MLC, through one channel of one of the separator-combiners, and through an arc girder. | bar: 2018 Apr 18
6.2 | Carry out performance testing of the identified sub-systems with and without the beam. | bar: 2018 Apr 18
6.3 | Document all trouble shooting incidents, performance issues and rectify them. | bar: 2018 Apr 18
In order to progress to Task 7, the contractor must demonstrate to NySERDA success…
7 | Complete Girder Production Run | bar: 2018 May 19 to 2018 Nov 25
Taks goal: Complete the girder production run.
7.1 | Complete construction of all FFAG magnets |  | 2018 Jun 20: final qty of FFAG production magnets delivered to BNL->; 2018 Jul 21: X
7.2 | Complete performance testing of all FFAG magnets. | bar: 2018 Aug 22
7.3 | Complete girder assembly and carry out the production run. | bar: 2018 Sep 23
-- | First production girder delivered to Cornell | bar: 2018 Mar 17
-- | (1 girder assembled per week = ~24 weeks = 6 months)
8 | Complete Final Assembly and Pre-Beam Commissioning | bar: 2018 Dec 26 to 2019 Feb 28
Task goal: Complete final assembly and pre-beam commissioning
8.1 | Ship pre-aligned girders to Cornell University |  | 2018 Oct 24: final FFAG girder plate assembly with magnets received at Cornell->; 2018 Nov 25: X
8.2 | Assemble, install and align the girders in the L0E hall, along with the other components including the vacuum system, beam instrumentation, shielding, control system and safety system | bar: 2018 Dec 26
8.3 | Complete the final assembly for pre-beam commissioning through system integration | bar: 2018 Dec 26
8.4 | Carry out detailed system checks to ensure accurate functioning of the system and have the system pre-beam commissioning ready. | bar: 2019 Feb 28
-- | Assembly for energy recovery single pass beam test complete, with splitters 3 & 4 installed, and splitter 2 prefit | bar: 2019 Feb 28
9 | Single Pass Beam Energy Scan | bar: 2019 Mar 29 to 2019 Jun 32
Task goal: Successfully complete single pass beam energy scan
9.1 | Pass the beam through the MLC and around the arc once during this first phase of beam commissioning. | bar: 2019 Apr 30
9.2 | Test the ability of the FFAG arc magnets to pass a broad range of beam energies during this test. | bar: 2019 Apr 30
9.3 | Perform energy scan by adjusting the accelerating voltage of the MLC by activating the beam diagnostic systems. Document all results. | bar: 2019 Apr 30
10 | Single Pass Beam with Energy Recovery | bar: 2019 Jul 33 to 2019 Oct 36
Task goal: Successfully complete single pass beam with energy recovery
10.1 | Pass the beam through the MLC and decelerate it during the second time. | bar: 2019 Jul 33
10.2 | Measure the efficiency of the energy recovery of the accelerator at low currents. | bar: 2019 Jul 33
10.3 | Perform design of experiments on energy recovery variation with beam current and with other accelerator parameters. | bar: 2019 Jul 33
-- | Reconfiguration of beam-line for 4 splitters each side, for four-pass beam acceleratation operation
-- | Four-pass beam-line reconfiguration complete | bar: 2019 Sep 35
11 | Four Pass Beam with Energy Recovery (Low Current) | bar: 2019 Nov 37 to 2019 Dec 38
Task goal: Successfully complete energy recovery during 4 passes
11.1 | Pass the beam through the MLC 8 times in full operation | bar: 2019 Dec 38
11.2 | Accelerate the beam to higher energies during 4 passes and then decelerate during remaining 4 passes. | bar: 2019 Dec 38
11.3 | Measure the multi-turn energy recovery in the superconducting accelerator during the 4 decelerating passes. | bar: 2019 Dec 38
11.4 | Document the results of this world-first experiment | bar: 2019 Dec 38
12 | Commissionn CBETA and Complete the Project | bar: 2020 Jan 39 to 2020 Apr 42
Task goal: Commission CBETA (Cornell-Brookhaven ERL Test Accelerator)
12.1 | Measure all key parameters identified in Table 1 (Electron beam energy, electron bunch charge, gun current, bunch repetition rate, RF frequency, injector energy, RF operation mode, number of ERL turns, and energy aperture of arc). | bar: 2020 Apr 42
12.2 | Compare measured KPPs against the design requirements. | bar: 2020 Apr 42
12.3 | Commision CBETA for further operation and experiments. | bar: 2020 Apr 42
12.4 | Prepare detailed comprehensive final report encompassing all activities performed. | bar: 2020 Apr 42
|  |  | 2016 |  | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
Milestone | Description |  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
| month number |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
Notes:
1 | Each main milestone is labeled with the milestone number per the NYSERDA contract The dot numbers are the bullets within each of the milestones defined in the contract. The tasks with a milestone number of "--" are additonal tasks that are not part of the contract. The hashed boxes indicate when each milestone is to be performed per the contract. The Xs mark the estimate for when each task should be completed in order to satisfy the schedule.
2 | Regarding the Go/No-Go decision points, in order to satisfy the schedule we will not be able to wait until milestones 4 (MLC test) and then milestone 6 (fractional arc test) are complete before proceeding. More specifically, the FFAG magnet and girder procurements will need to begin much sooner than completion of the MLC test. And the full girder production run (milestone 7) will need to be in full swing much sooner than completion of the fractional arc test. Therefore, we should consider requesting approval from NYSERDA to begin the full FFAG magnet and girder procurements (including all the vacuum devices) in April 2017.
3 | Milestone 3 - Approve Magnet Production is a bit unclear. I'm assuming this means that we approve magnet production, and this is not something NYSERDA needs to approve.
4 | Milestone 3 combines approval of FFAG magnets and splitter magnets. For the FFAG magnets, we'll need to approve production mid-April so that production procurements can begin and so that we can satisfy milestone 5. This will hopefully coincide with the completion of the FFAG magnet assembly and testing - although the full pre-production girder assembly is not likely to be complete until the end of April.
5 | My interpretation is that approving production of the splitter magnets is occurring now as part of the RFP review. For the splitter magnets we are not planning to procure preproduction units for testing and approval.
6 | Task 3.1, also under Approve Magnet Production, does not really apply to this milestone. The splitter magnets will not be completely installed until the four-turn configuration. We could consider this task as relating to the installation of splitter magnets for the low energy splitter line as required for the FAT. If so, then 3.1 is similar to the second half of 3.2. Also, the installation of these first splitter magnets for the FAT is not expected to be done until November 2017 which is 5 months after the milestone 3 date. How should we handle this?
7 | MLC test must be complete by 6/30/2017 due to the water shutdown.
8 | The FFAG permanent magnet material will need to be ordered very soon - early to mid April, and the FFAG magnet assembly vendor will need to be selected by mid-May in order to have a chance at satisfying milestone 5.
9 | Milestone 5 - Test Production FFAG Magnets seems to suggest all of the production magnets. This does not seem possible by December 31, 2017. Can we assume that milestone 5 is related to only the 10 first article production magnets? This may have actually been the original intent, because task 7.1 is "Complete construction of all FAG magnets."
10 | Only 4 months are provided for milestone 6 - Perform Fractional Arc Test. We should make every effort to complete the FAT beam line configuration installation by the very beginning of that period (Jan 1, 2018) in order to allow sufficient beam testing time. THIS MEANS THAT THE HOLE IN THE CONCRETE WALL MUST BE COMPLETED MUCH EARLIER THAN THAT. What can we do to try to get the hole cut sooner than the present schedule of Dec 2017/Jan 2018? This has the potential to significantly delay our efforts.
11 | It would be good for us to try to complete milestone 7 early - Complete Girder Production Run. This will allow more time to complete milestone 8 - Complete final Assembly and Pre-Beam Commissioning of the single pass configuration, which includes only 3 months.
12 | I added a task in the milestone 9 period to reconfigure the beam line from the accelerating splitter configuration to the decelerating splitter configuration. This needs to happen prior to beam work for milestone 10 - Single Pass Beam with Energy Recovery.
13 | There was no time provided to reconfigure the machine from the one-splitter configuration to the four-splitter configuration. I added this in the milestone 10 period - Single Pass Beam with Energy recovery.
14 | Due to the time required for the four-splitter beam-line reconfiguration, we'll need to plan on completing milestone 9 early, so that milestone 10 can begin early, so that the four-pass tests can begin on time (or hopefully a little early).