## August 2017 by Tier&Date
hide | hide | hide |  |  | hide | hide |  | ** Quarters are based on BNL's Fiscal Calendar ** T-3s are not reportable milestones | hide | hide | hide | hide | hide | hide | hide | hide |  |  | hide | hide | hide | hide | hide | hide
Calc_ID | Point of Contact L2 | Point of Contact L3 | Responsible Institution | WBS | Old WBS (Month 'YR) | System | Level | CBETA Reportable Milestones | Duration | % Complete | Current Schedule Finish Date | CBETA v0 Baseline Schedule Date (August 2017) | CBETA v1? Baseline (December 2017) | print order | Sorted Current Planned Date | Sorted Original Milestone Date | Original Reportable Milestone Date | Current Planned Date (A/F) | Mth 'YR Planned Date | Milestone | Reportable Milestone Sort | Reportable Milestone Level Sort | PCR | Comments
1 | Smolenski/Michnoff | Michnoff | BNL | A1.01.01.01.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): NYSERDA Funding Date Start (Actual 10/31/2016) | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | FY17Q1 | FY17Q1(A)
2 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.01.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Engineering Documentation Complete | 0 d | 100% | 2017-01-31 | 2017-01-31 |  |  |  |  | FY17Q2 | FY17Q2(A)
3 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.01.03 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Prototype Girder Assembled | 0 d | 100% | 2017-04-30 | 2017-04-30 |  |  |  |  | FY17Q3 | FY17Q3(A)
4 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.01.04 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Magnet Production Approved | 0 d | 100% | 2017-06-30 | 2017-06-30 |  |  |  |  | FY17Q3 | FY17Q3(A)
5 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.01.05 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Beam through Main Linac Cryomodule (MLC) [Actual Finish 6/16/17, Planned Finish 8/31/17] | 0 d | 100% | 2017-08-31 | 2017-08-31 |  |  |  |  | FY17Q4 | FY17Q3(A)
6 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.02.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): First Arc Production Magnet Tested | 0 d | 0% | 2017-12-31 | 2017-12-31 |  |  |  |  | FY18Q1
7 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.02.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Fractional Arc Test: Beam through MLC & Prototype Girder | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | FY18Q3
8 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.03.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Girder Production Run Complete | 0 d | 0% | 2018-11-30 | 2018-11-30 |  |  |  |  | FY19Q1
9 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.03.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Final Assembly & Pre-Beam Commissioning Complete | 0 d | 0% | 2019-02-28 | 2019-02-28 |  |  |  |  | FY19Q2
10 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.03.03 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Single Pass Beam Energy Scan | 0 d | 0% | 2019-06-30 | 2019-06-30 |  |  |  |  | FY19Q3
11 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.04.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Single Pass Beam with Energy Recovery | 0 d | 0% | 2019-10-31 | 2019-10-31 |  |  |  |  | FY20Q1
12 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.04.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Four Pass Beam with Energy Recovery (Low Current) | 0 d | 0% | 2019-12-31 | 2019-12-31 |  |  |  |  | FY20Q1
13 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.04.03 |  | A1.01 - Project Management | T-1 | Milestone (T-1): CBETA Commissioned and Project Complete | 0 d | 0% | 2020-04-30 | 2020-04-30 |  |  |  |  | FY20Q2
150 | Burke | Burke | Cornell | A1.06.02.02.03.03 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets - Beam Stop Table - Assembly Complete | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | FY17Q1 | [6 empty] | Incorrect dates - kwj
186 | Dobbins | Dobbins | Cornell | A1.09.05.03.01 |  | A1.09 - Instrumentation | T-2 | Milestone: BPM Assembly/Development - Pick-up Complete and ready for Final testing | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | FY17Q1 | [6 empty] | Incorrect dates - kwj
100 | Hoffstaetter | Trbojevic | BNL | A1.02.01.02.03 |  | A1.02 - Accelerator Physics | T-2 | Milestone: FFAG Halbach Magnet Design Chosen | 0 d | 100% | 2016-12-21 | 2016-12-21 |  |  |  |  | FY17Q1 | FY17Q1(A)
223 | Bartnik | Bartnik | Cornell | A1.12.01.03 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Gun, ICM, Beam Stop - Commissioning Complete | 0 d | 0% | 2017-01-25 | 2017-01-25 |  |  |  |  | FY17Q2
224 | Bartnik | Bartnik | Cornell | A1.12.02.03 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Diagnostics Line - Commissioning Complete | 0 d | 0% | 2017-02-27 | 2017-02-27 |  |  |  |  | FY17Q2
165 | Dobbins | Dobbins | Cornell | A1.08.03.01.04.02 |  | A1.08 - Controls | T-2 | Milestone: All File Server - Testing Complete | 0 d | 0% | 2017-03-31 | 2017-03-31 |  |  |  |  | FY17Q2
118 | Tuozzolo | Tuozzolo | BNL | A1.05.01.02.01.11 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Magnets - Procurements complete | 0 d | 100% | 2017-04-18 | 2017-04-18 |  |  |  |  | FY17Q3 | FY17Q3(A)
231 | Widger | Heltsely | Cornell | A1.13.01.02.05 |  | A1.13 - Safety | T-2 | Milestone: Safety/x-Ray Permit for MLC Beam through Merger Test Approved | 0 d | 100% | 2017-04-20 | 2017-04-20 |  |  |  |  | FY17Q3 | FY17Q3(A)
135 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.03 |  | A1.06 - Splitter Magnets | T-3(2?) | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - Contract Awarded | 0 d | 0% | 2017-04-21 | 2017-04-21 |  |  |  |  | FY17Q3
119 | Tuozzolo | Tuozzolo | BNL | A1.05.01.02.02.06 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Girder - Procurements complete | 0 d | 100% | 2017-04-26 | 2017-04-26 |  |  |  |  | FY17Q3 | FY17Q3(A)
120 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.01.06 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Magnets - Assembly complete | 0 d | 100% | 2017-04-27 | 2017-04-27 |  |  |  |  | FY17Q3 | FY17Q3(A)
121 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.02.02 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Girder - Assembly complete | 0 d | 100% | 2017-04-27 | 2017-04-27 |  |  |  |  | FY17Q3 | FY17Q3(A)
122 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.03.03 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Pre-Production Magnet/Vacuum Chamber Assembly on Girders Complete | 0 d | 100% | 2017-05-03 | 2017-05-03 |  |  |  |  | FY17Q3 | FY17Q3(A)
101 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.05 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Final Baseline Lattice Design Approved by CBETA Board | 0 d | 100% | 2017-05-15 | 2017-05-15 |  |  |  |  | FY17Q3 | FY17Q3(A)
202 | Gallagher | Gallagher | Cornell | A1.11.01.03.02.01.09 |  | A1.11 - System Integration | T-2 | Milestone: L0E Vacuum Lab Removal Complete | 0 d | 100% | 2017-06-08 | 2017-06-08 |  |  |  |  | FY17Q3 | FY17Q3(A)
102 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.08 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Lattice Design Updates/Adjustment for Fractional Arc Test Approved by CBETA Board | 0 d | 100% | 2017-06-14 | 2017-06-14 |  |  |  |  | FY17Q3 | FY17Q3(A)
103 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.02 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Lattice Design Updates/Adjustment for SPBT Approved by CBETA Board | 0 d | 0% | 2017-06-14 | 2017-06-14 |  |  |  |  | FY17Q3
225 | Bartnik | Bartnik | Cornell | A1.12.03.06 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): MLC - Commissioning Complete | 0 d | 0% | 2017-06-15 | 2017-06-15 |  |  |  |  | FY17Q3
108 | Gulliford | Gulliford | Cornell | A1.03.05.04.04 |  | A1.03 - DC/Gun Injector | T-2 | Milestone: B2 Diagnostic Beam Line Instrumentation Integration Complete | 0 d | 0% | 2017-06-21 | 2017-06-21 |  |  |  |  | FY17Q3
123 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.03.05 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Magnets and Girder - Halbach Magnets & Girder Assembly & Testing complete | 0 d | 100% | 2017-07-07 | 2017-07-07 |  |  |  |  | FY17Q4 | FY17Q4(A)
143 | Burke | Burke | Cornell | A1.06.01.02.01.01.05 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Electromagnet Table - ALL Design Complete | 0 d | 0% | 2017-07-21 | 2017-07-21 |  |  |  |  | FY17Q4
124 | Tuozzolo | Tuozzolo | BNL | A1.05.02.01.01.05 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets - Halbach w/ corrector design revisions complete | 0 d | 100% | 2017-08-02 | 2017-08-02 |  |  |  |  | FY17Q4 | FY17Q4(A)
139 | Burke | Burke | Cornell | A1.06.01.01.01.02.01.05 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Common Magnets - Design complete | 0 d | 0% | 2017-08-10 | 2017-08-10 |  |  |  |  | FY17Q4
162 | Dobbins | Dobbins | Cornell | A1.08.01.01.04 |  | A1.08 - Controls | T-2 | Milestone: Network Infrastructure Design Complete | 0 d | 0% | 2017-08-10 | 2017-08-10 |  |  |  |  | FY17Q4
199 | Gallagher | Gallagher | Cornell | A1.11.01.01.07 |  | A1.11 - System Integration | T-2 | Milestone: Water Turned On - L0E Work continued | 0 d | 0% | 2017-08-11 | 2017-08-11 |  |  |  |  | FY17Q4
106 | Gulliford | Bartnik | Cornell | A1.03.02.02.02.01 |  | A1.03 - DC/Gun Injector | T-2 | Milestone: Laser Room Move Complete and Ready for Table Setup[Clean Room conditions established | 0 d | 100% | 2017-08-15 | 2017-08-15 |  |  |  |  | FY17Q4 | FY17Q4(A)
194 | Li | Li | Cornell | A1.10.04.01.05 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc System - All Designs Complete | 0 d | 0% | 2017-08-15 | 2017-08-15 |  |  |  |  | FY17Q4
125 | Tuozzolo | Tuozzolo | BNL | A1.05.02.01.02.03 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Girders - Design Complete | 0 d | 0% | 2017-08-25 | 2017-08-25 |  |  |  |  | FY17Q4
210 | Gallagher | Gallagher | Cornell | A1.11.02.02.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 01-LA: North MLC and diagnostics Beam line -System Integration Complete | 0 d | 100% | 2017-08-25 | 2017-08-25 |  |  |  |  | FY17Q4 | FY17Q4(A)
112 | Fumata | Quigley | Cornell | A1.04.04.02.01.04 |  | A1.04 - RF Systems | T-2 | Milestone: 1st Article Solid State Amplifiers (SSA) Received @ Cornell (end of August) | 0 d | 0% | 2017-09-06 | 2017-09-06 |  |  |  |  | FY17Q4
107 | Gulliford | Gulliford | Cornell | A1.03.02.03.04 |  | A1.03 - DC/Gun Injector | T-2 | Milestone: Laser Transport Line - Beam Test (Gun Only) Complete | 0 d | 0% | 2017-09-22 | 2017-09-22 |  |  |  |  | FY17Q4
200 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.03.01 |  | A1.11 - System Integration | T-2 | Milestone: L0 ERF Testing Complete and ready for L0E ERF Move to L0 | 0 d | 0% | 2017-09-25 | 2017-09-25 |  |  |  |  | FY17Q4
149 | Burke | Burke | Cornell | A1.06.02.01.03.03.06 |  | A1.06 - Splitter Magnets | T-2 | Milestones: Extraction Line Magnets - Magnets and Mounts Assembled on Stands | 0 d | 0% | 2017-09-26 | 2017-09-26 |  |  |  |  | FY17Q4
140 | Burke | Burke | Cornell | A1.06.01.01.01.03.01.05 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Septa Magnets - Design complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
115 | Fumata | Quigley | Cornell | A1.04.04.04.01.03 |  | A1.04 - RF Systems | T-2 | Milestone: RF Systems Ready for Fractional Arc Test (FAT) | 0 d | 0% | 2017-10-05 | 2017-10-05 |  |  |  |  | FY18Q1
169 | Dobbins | Michnoff | BNL | A1.08.05.01.05 |  | A1.08 - Controls | T-2 | Milestone: EPICS device support - BPM - Testing Complete | 0 d | 0% | 2017-10-12 | 2017-10-12 |  |  |  |  | FY18Q1
177 | Dobbins | Dobbins | Cornell | A1.08.07.02.03 |  | A1.08 - Controls | T-2 | Milestone: All Timing System Procurements Complete | 0 d | 0% | 2017-10-17 | 2017-10-17 |  |  |  |  | FY18Q1
136 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.15 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - 1st Batch Delivered to Cornell (Sector-SX Northeast) 10/24/17 | 0 d | 0% | 2017-10-26 | 2017-10-26 |  |  |  |  | FY18Q1
158 | Barley | Barley | Cornell | A1.07.04.02.02 |  | A1.07 - Power Supplies | T-2 | Milestone: Contract Awarded - FFAG Corrector Power Supplies | 0 d | 0% | 2017-10-27 | 2017-10-27 |  |  |  |  | FY18Q1
152 | Barley | Barley | Cornell | A1.07.01.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Dipole Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2017-11-07 | 2017-11-07 |  |  |  |  | FY18Q1
154 | Barley | Barley | Cornell | A1.07.02.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Quadrupole Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2017-11-08 | 2017-11-08 |  |  |  |  | FY18Q1
156 | Barley | Barley | Cornell | A1.07.03.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Corrector Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2017-11-08 | 2017-11-08 |  |  |  |  | FY18Q1
166 | Dobbins | Dobbins | Cornell | A1.08.04.01.04.02 |  | A1.08 - Controls | T-2 | Milestone: All EPICS Archiver - Testing Complete | 0 d | 0% | 2017-11-28 | 2017-11-28 |  |  |  |  | FY18Q1
164 | Dobbins | Dobbins | Cornell | A1.08.02.02.04.02 |  | A1.08 - Controls | T-2 | Milestone: All Operator Consoles - Testing Complete | 0 d | 0% | 2017-11-29 | 2017-11-29 |  |  |  |  | FY18Q1
163 | Dobbins | Dobbins | Cornell | A1.08.02.01.04.02 |  | A1.08 - Controls | T-2 | Milestone: All IOC Computers - Testing Complete | 0 d | 0% | 2017-11-30 | 2017-11-30 |  |  |  |  | FY18Q1
168 | Dobbins | Dobbins | Cornell | A1.08.04.03.03.02 |  | A1.08 - Controls | T-2 | Milestone: Configuration Database - Testing Complete | 0 d | 0% | 2017-11-30 | 2017-11-30 |  |  |  |  | FY18Q1
171 | Dobbins | Dobbins | Cornell | A1.08.05.03.03.02 |  | A1.08 - Controls | T-2 | Milestone: EPICS device support - Magnet power supplies - Testing Complete | 0 d | 0% | 2017-11-30 | 2017-11-30 |  |  |  |  | FY18Q1
148 | Burke | Burke | Cornell | A1.06.02.01.02.02.07 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets - Quads - Procurement complete | 0 d | 0% | 2017-12-27 | 2017-12-27 |  |  |  |  | FY18Q1
113 | Fumata | Quigley | Cornell | A1.04.04.02.01.05 |  | A1.04 - RF Systems | T-2 | Milestone: 5 Remaining Solid State Amplifiers (SSA) Received @ Cornell (by end of Dec) | 0 d | 0% | 2017-12-29 | 2017-12-29 |  |  |  |  | FY18Q1
167 | Dobbins | Dobbins | Cornell | A1.08.04.02.04.02 |  | A1.08 - Controls | T-2 | Milestone: All EPICS Alarm Handler - Testing Complete | 0 d | 0% | 2018-01-03 | 2018-01-03 |  |  |  |  | FY18Q2
147 | Burke | Burke | Cornell | A1.06.02.01.01.02.07 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets - Dipoles - Procurement complete | 0 d | 0% | 2018-01-05 | 2018-01-05 |  |  |  |  | FY18Q2
205 | Gallagher | Gallagher | Cornell | A1.11.01.04.02.01 |  | A1.11 - System Integration | T-2 | Milestone: Rack specifications finalized/designed (by 12/31/17 for entire system - SPBT/4PBT) - | 0 d | 0% | 2018-01-09 | 2018-01-09 |  |  |  |  | FY18Q2
201 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.04.04 |  | A1.11 - System Integration | T-2 | Milestone: East RF System Relocation Complete | 0 d | 0% | 2018-01-19 | 2018-01-19 |  |  |  |  | FY18Q2
141 | Burke | Burke | Cornell | A1.06.01.01.01.05.02.03 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Magnets & Hardware - Pre-Table Installation Complete (FAT) | 0 d | 0% | 2018-01-26 | 2018-01-26 |  |  |  |  | FY18Q2
189 | Dobbins | Dobbins | Cornell | A1.09.05.06.03.02 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Stops Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-02-05 | 2018-02-05 |  |  |  |  | FY18Q2
170 | Dobbins | Michnoff | BNL | A1.08.05.02.05 |  | A1.08 - Controls | T-2 | Milestone: EPICS device support - BAM - Testing Complete | 0 d | 0% | 2018-02-14 | 2018-02-14 |  |  |  |  | FY18Q2
190 | Dobbins | Dobbins | Cornell | A1.09.05.07.02.01.07 |  | A1.09 - Instrumentation | T-2 | Milestone: FAT - Instrumentation System Testing Complete | 0 d | 0% | 2018-02-20 | 2018-02-20 |  |  |  |  | FY18Q2
114 | Fumata | Quigley | Cornell | A1.04.04.03.11 |  | A1.04 - RF Systems | T-2 | Milestone - RF Amplifier/Deflector RF Cavity System Installation Complete | 0 d | 0% | 2018-02-21 | 2018-02-21 |  |  |  |  | FY18Q2
180 | Dobbins | Dobbins | Cornell | A1.08.09.02.02.01.01.16 |  | A1.08 - Controls | T-2 | Milestone: Fractional Arc Test - Integrated pre-beam testing for all Controls System Complete | 0 d | 0% | 2018-02-22 | 2018-02-22 |  |  |  |  | FY18Q2
142 | Burke | Burke | Cornell | A1.06.01.01.01.05.02.04 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Magnets & Hardware - Pre-Table Installation Compete (SPBT & 4PBT) | 0 d | 0% | 2018-03-05 | 2018-03-05 |  |  |  |  | FY18Q2
207 | Gallagher | Gallagher | Cornell | A1.11.01.04.07.03.03 |  | A1.11 - System Integration | T-2 | Milestone: East Wall Modifications (Penetrations) Complete | 0 d | 0% | 2018-03-09 | 2018-03-09 |  |  |  |  | FY18Q2
178 | Dobbins | Dobbins | Cornell | A1.08.08.04.06 |  | A1.08 - Controls | T-2 | Milestone: Machine Protection System - Installation and Testing - complete and ready for (FAT) Test | 0 d | 0% | 2018-03-13 | 2018-03-13 |  |  |  |  | FY18Q2
117 | Fumata | Sabol | Cornell | A1.04.05.02.02.03.10 |  | A1.04 - RF Systems | T-2 | Milestone: MLC Pump Skid #2-3-4 - Installation Complete | 0 d | 0% | 2018-03-22 | 2018-03-22 |  |  |  |  | FY18Q2
129 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.12 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Girders Procurements complete | 0 d | 0% | 2018-03-23 | 2018-03-23 |  |  |  |  | FY18Q2
159 | Barley | Barley | Cornell | A1.07.04.02.08 |  | A1.07 - Power Supplies | T-2 | Milestone: All FFAG Corrector PS Procurement Received | 0 d | 0% | 2018-03-28 | 2018-03-28 |  |  |  |  | FY18Q2
232 | Widger | Heltsely | Cornell | A1.13.01.03.06 |  | A1.13 - Safety | T-2 | Milestone: x-Ray Permit for Fractional Arc Test Approved | 0 d | 0% | 2018-03-30 | 2018-03-30 |  |  |  |  | FY18Q2
196 | Li | Li | Cornell | A1.10.04.03.09 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc Assemblies Complete for FAT Test | 0 d | 0% | 2018-04-03 | 2018-04-03 |  |  |  |  | FY18Q3
188 | Dobbins | Dobbins | Cornell | A1.09.05.05.02.05 |  | A1.09 - Instrumentation | T-2 | Milestone: All View Screen Procurements Complete | 0 d | 0% | 2018-04-04 | 2018-04-04 |  |  |  |  | FY18Q3
183 | Dobbins | Dobbins | Cornell | A1.09.02.03.07 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Arrival Monitors Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-04-12 | 2018-04-12 |  |  |  |  | FY18Q3
109 | Fumata | Quigley | Cornell | A1.04.01.03.01.05 |  | A1.04 - RF Systems | T-2 | Milestone: MLC Cool Down #2A - RF Power Turned On and MLC System Stable | 0 d | 0% | 2018-04-16 | 2018-04-16 |  |  |  |  | FY18Q3
151 | Burke | Burke | Cornell | A1.06.02.03.01.06 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets and Tables - Assembly (SPBT) - Complete | 0 d | 0% | 2018-04-18 | 2018-04-18 |  |  |  |  | FY18Q3
160 | Barley | Barley | Cornell | A1.07.04.03.03.03 |  | A1.07 - Power Supplies | T-2 | Milestone: FFAG Corrector Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2018-04-25 | 2018-04-25 |  |  |  |  | FY18Q3
137 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.16 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - 2nd Batch Delivered to Cornell (Sector-RX - Northwest) 4/20/18 | 0 d | 0% | 2018-04-26 | 2018-04-26 |  |  |  |  | FY18Q3
153 | Barley | Barley | Cornell | A1.07.01.03.03.05 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Dipole Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | FY18Q3
155 | Barley | Barley | Cornell | A1.07.02.03.03.05 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Quadrupole Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | FY18Q3
157 | Barley | Barley | Cornell | A1.07.03.03.03.05 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Corrector Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-05-01 | 2018-05-01 |  |  |  |  | FY18Q3
195 | Li | Li | Cornell | A1.10.04.02.06 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc System - All Procurements complete | 0 d | 0% | 2018-05-08 | 2018-05-08 |  |  |  |  | FY18Q3
197 | Li | Li | Cornell | A1.10.04.03.10 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc Assemblies Complete for SPBT/Remainder | 0 d | 0% | 2018-05-11 | 2018-05-11 |  |  |  |  | FY18Q3
111 | Fumata | Quigley | Cornell | A1.04.03.01.02.03 |  | A1.04 - RF Systems | T-2 | Milestone: SPBT - LLRF Design Updates Complete | 0 d | 0% | 2018-06-04 | 2018-06-04 |  |  |  |  | FY18Q3
144 | Burke | Burke | Cornell | A1.06.01.03.01.08 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets and Tables - Assembly (FAT) - Complete | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | FY18Q3
193 | Li | Li | Cornell | A1.10.01.02.06 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Global Vacuum System - Procurements complete | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | FY18Q3
138 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.21 |  | A1.06 - Splitter Magnets | T-2(3?) | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - ALL Procurements complete | 0 d | 0% | 2018-06-14 | 2018-06-14 |  |  |  |  | FY18Q3
126 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.01.03.04 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Vendor Procurement [BNL]: Production FFAG Magnets - Permanent Magnet Blocks -All Lots Received @ BNL | 0 d | 0% | 2018-06-25 | 2018-06-25 |  |  |  |  | FY18Q3
198 | Gallagher | Gallagher | Cornell | A1.11.01.01.01.06 |  | A1.11 - System Integration | T-2 | Milestone: CESR 2018 CHESS-U Commissioning/Startup | 0 d | 0% | 2018-06-27 | 2018-06-27 |  |  |  |  | FY18Q3
220 | Gallagher | Gallagher | Cornell | A1.11.02.09.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 08-FB: West Arc -System Integration Complete | 0 d | 0% | 2018-07-09 | 2018-07-09 |  |  |  |  | FY18Q4
116 | Fumata | Quigley | Cornell | A1.04.04.04.02.02 |  | A1.04 - RF Systems | T-2 | Milestone: RF Systems Ready for SPBT | 0 d | 0% | 2018-07-10 | 2018-07-10 |  |  |  |  | FY18Q4
230 | Widger | Kostroun | Cornell | A1.13.01.01.05 |  | A1.13 - Safety | T-2 | Milestone: Shielding Calculations/Physics Design Completed | 0 d | 0% | 2018-07-10 | 2018-07-10 |  |  |  |  | FY18Q4
211 | Gallagher | Gallagher | Cornell | A1.11.02.03.01.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 02-SX (FAT) Northeast Splitter - System Integration Complete | 0 d | 0% | 2018-07-16 | 2018-07-16 |  |  |  |  | FY18Q4
221 | Gallagher | Gallagher | Cornell | A1.11.02.10.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 09-RX: Northwest Splitter -System Integration Complete | 0 d | 0% | 2018-07-23 | 2018-07-23 |  |  |  |  | FY18Q4
226 | Bartnik | Bartnik | Cornell | A1.12.04.05 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Fractional Arc Test - Commissioning Complete | 0 d | 0% | 2018-07-27 | 2018-07-27 |  |  |  |  | FY18Q4
213 | Gallagher | Gallagher | Cornell | A1.11.02.03.03.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 02-SX (4PBT): Northeast Splitter -System Integration Complete | 0 d | 0% | 2018-07-31 | 2018-07-31 |  |  |  |  | FY18Q4
161 | Barley | Barley | Cornell | A1.07.04.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: FFAG Corrector Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-08-07 | 2018-08-07 |  |  |  |  | FY18Q4
216 | Gallagher | Gallagher | Cornell | A1.11.02.05.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 04-TA: South Southeast arc -System Integration Complete | 0 d | 0% | 2018-08-10 | 2018-08-10 |  |  |  |  | FY18Q4
145 | Burke | Burke | Cornell | A1.06.01.03.02.08 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets and Tables - Assembly (SPBT) - Complete | 0 d | 0% | 2018-08-15 | 2018-08-15 |  |  |  |  | FY18Q4
222 | Gallagher | Gallagher | Cornell | A1.11.02.11.04.07 |  | A1.11 - System Integration | T-2 | Milestone: Sector 10-BS: Beam stop - System Integration Complete | 0 d | 0% | 2018-08-20 | 2018-08-20 |  |  |  |  | FY18Q4
172 | Dobbins | Dobbins | Cornell | A1.08.06.01.02.02 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - Software development complete | 0 d | 0% | 2018-08-21 | 2018-08-21 |  |  |  |  | FY18Q4
187 | Dobbins | Michnoff | BNL | A1.09.05.03.02.03 |  | A1.09 - Instrumentation | T-2 | Milestone: BPM Assembly/Development - DAQ Electronics Complete and ready for Final testing | 0 d | 0% | 2018-08-21 | 2018-08-21 |  |  |  |  | FY18Q4
185 | Dobbins | Dobbins | Cornell | A1.09.04.03.04 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Loss Monitors Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-08-27 | 2018-08-27 |  |  |  |  | FY18Q4
203 | Gallagher | Gallagher | Cornell | A1.11.01.03.03.03.03 |  | A1.11 - System Integration | T-2 | Milestone: CESR-85F Cooling System Relocation Complete | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | FY18Q4
212 | Gallagher | Gallagher | Cornell | A1.11.02.03.02.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 02-SX (SPBT) - Northeast Splitter - System Integration Complete | 0 d | 0% | 2018-09-17 | 2018-09-17 |  |  |  |  | FY18Q4
214 | Gallagher | Gallagher | Cornell | A1.11.02.04.01.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 03-FA (FAT): East Arc -System Integration Complete | 0 d | 0% | 2018-09-18 | 2018-09-18 |  |  |  |  | FY18Q4
215 | Gallagher | Gallagher | Cornell | A1.11.02.04.02.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 03-FA (SPBT-4PBT): East Arc -System Integration Complete | 0 d | 0% | 2018-09-18 | 2018-09-18 |  |  |  |  | FY18Q4
173 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.01.03 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - SPBT hardware installation complete | 0 d | 0% | 2018-09-19 | 2018-09-19 |  |  |  |  | FY18Q4
104 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.02.01 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Design optics for two, three, and four ERL loops finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | FY18Q4
105 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.02.03 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Tracking of beam through full loops and check acceptance at dump complete | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | FY18Q4
146 | Burke | Burke | Cornell | A1.06.01.03.03.08 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets and Tables - Assembly (4PBT) - Complete | 0 d | 0% | 2018-10-04 | 2018-10-04 |  |  |  |  | FY19Q1
217 | Gallagher | Gallagher | Cornell | A1.11.02.06.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 05-ZA: Southeast straight -System Integration Complete | 0 d | 0% | 2018-10-09 | 2018-10-09 |  |  |  |  | FY19Q1
204 | Gallagher | Gallagher | Cornell | A1.11.01.04.01.07 |  | A1.11 - System Integration | T-2 | Milestone: CBETA Global Layout Plans Complete | 0 d | 0% | 2018-10-18 | 2018-10-18 |  |  |  |  | FY19Q1
208 | Gallagher | Gallagher | Cornell | A1.11.01.04.09.03.02 |  | A1.11 - System Integration | T-2 | Milestone: Electrical System Installation Complete | 0 d | 0% | 2018-10-25 | 2018-10-25 |  |  |  |  | FY19Q1
127 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.01.07.04 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets Halbach Magnets Assembly (Magnet, Housing, Windowframe Corrector) - ALL Sectors Received @ BNL [Qty: xx] | 0 d | 0% | 2018-11-27 | 2018-11-27 |  |  |  |  | FY19Q1
128 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.01.08 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets ALL Procurements complete and received from vendor | 0 d | 0% | 2018-11-27 | 2018-11-27 |  |  |  |  | FY19Q1
130 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.03 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: ALL Sectors - Measuring and adjusting Halbach Magnet Assemblies Complete [Qty: xx] | 0 d | 0% | 2018-12-04 | 2018-12-04 |  |  |  |  | FY19Q1
218 | Gallagher | Gallagher | Cornell | A1.11.02.07.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 06-ZB: Southwest straight -System Integration Complete | 0 d | 0% | 2018-12-07 | 2018-12-07 |  |  |  |  | FY19Q1
184 | Dobbins | Dobbins | Cornell | A1.09.03.03.04 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Current Monitors Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-12-17 | 2018-12-17 |  |  |  |  | FY19Q1
233 | Widger | Heltsely | Cornell | A1.13.01.04.04 |  | A1.13 - Safety | T-2 | Milestone: x-Ray permit for SPBT Approved (No additional permits needed for 4PBT) | 0 d | 0% | 2018-12-19 | 2018-12-19 |  |  |  |  | FY19Q1
131 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.04.02.07 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: ALL Sectors - Survey & Testing of Halbach Magnet Assemblies Complete [Qty: xx] | 0 d | 0% | 2019-01-04 | 2019-01-04 |  |  |  |  | FY19Q2
134 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.03.03.07 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets and Girders - ALL Sectors - Halbach Magnets & Girder Ship to Cornell complete | 0 d | 0% | 2019-01-24 | 2019-01-24 |  |  |  |  | FY19Q2
209 | Gallagher | Gallagher | Cornell | A1.11.02.01.01 |  | A1.11 - System Integration | T-2 | Milestone: All BNL Magnets and Hardware Received for Installation in L0E | 0 d | 0% | 2019-01-24 | 2019-01-24 |  |  |  |  | FY19Q2
219 | Gallagher | Gallagher | Cornell | A1.11.02.08.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 07-TB: Southwest Arc -System Integration Complete | 0 d | 0% | 2019-02-07 | 2019-02-07 |  |  |  |  | FY19Q2
179 | Dobbins | Dobbins | Cornell | A1.08.08.04.09 |  | A1.08 - Controls | T-2 | Milestone: Machine Protection System - Installation and Testing - complete and ready for SPBT | 0 d | 0% | 2019-02-13 | 2019-02-13 |  |  |  |  | FY19Q2
133 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.04.02.07 |  | A1.05 - FFAG Magnets & Girders | T-2 | FFAG Production Magnets and Girders - ALL Sectors - ALL Halbach Magnet & Girder Assembly, Survey, Testing, and Documentation Complete [Qty: xx] | 0 d | 0% | 2019-03-08 | 2019-03-08 |  |  |  |  | FY19Q2
132 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.04.04 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets - Pre-Girder Halbach Magnet Assembly tests & documentation complete | 0 d | 0% | 2019-03-12 | 2019-03-12 |  |  |  |  | FY19Q2
110 | Fumata | Quigley | Cornell | A1.04.01.04.02.04 |  | A1.04 - RF Systems | T-2 | Milestone: MLC Cool Down #3 - RF Power Turned On and MLC System Stable | 0 d | 0% | 2019-04-15 | 2019-04-15 |  |  |  |  | FY19Q3
174 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.01.06 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - SPBT - commissioning with beam complete | 0 d | 0% | 2019-05-08 | 2019-05-08 |  |  |  |  | FY19Q3
181 | Dobbins | Dobbins | Cornell | A1.08.09.03.02.02.16 |  | A1.08 - Controls | T-2 | Milestone: Controls - SPBT - Commissioning with Beam for all Controls System Complete | 0 d | 0% | 2019-05-08 | 2019-05-08 |  |  |  |  | FY19Q3
191 | Dobbins | Dobbins | Cornell | A1.09.05.07.03.01.08 |  | A1.09 - Instrumentation | T-2 | Milestone: SPBT - Instrumentation System Testing Complete | 0 d | 0% | 2019-07-10 | 2019-07-10 |  |  |  |  | FY19Q4
227 | Bartnik | Bartnik | Cornell | A1.12.05.07 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Single Pass Energy Scan - Commissioning Complete | 0 d | 0% | 2019-09-19 | 2019-09-19 |  |  |  |  | FY19Q4
206 | Gallagher | Gallagher | Cornell | A1.11.01.04.04.02.03 |  | A1.11 - System Integration | T-2 | Milestone: Shielding Installation Complete | 0 d | 0% | 2019-10-04 | 2019-10-04 |  |  |  |  | FY20Q1
175 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.02.01 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - 4PBT hardware installation complete | 0 d | 0% | 2019-10-07 | 2019-10-07 |  |  |  |  | FY20Q1
182 | Dobbins | Dobbins | Cornell | A1.08.09.04.02.02.16 |  | A1.08 - Controls | T-2 | Milestone: Controls - 4PBT - Commissioning with Beam for all Controls System Complete | 0 d | 0% | 2019-12-02 | 2019-12-02 |  |  |  |  | FY20Q1
176 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.02.04 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - 4PBT - Commissioning with beam complete | 0 d | 0% | 2019-12-20 | 2019-12-20 |  |  |  |  | FY20Q1
192 | Dobbins | Dobbins | Cornell | A1.09.05.07.04.01.07 |  | A1.09 - Instrumentation | T-2 | Milestone: 4PBT - Instrumentation System Testing Complete | 0 d | 0% | 2020-01-21 | 2020-01-21 |  |  |  |  | FY20Q2
228 | Bartnik | Bartnik | Cornell | A1.12.06.05 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Single Pass Energy Recovery - Commissioning Complete | 0 d | 0% | 2020-02-04 | 2020-02-04 |  |  |  |  | FY20Q2
234 | Widger | Widger | Cornell | A1.13.04.01.09 |  | A1.13 - Safety | T-2 | Milestone: All Radiation Monitoring Procurements Received | 0 d | 0% | 2020-04-29 | 2020-04-29 |  |  |  |  | FY20Q2
229 | Bartnik | Bartnik | Cornell | A1.12.07.05 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Four Pass Energy Recovery - Commissioning Complete | 0 d | 0% | 2020-05-06 | 2020-05-06 |  |  |  |  | FY20Q2
500 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.01.06 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY17 - Complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
501 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.01 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design Activities Starts | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | FY17Q1 | FY17Q1(A)
502 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.02 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Initial Baseline Lattice Design Complete | 0 d | 100% | 2016-11-17 | 2016-11-17 |  |  |  |  | FY17Q1 | FY17Q1(A)
503 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Final Baseline Lattice Design complete | 0 d | 100% | 2017-04-10 | 2017-04-10 |  |  |  |  | FY17Q3 | FY17Q3(A)
504 | Hoffstaetter | Berg | Cornell | A1.02.01.02.06 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Finalize mechanical coordinates of the lattice - FFAG beam pipe and magnet girders | 0 d | 0% | 2017-08-24 | 2017-08-24 |  |  |  |  | FY17Q4
505 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.07 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Lattice Design Updates/Adjustment for Fractional Arc Test Complete | 0 d | 100% | 2017-06-01 | 2017-06-01 |  |  |  |  | FY17Q3 | FY17Q3(A)
506 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.09 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics with suitable high-energy septum finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
507 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.10 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics for low-energy septum finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
508 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.11 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design of transition Halbach with reduced QF and BDTs finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
509 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.12 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design lattice for the prototype magnets finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
510 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.13 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design lattice for splitter line to match the full energy range finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
511 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.14 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Simulation of orbit correction for the full energy range complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
512 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.15 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Simulation of aperture measurements with beam-loss monitors complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
513 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.16 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Complete optics for each accelerating and recirculating pass finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
514 | Hoffstaetter | Liu | Cornell | A1.02.01.02.17 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Finalize mechanical coordinates of the lattice - Splitter beam pipe and magnet girders | 0 d | 0% | 2017-06-20 | 2017-06-20 |  |  |  |  | FY17Q3
515 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.01.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY18 - Complete | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | FY18Q4
516 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.01 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Lattice Design Updates/Adjustment for SPBT Complete | 0 d | 0% | 2017-06-01 | 2017-06-01 |  |  |  |  | FY17Q3
517 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.03 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics from source through MLC(1) with space charge finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
518 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics for one ERL turn through splitter and FFAG finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | FY18Q4
519 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.05 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design dump line for maximal energy spread and track beam finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | FY18Q4
520 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.06 |  | A1.02 - Accelerator Physics | T-3 | Milestone: (SPB) Simulation of beam-loss scenarios, including ions, Touschek, wakes, etc. complete | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | FY18Q4
521 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.01.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY19 - Complete | 0 d | 0% | 2019-10-07 | 2019-10-07 |  |  |  |  | FY20Q1
522 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.02.02 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design of orbit correction for two, three, and four ERL loops finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | FY18Q4
523 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.04.01.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY20 - Complete | 0 d | 0% | 2020-05-06 | 2020-05-06 |  |  |  |  | FY20Q2
524 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.04.02.01 |  | A1.02 - Accelerator Physics | T-3 | Milestone: (4PB) Simulation of beam-loss scenarios, including ions, Touschek, wakes, etc. complete | 0 d | 0% | 2019-10-16 | 2019-10-16 |  |  |  |  | FY20Q1
525 | Gulliford | Gulliford | Cornell | A1.03.01.01.01.01.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: Start of DC Gun Conditioning Activities | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | FY17Q1 | FY17Q1(A)
526 | Gulliford | Bartnik | Cornell | A1.03.02.01.02.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - E/O Modulator | 0 d | 0% | 2017-07-12 | 2017-07-12 |  |  |  |  | FY17Q4
527 | Gulliford | Bartnik | Cornell | A1.03.02.01.03.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: E/O Modulator Software Development Complete | 0 d | 0% | 2017-09-07 | 2017-09-07 |  |  |  |  | FY17Q4
528 | Gulliford | Bartnik | Cornell | A1.03.02.02.01.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - 43 MHz Laser Parts | 0 d | 100% | 2017-05-05 | 2017-05-05 |  |  |  |  | FY17Q3 | FY17Q3(A)
529 | Gulliford | Bartnik | Cornell | A1.03.02.02.02.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: 43 MHz Laser - Modification and Table Set-up Complete | 0 d | 0% | 2017-09-13 | 2017-09-13 |  |  |  |  | FY17Q4
530 | Gulliford | Cultrera | Cornell | A1.03.03.01.02 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - Cathode Material | 0 d | 0% | 2018-01-25 | 2018-01-25 |  |  |  |  | FY18Q2
531 | Gulliford | Cultera | Cornell | A1.03.03.02.01.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: Preliminary Cathode Material Existing and Available @ Cornell | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | FY17Q3 | FY17Q3(A)
532 | Gulliford | Cultera | Cornell | A1.03.03.02.02.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: FAT Cathode Material Available @ Cornell | 0 d | 100% | 2017-08-31 | 2017-08-31 |  |  |  |  | FY17Q4 | FY17Q4(A)
533 | Gulliford | Cultera | Cornell | A1.03.03.02.03.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: SPBT Cathode Material Available @ Cornell | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | FY18Q3
534 | Gulliford | Cultera | Cornell | A1.03.03.02.04.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: SPBT-ER Cathode Material Available @ Cornell | 0 d | 0% | 2019-06-30 | 2019-06-30 |  |  |  |  | FY19Q3
535 | Gulliford | Cultera | Cornell | A1.03.03.02.05.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: 4PBT Cathode Material Available @ Cornell | 0 d | 0% | 2019-10-31 | 2019-10-31 |  |  |  |  | FY20Q1
536 | Gulliford | Gulliford | Cornell | A1.03.04.01.02 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B1 Merger - Transport Line Layout & Drawings Complete | 0 d | 100% | 2017-02-20 | 2017-02-20 |  |  |  |  | FY17Q2 | FY17Q2(A)
537 | Gulliford | Gulliford | Cornell | A1.03.04.02.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - 80x20 Stand/Girders | 0 d | 100% | 2017-03-16 | 2017-03-16 |  |  |  |  | FY17Q2 | FY17Q2(A)
538 | Gulliford | Gulliford | Cornell | A1.03.04.03.08 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B1 Merger Installation Complete | 0 d | 100% | 2017-04-26 | 2017-04-26 |  |  |  |  | FY17Q3 | FY17Q3(A)
539 | Gulliford | Gulliford | Cornell | A1.03.04.04.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B1 Merger Beam Line Instrumentation Integration Complete | 0 d | 100% | 2017-05-02 | 2017-05-02 |  |  |  |  | FY17Q3 | FY17Q3(A)
540 | Gulliford | Gulliford | Cornell | A1.03.05.01.01.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 DL - Transport Line Layout & Drawings Complete | 0 d | 100% | 2017-03-22 | 2017-03-22 |  |  |  |  | FY17Q2 | FY17Q2(A)
541 | Gulliford | Gulliford | Cornell | A1.03.05.01.02.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 DL - Cross Pipe Layout & Drawings Complete | 0 d | 0% | 2018-02-08 | 2018-02-08 |  |  |  |  | FY18Q2
542 | Gulliford | Gulliford | Cornell | A1.03.05.02.01.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received and Accepted - B2 DL Magnets | 0 d | 100% | 2017-06-26 | 2017-06-26 |  |  |  |  | FY17Q3 | FY17Q3(A)
543 | Gulliford | Gulliford | Cornell | A1.03.05.02.02.07 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All B2 DL Vacuum Transport Line Materials Received | 0 d | 100% | 2017-04-12 | 2017-04-12 |  |  |  |  | FY17Q3 | FY17Q3(A)
544 | Gulliford | Gulliford | Cornell | A1.03.05.02.03.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All B2 DL Cross Pipe Materials Received | 0 d | 0% | 2018-03-30 | 2018-03-30 |  |  |  |  | FY18Q2
545 | Gulliford | Gulliford | Cornell | A1.03.05.03.01.05 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 Diagnostic Beam Line (FY17) Installation Complete | 0 d | 100% | 2017-05-04 | 2017-05-04 |  |  |  |  | FY17Q3 | FY17Q3(A)
546 | Gulliford | Gulliford | Cornell | A1.03.05.03.02.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 Diagnostic Beam Line (FY18) Installation Complete | 0 d | 0% | 2018-04-10 | 2018-04-10 |  |  |  |  | FY18Q3
547 | Fumata | Quigley | Cornell | A1.04.01.01.01.01 |  | A1.04 - RF Systems | T-3 | Milestone: MLC ready for CBETA work | 0 d | 100% | 2016-12-01 | 2016-12-01 |  |  |  |  | FY17Q1 | FY17Q1(A)
548 | Fumata | Quigley | Cornell | A1.04.01.01.02.06 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Warmed Up and Ready for Disconnects | 0 d | 100% | 2016-12-22 | 2016-12-22 |  |  |  |  | FY17Q1 | FY17Q1(A)
549 | Fumata | Quigley | Cornell | A1.04.01.01.03.03 |  | A1.04 - RF Systems | T-3 | Milestone: MLC in final Location | 0 d | 100% | 2017-01-12 | 2017-01-12 |  |  |  |  | FY17Q2 | FY17Q2(A)
550 | Fumata | Quigley | Cornell | A1.04.01.02.01.04 |  | A1.04 - RF Systems | T-3 | MLC Cool Down #2 - Cool down to 4K (by Apr 3) | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | FY17Q3 | FY17Q3(A)
551 | Fumata | Quigley | Cornell | A1.04.01.02.01.06 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #2 - Ready for RF Power (by 4/20) | 0 d | 100% | 2017-04-20 | 2017-04-20 |  |  |  |  | FY17Q3 | FY17Q3(A)
552 | Fumata | Quigley | Cornell | A1.04.01.02.01.07 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #2 - RF Power Turned On and MLC System Stable by 5/2 | 0 d | 100% | 2017-05-03 | 2017-05-03 |  |  |  |  | FY17Q3 | FY17Q3(A)
553 | Fumata | Quigley | Cornell | A1.04.01.03.01.04 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #2A - Ready for RF Power | 0 d | 0% | 2018-04-02 | 2018-04-02 |  |  |  |  | FY18Q3
554 | Fumata | Quigley | Cornell | A1.04.01.04.02.03 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #3 - Ready for RF Power | 0 d | 0% | 2019-04-15 | 2019-04-15 |  |  |  |  | FY19Q3
555 | Fumata | Quigley | Cornell | A1.04.02.01.01 |  | A1.04 - RF Systems | T-3 | Milestone: ICM ready for CBETA work | 0 d | 100% | 2016-12-01 | 2016-12-01 |  |  |  |  | FY17Q1 | FY17Q1(A)
556 | Fumata | Quigley | Cornell | A1.04.02.02.06 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Warmed Up and Ready for Disconnects | 0 d | 100% | 2016-11-21 | 2016-11-21 |  |  |  |  | FY17Q1 | FY17Q1(A)
557 | Fumata | Quigley | Cornell | A1.04.02.03.01.05 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Cool Down #2 - Ready for RF Power (by 4/20) | 0 d | 100% | 2017-04-20 | 2017-04-20 |  |  |  |  | FY17Q3 | FY17Q3(A)
558 | Fumata | Quigley | Cornell | A1.04.02.03.01.06 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Cool Down #2 - RF Power Turned On and ICM System Stable by 5/2 | 0 d | 100% | 2017-05-03 | 2017-05-03 |  |  |  |  | FY17Q3 | FY17Q3(A)
559 | Fumata | Quigley | Cornell | A1.04.03.01.01.05 |  | A1.04 - RF Systems | T-3 | Milestone: FAT - LLRF Design Complete | 0 d | 100% | 2017-02-22 | 2017-02-22 |  |  |  |  | FY17Q2 | FY17Q2(A)
560 | Fumata | Quigley | Cornell | A1.04.03.02.01.05 |  | A1.04 - RF Systems | T-3 | Milestone: All LLRF Material/Components (FAT) Complete | 0 d | 0% | 2017-10-10 | 2017-10-10 |  |  |  |  | FY18Q1
561 | Fumata | Quigley | Cornell | A1.04.03.02.02.05 |  | A1.04 - RF Systems | T-3 | Milestone: All LLRF Material/Components (SPBT) Complete | 0 d | 0% | 2018-08-28 | 2018-08-28 |  |  |  |  | FY18Q4
562 | Fumata | Quigley | Cornell | A1.04.03.03.01.07 |  | A1.04 - RF Systems | T-3 | Milestone: LLRF (FAT) Installation & Integration Complete | 0 d | 0% | 2017-12-26 | 2017-12-26 |  |  |  |  | FY18Q1
563 | Fumata | Quigley | Cornell | A1.04.03.03.02.05 |  | A1.04 - RF Systems | T-3 | Milestone: LLRF (SPBT) Installation & Integration Complete | 0 d | 0% | 2018-09-26 | 2018-09-26 |  |  |  |  | FY18Q4
564 | Fumata | Quigley | Cornell | A1.04.04.02.01.09 |  | A1.04 - RF Systems | T-3 | Milestone: All RF Amplifier Procurements Received and Complete | 0 d | 0% | 2017-12-29 | 2017-12-29 |  |  |  |  | FY18Q1
565 | Fumata | Quigley | Cornell | A1.04.04.02.02.06 |  | A1.04 - RF Systems | T-3 | Milestone: All Waveguide & Tuner Procurements Received and Complete | 0 d | 0% | 2017-05-08 | 2017-05-08 |  |  |  |  | FY17Q3
566 | Fumata | Sabol | Cornell | A1.04.05.01.01.01.03.03 |  | A1.04 - RF Systems | T-3 | Milestone: All Cryogenic MLC Transferline Procurements Received and Complete | 0 d | 100% | 2017-02-24 | 2017-02-24 |  |  |  |  | FY17Q2 | FY17Q2(A)
567 | Fumata | Sabol | Cornell | A1.04.05.01.02.02.03 |  | A1.04 - RF Systems | T-3 | Milestone: All Cryogenic MLC Transferline Procurements Received and Complete | 0 d | 100% | 2017-03-10 | 2017-03-10 |  |  |  |  | FY17Q2 | FY17Q2(A)
568 | Fumata | Sabol | Cornell | A1.04.05.01.03.03 |  | A1.04 - RF Systems | T-3 | Milestone: All Cryogenic MLC Transferline Installation & Leak Test Complete | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | FY17Q3 | FY17Q3(A)
569 | Fumata | Sabol | Cornell | A1.04.05.02.01.01.02 |  | A1.04 - RF Systems | T-3 | Milestone: Design Pump System Layout (#1) Complete | 0 d | 100% | 2016-11-07 | 2016-11-07 |  |  |  |  | FY17Q1 | FY17Q1(A)
570 | Fumata | Sabol | Cornell | A1.04.05.02.01.02.07 |  | A1.04 - RF Systems | T-3 | Milestone: Pump Skid #1 - All Procurement Materials Received and Ready for Installation | 0 d | 100% | 2017-03-10 | 2017-03-10 |  |  |  |  | FY17Q2 | FY17Q2(A)
571 | Fumata | Sabol | Cornell | A1.04.05.02.01.03.09.04 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Pump Skid #1 - Vibration Mitigation Complete | 0 d | 0% | 2018-05-09 | 2018-05-09 |  |  |  |  | FY18Q3
572 | Fumata | Sabol | Cornell | A1.04.05.02.01.03.10 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Pump Skid#1 Installation Complete | 0 d | 0% | 2018-05-09 | 2018-05-09 |  |  |  |  | FY18Q3
573 | Fumata | Sabol | Cornell | A1.04.05.02.02.01.02 |  | A1.04 - RF Systems | T-3 | Milestone: Design Pump System Layout (#2-3-4) Complete | 0 d | 0% | 2017-09-28 | 2017-09-28 |  |  |  |  | FY17Q4
574 | Fumata | Sabol | Cornell | A1.04.05.02.02.02.08 |  | A1.04 - RF Systems | T-3 | Milestone: Pump Skid #2-3-4 - All Procurement Materials Received and Ready for Installation | 0 d | 0% | 2018-01-30 | 2018-01-30 |  |  |  |  | FY18Q2
575 | Fumata | Sabol | Cornell | A1.04.05.02.02.03.08.02 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Pump Skid #2-3-4 - Vibration Mitigation Complete | 0 d | 0% | 2018-03-15 | 2018-03-15 |  |  |  |  | FY18Q2
576 | Fumata | Sabol | Cornell | A1.04.05.03.01.01.04 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Pump Skids - All Procurement Materials Received and Ready for Installation | 0 d | 0% | 2017-10-10 | 2017-10-10 |  |  |  |  | FY18Q1
577 | Fumata | Sabol | Cornell | A1.04.05.03.01.02.10 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Pump Skids- Installation Complete | 0 d | 0% | 2017-11-27 | 2017-11-27 |  |  |  |  | FY18Q1
578 | Tuozzolo | Tuozzolo | BNL | A1.05.01.01.01.04 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: PreProd FFAG Magnets - Halbach magnet w/ corrector design complete | 0 d | 100% | 2017-03-01 | 2017-03-01 |  |  |  |  | FY17Q2 | FY17Q2(A)
579 | Tuozzolo | Tuozzolo | BNL | A1.05.01.01.02.03 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: PreProd FFAG Girder - Design Complete | 0 d | 100% | 2017-03-17 | 2017-03-17 |  |  |  |  | FY17Q2 | FY17Q2(A)
580 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.01.02 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: PreProd FFAG Magnets - PMM measurements complete and documented | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | FY17Q3 | FY17Q3(A)
581 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.03.01 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Vacuum Chambers Received from Cornell for Pre-Production FFAG Magnet Assembly as of 4/24 | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | FY17Q3 | FY17Q3(A)
582 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.08 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - 1st Article Table Top plate Procurement complete and received @ BNL | 0 d | 0% | 2018-01-25 | 2018-01-25 |  |  |  |  | FY18Q2
583 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.09 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - ALL Top plate Procurement complete and received @ BNL | 0 d | 0% | 2018-03-23 | 2018-03-23 |  |  |  |  | FY18Q2
584 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.10 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - 1st Article Frame/Stand Procurements complete and received @ Cornell in time for FAT | 0 d | 0% | 2018-01-25 | 2018-01-25 |  |  |  |  | FY18Q2
585 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.11 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - ALL Frame/Stand Procurements complete and received @ Cornell | 0 d | 0% | 2018-03-23 | 2018-03-23 |  |  |  |  | FY18Q2
586 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.04.03 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Magnets - Pre-Girder Halbach Magnet Assembly 1st Article tests & documentation complete | 0 d | 0% | 2018-02-26 | 2018-02-26 |  |  |  |  | FY18Q2
587 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.01 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Vacuum Chambers Received from Cornell for Production Magnet Assembly (1st Article) - FAGD1 | 0 d | 0% | 2018-04-10 | 2018-04-10 |  |  |  |  | FY18Q3
588 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.02 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: FFAG Arc&Transition Vacuum Chambers Received from Cornell for Production Magnet Assembly (Remainder) (Multiple shipments per diagram on Yulins layout) | 0 d | 0% | 2018-05-18 | 2018-05-18 |  |  |  |  | FY18Q3
589 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.03 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: FFAG Straight Vacuum Chambers Received from Cornell for Production Magnet Assembly (Remainder) | 0 d | 0% | 2018-03-28 | 2018-03-28 |  |  |  |  | FY18Q2
590 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Dipoles - Design complete | 0 d | 100% | 2017-01-27 | 2017-01-27 |  |  |  |  | FY17Q2 | FY17Q2(A)
591 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Quadrupoles - Design complete | 0 d | 100% | 2017-01-27 | 2017-01-27 |  |  |  |  | FY17Q2 | FY17Q2(A)
592 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.03.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Dipole Corrector Magnets - Design complete | 0 d | 100% | 2017-01-20 | 2017-01-20 |  |  |  |  | FY17Q2 | FY17Q2(A)
593 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.05 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Dipoles - Quadrupoles-Correctors - ALL Design complete | 0 d | 100% | 2017-03-13 | 2017-03-13 |  |  |  |  | FY17Q2 | FY17Q2(A)
594 | Burke | Burke | Cornell | A1.06.01.01.01.02.02.06 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Common Magnets - Procurement Complete | 0 d | 0% | 2018-03-21 | 2018-03-21 |  |  |  |  | FY18Q2
595 | Burke | Burke | Cornell | A1.06.01.01.01.03.02.06 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Septa Magnets - Procurement complete | 0 d | 0% | 2018-04-12 | 2018-04-12 |  |  |  |  | FY18Q3
596 | Burke | Burke | Cornell | A1.06.01.01.01.04.01.05 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Mounts and Stages - ALL Design Complete | 0 d | 0% | 2017-05-17 | 2017-05-17 |  |  |  |  | FY17Q3
597 | Burke | Burke | Cornell | A1.06.01.01.01.04.02.08 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Support Hardware - Procurements complete | 0 d | 0% | 2017-09-26 | 2017-09-26 |  |  |  |  | FY17Q4
598 | Burke | Burke | Cornell | A1.06.01.01.01.05.01.08 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Supporting Hardware - Assembly complete for FAT | 0 d | 0% | 2018-01-11 | 2018-01-11 |  |  |  |  | FY18Q2
599 | Burke | Burke | Cornell | A1.06.01.01.01.05.01.09 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Supporting Hardware - Assembly complete for SPBT and 4PBT | 0 d | 0% | 2018-02-09 | 2018-02-09 |  |  |  |  | FY18Q2
600 | Burke | Burke | Cornell | A1.06.01.02.01.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Electromagnet Table - Procurements complete | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | FY17Q1
601 | Burke | Burke | Cornell | A1.06.01.02.01.03.09 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets -Electromagnet Table Supporting Hardware - ALL Design Complete | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | FY17Q4
602 | Burke | Burke | Cornell | A1.06.01.02.01.04.12 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Procurements complete (FAT) | 0 d | 0% | 2018-01-18 | 2018-01-18 |  |  |  |  | FY18Q2
603 | Burke | Burke | Cornell | A1.06.01.02.01.04.13 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Procurements complete (SPBT & 4PBT) | 0 d | 0% | 2018-03-12 | 2018-03-12 |  |  |  |  | FY18Q2
604 | Burke | Burke | Cornell | A1.06.01.02.01.05.09 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Pre-Assembly complete (FAT) | 0 d | 0% | 2018-02-21 | 2018-02-21 |  |  |  |  | FY18Q2
605 | Burke | Burke | Cornell | A1.06.01.02.01.05.10 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Pre-Assembly complete (SPBT & 4PBT) | 0 d | 0% | 2018-05-30 | 2018-05-30 |  |  |  |  | FY18Q3
606 | Burke | Burke | Cornell | A1.06.01.03.01.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets and Tables - Assembly (FAT) - All Material available for Installation (1/8th magnets + 2 tables) | 0 d | 0% | 2018-03-21 | 2018-03-21 |  |  |  |  | FY18Q2
607 | Burke | Burke | Cornell | A1.06.01.03.02.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets and Tables - Assembly (SPBT) - All Material available for Installation (? magnets + 2 tables) | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | FY18Q3
608 | Burke | Burke | Cornell | A1.06.01.03.03.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets and Tables - Assembly (4PBT) - All Material available for Installation (3/4 of magnets - remaining) | 0 d | 0% | 2018-08-15 | 2018-08-15 |  |  |  |  | FY18Q4
609 | Burke | Burke | Cornell | A1.06.02.01.01.01.04 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Dipoles - Design complete | 0 d | 0% | 2017-06-07 | 2017-06-07 |  |  |  |  | FY17Q3
610 | Burke | Burke | Cornell | A1.06.02.01.01.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets (Dipoles) - Contract Awarded | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | FY17Q4
611 | Burke | Burke | Cornell | A1.06.02.01.02.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Quadrupoles - Design complete | 0 d | 0% | 2017-05-30 | 2017-05-30 |  |  |  |  | FY17Q3
612 | Burke | Burke | Cornell | A1.06.02.01.02.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets (Quads) - Contract Awarded | 0 d | 0% | 2017-06-27 | 2017-06-27 |  |  |  |  | FY17Q3
613 | Burke | Burke | Cornell | A1.06.02.01.03.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Magnet Mounts - Design complete | 0 d | 0% | 2017-05-30 | 2017-05-30 |  |  |  |  | FY17Q3
614 | Burke | Burke | Cornell | A1.06.02.01.03.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Support Hardware Procurements complete | 0 d | 0% | 2017-07-26 | 2017-07-26 |  |  |  |  | FY17Q4
615 | Burke | Burke | Cornell | A1.06.02.02.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Beam Stop Table - ALL Design Complete | 0 d | 0% | 2017-08-25 | 2017-08-25 |  |  |  |  | FY17Q4
616 | Burke | Burke | Cornell | A1.06.02.02.02.04 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Table Support Hardware - Procurements complete | 0 d | 0% | 2017-09-25 | 2017-09-25 |  |  |  |  | FY17Q4
617 | Burke | Burke | Cornell | A1.06.02.03.01.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets and Tables - Assembly (SPBT) - All Material available for Installation | 0 d | 0% | 2018-03-09 | 2018-03-09 |  |  |  |  | FY18Q2
618 | Dobbins | Dobbins | Cornell | A1.08.01.02.05 |  | A1.08 - Controls | T-3 | Milestone: All Network Infrastructure Procurements Complete | 0 d | 0% | 2017-10-06 | 2017-10-06 |  |  |  |  | FY18Q1
619 | Dobbins | Dobbins | Cornell | A1.08.01.03.03 |  | A1.08 - Controls | T-3 | Milestone: Network Infrastructure Installation and Configuration Complete | 0 d | 0% | 2017-11-06 | 2017-11-06 |  |  |  |  | FY18Q1
620 | Dobbins | Dobbins | Cornell | A1.08.01.04.02 |  | A1.08 - Controls | T-3 | Milestone: Network Infrastructure Complete | 0 d | 0% | 2017-12-07 | 2017-12-07 |  |  |  |  | FY18Q1
621 | Dobbins | Dobbins | Cornell | A1.08.02.01.01.03 |  | A1.08 - Controls | T-3 | Milestone: IOC Computer Design Complete | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | FY17Q4
622 | Dobbins | Dobbins | Cornell | A1.08.02.01.02.03 |  | A1.08 - Controls | T-3 | Milestone: All IOC Computer Procurements Complete | 0 d | 0% | 2017-09-15 | 2017-09-15 |  |  |  |  | FY17Q4
623 | Dobbins | Dobbins | Cornell | A1.08.02.01.03.02 |  | A1.08 - Controls | T-3 | Milestone: IOC Computer Installation and Configuration Complete | 0 d | 0% | 2017-11-14 | 2017-11-14 |  |  |  |  | FY18Q1
624 | Dobbins | Dobbins | Cornell | A1.08.02.02.01.03 |  | A1.08 - Controls | T-3 | Milestone: Operator Consoles Design Complete | 0 d | 100% | 2017-07-06 | 2017-07-06 |  |  |  |  | FY17Q4 | FY17Q4(A)
625 | Dobbins | Dobbins | Cornell | A1.08.02.02.02.03 |  | A1.08 - Controls | T-3 | Milestone: All Operator Consoles Procurements Complete | 0 d | 0% | 2017-09-15 | 2017-09-15 |  |  |  |  | FY17Q4
626 | Dobbins | Dobbins | Cornell | A1.08.02.02.03.02 |  | A1.08 - Controls | T-3 | Milestone: Operator Consoles Installation and Configuration Complete | 0 d | 0% | 2017-11-14 | 2017-11-14 |  |  |  |  | FY18Q1
627 | Dobbins | Dobbins | Cornell | A1.08.03.01.01.03 |  | A1.08 - Controls | T-3 | Milestone: File Server Design Complete | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | FY17Q1 | FY17Q1(A)
628 | Dobbins | Dobbins | Cornell | A1.08.03.01.02.03 |  | A1.08 - Controls | T-3 | Milestone: All File Server Procurements Complete | 0 d | 100% | 2017-01-20 | 2017-01-20 |  |  |  |  | FY17Q2 | FY17Q2(A)
629 | Dobbins | Dobbins | Cornell | A1.08.03.01.03.02 |  | A1.08 - Controls | T-3 | Milestone: File Server Installation and Configuration Complete | 0 d | 100% | 2017-03-17 | 2017-03-17 |  |  |  |  | FY17Q2 | FY17Q2(A)
630 | Dobbins | Dobbins | Cornell | A1.08.04.01.01.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS Archiver Design Complete | 0 d | 100% | 2017-07-06 | 2017-07-06 |  |  |  |  | FY17Q4 | FY17Q4(A)
631 | Dobbins | Dobbins | Cornell | A1.08.04.01.02.03 |  | A1.08 - Controls | T-3 | Milestone: All Archiver Computer Procurements Complete | 0 d | 100% | 2017-09-15 | 2017-09-15 |  |  |  |  | FY17Q4 | FY17Q4(A)
632 | Dobbins | Dobbins | Cornell | A1.08.04.01.03.02 |  | A1.08 - Controls | T-3 | Milestone: EPICS Archiver Installation and Configuration Complete | 0 d | 100% | 2017-11-10 | 2017-11-10 |  |  |  |  | FY18Q1 | FY17Q4(A)
633 | Dobbins | Dobbins | Cornell | A1.08.04.02.01.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS Alarm Handler Design Complete | 0 d | 0% | 2017-07-07 | 2017-07-07 |  |  |  |  | FY17Q4
634 | Dobbins | Dobbins | Cornell | A1.08.04.02.02.03 |  | A1.08 - Controls | T-3 | Milestone: All EPICS Alarm Handler Procurements Complete | 0 d | 0% | 2017-09-18 | 2017-09-18 |  |  |  |  | FY17Q4
635 | Dobbins | Dobbins | Cornell | A1.08.04.02.03.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS Alarm Handler Installation and Configuration Complete | 0 d | 0% | 2017-12-15 | 2017-12-15 |  |  |  |  | FY18Q1
636 | Dobbins | Dobbins | Cornell | A1.08.04.03.01.03 |  | A1.08 - Controls | T-3 | Milestone: Configuration Database Design Complete | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | FY17Q4
637 | Dobbins | Dobbins | Cornell | A1.08.04.03.02.02 |  | A1.08 - Controls | T-3 | Milestone: Configuration Database Installation and Configuration Complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | FY17Q4
638 | Dobbins | Michnoff | BNL | A1.08.05.01.02 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - BPM - Sample hardware available for software development (Rob has the equipment and is bringing it back to CU for testing by the end of June) | 0 d | 100% | 2017-08-15 | 2017-08-15 |  |  |  |  | FY17Q4 | FY17Q4(A)
639 | Dobbins | Michnoff | BNL | A1.08.05.02.02 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - BAM - Sample hardware available for software development | 0 d | 0% | 2017-10-16 | 2017-10-16 |  |  |  |  | FY18Q1
640 | Dobbins | Dobbins | Cornell | A1.08.05.03.01.01 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - Magnet power supplies - Hardware Identified/Specification Complete (Predecessors - All Power Supplies selected) | 0 d | 0% | 2017-10-26 | 2017-10-26 |  |  |  |  | FY18Q1
641 | Dobbins | Dobbins | Cornell | A1.08.05.03.02.01 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - Magnet power supplies - Sample hardware available for software development (predecessor power supply specs - verify with Karl, successor is FF to at least 1 hardware available - redundant due to #1254?) | 0 d | 0% | 2017-11-20 | 2017-11-20 |  |  |  |  | FY18Q1
642 | Dobbins | Dobbins | Cornell | A1.08.05.03.02.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - Magnet power supplies - Software development complete | 0 d | 0% | 2017-11-29 | 2017-11-29 |  |  |  |  | FY18Q1
643 | Dobbins | Dobbins | Cornell | A1.08.06.01.01.02 |  | A1.08 - Controls | T-3 | Milestone: Orbit Correction - Requirements definition complete | 0 d | 0% | 2018-05-25 | 2018-05-25 |  |  |  |  | FY18Q3
644 | Dobbins | Dobbins | Cornell | A1.08.06.01.01.04 |  | A1.08 - Controls | T-3 | Milestone: Orbit Correction - Software design complete | 0 d | 0% | 2018-06-25 | 2018-06-25 |  |  |  |  | FY18Q3
645 | Dobbins | Dobbins | Cornell | A1.08.07.01.03 |  | A1.08 - Controls | T-3 | Milestone: Timing system - System design complete | 0 d | 0% | 2017-08-18 | 2017-08-18 |  |  |  |  | FY17Q4
646 | Dobbins | Dobbins | Cornell | A1.08.07.04.03 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for MLC Test | 0 d | 100% | 2017-05-08 | 2017-05-08 |  |  |  |  | FY17Q3 | FY17Q3(A)
647 | Dobbins | Dobbins | Cornell | A1.08.07.04.06 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for (FAT) Test | 0 d | 0% | 2018-01-23 | 2018-01-23 |  |  |  |  | FY18Q2
648 | Dobbins | Dobbins | Cornell | A1.08.07.04.09 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for SPBT | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | FY18Q3
649 | Dobbins | Dobbins | Cornell | A1.08.07.04.12 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for 4PBT | 0 d | 0% | 2018-07-24 | 2018-07-24 |  |  |  |  | FY18Q4
650 | Dobbins | Dobbins | Cornell | A1.08.08.02.03 |  | A1.08 - Controls | T-3 | Milestone: All Machine Protection System Procurements Complete | 0 d | 0% | 2018-02-01 | 2018-02-01 |  |  |  |  | FY18Q2
651 | Dobbins | Dobbins | Cornell | A1.08.08.03.01.04 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System Assembly/Development and initial testing complete (FAT) | 0 d | 0% | 2018-02-23 | 2018-02-23 |  |  |  |  | FY18Q2
652 | Dobbins | Dobbins | Cornell | A1.08.08.03.02.04 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System Assembly/Development and initial testing complete (SPBT) | 0 d | 0% | 2019-01-18 | 2019-01-18 |  |  |  |  | FY19Q2
653 | Dobbins | Dobbins | Cornell | A1.08.08.04.03 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System - Installation and Testing - Complete and ready for MLC Test | 0 d | 100% | 2017-05-08 | 2017-05-08 |  |  |  |  | FY17Q3 | FY17Q3(A)
654 | Dobbins | Dobbins | Cornell | A1.08.08.04.12 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System - Installation and Testing - complete and ready for 4PBT | 0 d | 0% | 2019-11-18 | 2019-11-18 |  |  |  |  | FY20Q1
655 | Dobbins | Dobbins | Cornell | A1.08.09.01.01.16 |  | A1.08 - Controls | T-3 | Milestone: MLC Test - Controls EPICS Integration complete | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | FY17Q3 | FY17Q3(A)
656 | Dobbins | Dobbins | Cornell | A1.08.09.01.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: MLC Test - Integrated pre-beam testing for all Controls System Complete | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | FY17Q3 | FY17Q3(A)
657 | Dobbins | Dobbins | Cornell | A1.08.09.01.02.02.16 |  | A1.08 - Controls | T-3 | Milestone: Controls - MLC Test - Commissioning with Beam for all Controls System Complete | 0 d | 100% | 2017-05-05 | 2017-05-05 |  |  |  |  | FY17Q3 | FY17Q3(A)
658 | Dobbins | Dobbins | Cornell | A1.08.09.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: Fractional Arc Test - Controls EPICS Integration complete | 0 d | 0% | 2018-02-07 | 2018-02-07 |  |  |  |  | FY18Q2
659 | Dobbins | Dobbins | Cornell | A1.08.09.02.02.01.02.16 |  | A1.08 - Controls | T-3 | Milestone: Controls - Fractional Arc Test - Commissioning with Beam for all Controls System Complete | 0 d | 0% | 2018-03-08 | 2018-03-08 |  |  |  |  | FY18Q2
660 | Dobbins | Dobbins | Cornell | A1.08.09.03.01.16 |  | A1.08 - Controls | T-3 | Milestone: SPBT - Controls EPICS Integration complete | 0 d | 0% | 2019-04-03 | 2019-04-03 |  |  |  |  | FY19Q3
661 | Dobbins | Dobbins | Cornell | A1.08.09.03.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: SPBT - Integrated pre-beam testing for all Controls System Complete | 0 d | 0% | 2019-05-01 | 2019-05-01 |  |  |  |  | FY19Q3
662 | Dobbins | Dobbins | Cornell | A1.08.09.04.01.16 |  | A1.08 - Controls | T-3 | Milestone: 4PBT - Controls EPICS Integration complete | 0 d | 0% | 2019-08-26 | 2019-08-26 |  |  |  |  | FY19Q4
663 | Dobbins | Dobbins | Cornell | A1.08.09.04.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: 4PBT - Integrated pre-beam testing for all Controls System Complete | 0 d | 0% | 2019-11-14 | 2019-11-14 |  |  |  |  | FY20Q1
664 | Dobbins | Dobbins | Cornell | A1.09.02.01.07 |  | A1.09 - Instrumentation | T-3 | Milestone: BAM Design Complete | 0 d | 0% | 2017-09-15 | 2017-09-15 |  |  |  |  | FY17Q4
665 | Dobbins | Dobbins | Cornell | A1.09.02.02.06 |  | A1.09 - Instrumentation | T-3 | Milestone: 1st Article - V301 Digital Boards Received (Qty: xx [BNL]) (5 mths after order placement??) | 0 d | 0% | 2018-01-24 | 2018-01-24 |  |  |  |  | FY18Q2
666 | Dobbins | Dobbins | Cornell | A1.09.02.02.08 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Arrival Monitor Procurements Complete | 0 d | 0% | 2018-06-15 | 2018-06-15 |  |  |  |  | FY18Q3
667 | Dobbins | Dobbins | Cornell | A1.09.02.03.01 |  | A1.09 - Instrumentation | T-3 | Milestone: Existing BAMs tested and available for install | 0 d | 100% | 2017-04-28 | 2017-04-28 |  |  |  |  | FY17Q3 | FY17Q3(A)
668 | Dobbins | Dobbins | Cornell | A1.09.03.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: BCM Design Complete | 0 d | 0% | 2017-08-10 | 2017-08-10 |  |  |  |  | FY17Q4
669 | Dobbins | Dobbins | Cornell | A1.09.03.02.05 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Current Monitor Procurements Complete | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | FY18Q3
670 | Dobbins | Dobbins | Cornell | A1.09.04.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: Beam Loss Monitor Design Complete | 0 d | 0% | 2017-09-22 | 2017-09-22 |  |  |  |  | FY17Q4
671 | Dobbins | Dobbins | Cornell | A1.09.04.02.04 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Loss Monitor Procurements Complete | 0 d | 0% | 2018-01-24 | 2018-01-24 |  |  |  |  | FY18Q2
672 | Dobbins | Dobbins | Cornell | A1.09.05.01.01.06 |  | A1.09 - Instrumentation | T-3 | Milestone: All System Specifications Finalized/Complete | 0 d | 100% | 2017-08-01 | 2017-08-01 |  |  |  |  | FY17Q4 | FY17Q4(A)
673 | Dobbins | Dobbins | Cornell | A1.09.05.01.03.03 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM - DAQ Board Design Complete | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | FY18Q3
674 | Dobbins | Dobbins | Cornell | A1.09.05.01.03.08 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM Clock Distribution Design Complete (FAT) | 0 d | 0% | 2017-09-13 | 2017-09-13 |  |  |  |  | FY17Q4
675 | Dobbins | Dobbins | Cornell | A1.09.05.01.03.09 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM Clock Distribution Design Complete (SPBT) | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | FY18Q3
676 | Dobbins | Dobbins | Cornell | A1.09.05.02.01.06 |  | A1.09 - Instrumentation | T-3 | Milestone: All DAQ Electronics Procurements Complete | 0 d | 0% | 2019-04-02 | 2019-04-02 |  |  |  |  | FY19Q3
677 | Dobbins | Dobbins | Cornell | A1.09.05.02.02.05 |  | A1.09 - Instrumentation | T-3 | Milestone: All BPM Clock Distribution Procurements Complete | 0 d | 0% | 2018-10-03 | 2018-10-03 |  |  |  |  | FY19Q1
678 | Dobbins | Dobbins | Cornell | A1.09.05.03.03.04 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM Assembly/Development - BPM Clock Complete and ready for Final testing | 0 d | 0% | 2018-10-03 | 2018-10-03 |  |  |  |  | FY19Q1
679 | Dobbins | Dobbins | Cornell | A1.09.05.05.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: View Screen Design Complete | 0 d | 0% | 2017-09-14 | 2017-09-14 |  |  |  |  | FY17Q4
680 | Dobbins | Dobbins | Cornell | A1.09.05.06.01.02 |  | A1.09 - Instrumentation | T-3 | Milestone: Develop Beam stop beam-pipe hardware design complete (Vacuum section) | 0 d | 0% | 2017-08-15 | 2017-08-15 |  |  |  |  | FY17Q4
681 | Dobbins | Dobbins | Cornell | A1.09.05.06.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: Beam Stop Design Complete | 0 d | 0% | 2017-08-15 | 2017-08-15 |  |  |  |  | FY17Q4
682 | Dobbins | Dobbins | Cornell | A1.09.05.06.02.05 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Stop Procurements Complete | 0 d | 0% | 2017-12-05 | 2017-12-05 |  |  |  |  | FY18Q1
683 | Dobbins | Dobbins | Cornell | A1.09.05.07.01.01.08 |  | A1.09 - Instrumentation | T-3 | Milestone: MLC Test - Instrumentation System Final Installation Complete | 0 d | 100% | 2017-05-11 | 2017-05-11 |  |  |  |  | FY17Q3 | FY17Q3(A)
684 | Dobbins | Dobbins | Cornell | A1.09.05.07.01.02.02 |  | A1.09 - Instrumentation | T-3 | Milestone: MLC Test - Instrumentation System Testing Complete | 0 d | 100% | 2017-05-12 | 2017-05-12 |  |  |  |  | FY17Q3 | FY17Q3(A)
685 | Dobbins | Dobbins | Cornell | A1.09.05.07.01.03.02 |  | A1.09 - Instrumentation | T-3 | Milestone: MLC Test - Instrumentation Commissioning with Beam Complete | 0 d | 100% | 2017-05-15 | 2017-05-15 |  |  |  |  | FY17Q3 | FY17Q3(A)
686 | Dobbins | Dobbins | Cornell | A1.09.05.07.02.02.03 |  | A1.09 - Instrumentation | T-3 | Milestone: FAT - Instrumentation Commissioning with Beam Complete | 0 d | 0% | 2018-03-27 | 2018-03-27 |  |  |  |  | FY18Q2
687 | Dobbins | Dobbins | Cornell | A1.09.05.07.03.02.03 |  | A1.09 - Instrumentation | T-3 | Milestone: SPBT - Instrumentation Commissioning with Beam Complete | 0 d | 0% | 2019-09-05 | 2019-09-05 |  |  |  |  | FY19Q4
688 | Dobbins | Dobbins | Cornell | A1.09.05.07.04.02.03 |  | A1.09 - Instrumentation | T-3 | Milestone: 4PBT - Instrumentation Commissioning with Beam Complete | 0 d | 0% | 2020-04-29 | 2020-04-29 |  |  |  |  | FY20Q2
689 | Li | Li | Cornell | A1.10.01.03.04 |  | A1.10 - Vacuum Systems | T-3 | Milestone: Global Vacuum System - All assembly/support complete | 0 d | 0% | 2018-05-25 | 2018-05-25 |  |  |  |  | FY18Q3
690 | Li | Li | Cornell | A1.10.04.03.02.04 |  | A1.10 - Vacuum Systems | T-3 | Milestone: BPM buttons machining complete and ready for delivery to vendor | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | FY17Q1
691 | Li | Li | Cornell | A1.10.05.01.05 |  | A1.10 - Vacuum Systems | T-3 | Milestone: Vacuum FFAG Straight System - All Designs Complete | 0 d | 0% | 2017-05-09 | 2017-05-09 |  |  |  |  | FY17Q3
692 | Li | Li | Cornell | A1.10.05.04.01 |  | A1.10 - Vacuum Systems | T-3 | Milestone: BPM buttons machining complete and ready for delivery to vendor (Change) | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | FY17Q1
693 | Gallagher | Gallagher | Cornell | A1.11.01.01.02 |  | A1.11 - System Integration | T-3 | CBETA ALL DWGS Start | 0 d | 100% | 2016-06-01 | 2016-06-01 |  |  |  |  | FY17Q1 | FY17Q1(A)
694 | Gallagher | Gallagher | Cornell | A1.11.01.01.04 |  | A1.11 - System Integration | T-3 | Milestone: Gun and ICM operational (Sector 00) (10/3/2016) | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | FY17Q1 | FY17Q1(A)
695 | Gallagher | Gallagher | Cornell | A1.11.01.01.05 |  | A1.11 - System Integration | T-3 | Milestone: Vacuum Lab ready for Removal activities | 0 d | 100% | 2017-04-01 | 2017-04-01 |  |  |  |  | FY17Q3 | FY17Q3(A)
696 | Gallagher | Gallagher | Cornell | A1.11.01.01.06 |  | A1.11 - System Integration | T-3 | Milestone: Water Shut off (by June 30 2017) - 6 weeks | 0 d | 100% | 2017-06-30 | 2017-06-30 |  |  |  |  | FY17Q3 | FY17Q3(A)
697 | Gallagher | Gallagher | Cornell | A1.11.01.01.08 |  | A1.11 - System Integration | T-3 | Milestone: Start L0E construction (East-RF move to L0 Pit complete/operational) 12/4/17? | 0 d | 0% | 2017-12-04 | 2017-12-04 |  |  |  |  | FY18Q1
698 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Final Design/Layout for East RF System Complete | 0 d | 100% | 2017-03-31 | 2017-03-31 |  |  |  |  | FY17Q2 | FY17Q2(A)
699 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All East RF System Relocation Procurements Complete | 0 d | 0% | 2017-08-08 | 2017-08-08 |  |  |  |  | FY17Q4
700 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.03.04 |  | A1.11 - System Integration | T-3 | Milestone: East RF Systems Install Complete | 0 d | 0% | 2017-11-07 | 2017-11-07 |  |  |  |  | FY18Q1
701 | Gallagher | Gallagher | Cornell | A1.11.01.03.03.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All CESR-85F Cooling System Components Procurements Received | 0 d | 0% | 2017-10-27 | 2017-10-27 |  |  |  |  | FY18Q1
702 | Gallagher | Gallagher | Cornell | A1.11.01.04.03.01.03 |  | A1.11 - System Integration | T-3 | Milestone: All Survey & Alignment Procurements Complete | 0 d | 0% | 2018-04-06 | 2018-04-06 |  |  |  |  | FY18Q3
703 | Gallagher | Gallagher | Cornell | A1.11.01.04.03.02.03 |  | A1.11 - System Integration | T-3 | Milestone: Survey and alignment - Reference system Complete | 0 d | 0% | 2018-07-02 | 2018-07-02 |  |  |  |  | FY18Q4
704 | Gallagher | Gallagher | Cornell | A1.11.01.04.04.01.03 |  | A1.11 - System Integration | T-3 | Milestone: All New Shielding Wall & Blocks Procurements Complete | 0 d | 0% | 2019-04-16 | 2019-04-16 |  |  |  |  | FY19Q3
705 | Gallagher | Gallagher | Cornell | A1.11.01.04.05.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Laser Room Design Complete | 0 d | 100% | 2017-04-11 | 2017-04-11 |  |  |  |  | FY17Q3 | FY17Q3(A)
706 | Gallagher | Gallagher | Cornell | A1.11.01.04.05.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All Laser Room Procurements Complete | 0 d | 0% | 2017-05-23 | 2017-05-23 |  |  |  |  | FY17Q3
707 | Gallagher | Gallagher | Cornell | A1.11.01.04.05.03.02 |  | A1.11 - System Integration | T-3 | Milestone: Laser Room Fabrication Complete and Table Ready for Set-Up | 0 d | 0% | 2017-08-17 | 2017-08-17 |  |  |  |  | FY17Q4
708 | Gallagher | Gallagher | Cornell | A1.11.01.04.06.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All Mezzanine Procurements Complete | 0 d | 0% | 2018-02-23 | 2018-02-23 |  |  |  |  | FY18Q2
709 | Gallagher | Gallagher | Cornell | A1.11.01.04.06.03.02 |  | A1.11 - System Integration | T-3 | Milestone: Mezzanine Installation Complete | 0 d | 0% | 2018-05-18 | 2018-05-18 |  |  |  |  | FY18Q3
710 | Gallagher | Gallagher | Cornell | A1.11.01.04.08.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Water Cooling System Design Complete | 0 d | 0% | 2018-04-06 | 2018-04-06 |  |  |  |  | FY18Q3
711 | Gallagher | Gallagher | Cornell | A1.11.01.04.08.03.04 |  | A1.11 - System Integration | T-3 | Milestone: Water Cooling System Installation Complete | 0 d | 0% | 2019-04-23 | 2019-04-23 |  |  |  |  | FY19Q3
712 | Gallagher | Gallagher | Cornell | A1.11.01.04.09.01.05 |  | A1.11 - System Integration | T-3 | Milestone: Electrical System Design Complete | 0 d | 0% | 2018-02-08 | 2018-02-08 |  |  |  |  | FY18Q2
713 | Gallagher | Gallagher | Cornell | A1.11.01.04.09.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All Electrical System Procurements Complete | 0 d | 0% | 2018-05-04 | 2018-05-04 |  |  |  |  | FY18Q3
714 | Gallagher | Gallagher | Cornell | A1.11.01.04.10.04 |  | A1.11 - System Integration | T-3 | Milestone: Compressed Air System Installation Complete | 0 d | 0% | 2018-01-10 | 2018-01-10 |  |  |  |  | FY18Q2
715 | Gallagher | Gallagher | Cornell | A1.11.01.04.11.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Design of HVAC Upgrade Complete | 0 d | 0% | 2018-02-08 | 2018-02-08 |  |  |  |  | FY18Q2
716 | Gallagher | Gallagher | Cornell | A1.11.01.04.11.04 |  | A1.11 - System Integration | T-3 | Milestone: Environmental Controls Installation Complete | 0 d | 0% | 2018-06-04 | 2018-06-04 |  |  |  |  | FY18Q3
717 | Gallagher | Gallagher | Cornell | A1.11.01.04.12.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Network and IT Requirements Complete | 0 d | 0% | 2018-04-06 | 2018-04-06 |  |  |  |  | FY18Q3
718 | Gallagher | Gallagher | Cornell | A1.11.01.04.12.02.02 |  | A1.11 - System Integration | T-3 | Milestone: All Network and IT Support Procurements Complete | 0 d | 0% | 2018-05-04 | 2018-05-04 |  |  |  |  | FY18Q3
719 | Gallagher | Gallagher | Cornell | A1.11.01.04.12.03.02 |  | A1.11 - System Integration | T-3 | Milestone: Network and IT Support items installed | 0 d | 0% | 2018-07-31 | 2018-07-31 |  |  |  |  | FY18Q4
720 | Gallagher | Gallagher | Cornell | A1.11.02.01.03 |  | A1.11 - System Integration | T-3 | Milestone: All Sectors - System Integration Complete | 0 d | 0% | 2019-10-07 | 2019-10-07 |  |  |  |  | FY20Q1
721 | Gallagher | Gallagher | Cornell | A1.11.02.02.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 01-LA: North MLC and diagnostics Beam line Ready for System Integration | 0 d | 100% | 2017-08-11 | 2017-08-11 |  |  |  |  | FY17Q4 | FY17Q4(A)
722 | Gallagher | Gallagher | Cornell | A1.11.02.03.01.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 02-SX (FAT) Northeast Splitter Ready for System Integration | 0 d | 0% | 2018-06-29 | 2018-06-29 |  |  |  |  | FY18Q3
723 | Gallagher | Gallagher | Cornell | A1.11.02.03.02.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 02-SX (SPBT) - Northeast Splitter Ready for System Integration | 0 d | 0% | 2018-08-17 | 2018-08-17 |  |  |  |  | FY18Q4
724 | Gallagher | Gallagher | Cornell | A1.11.02.03.03.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 02-SX (4PBT): Northeast Splitter Ready for System Integration | 0 d | 0% | 2018-07-02 | 2018-07-02 |  |  |  |  | FY18Q4
725 | Gallagher | Gallagher | Cornell | A1.11.02.04.01.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (FAT): East arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | FY18Q4
726 | Gallagher | Gallagher | Cornell | A1.11.02.04.01.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (FAT): East Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | FY18Q3
727 | Gallagher | Gallagher | Cornell | A1.11.02.04.02.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (SPBT-4PBT): East arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | FY18Q4
728 | Gallagher | Gallagher | Cornell | A1.11.02.04.02.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (SPBT-4PBT): East Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | FY18Q3
729 | Gallagher | Gallagher | Cornell | A1.11.02.05.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 04-TA - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | FY18Q4
730 | Gallagher | Gallagher | Cornell | A1.11.02.05.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 04-TA: South Southeast arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | FY18Q3
731 | Gallagher | Gallagher | Cornell | A1.11.02.06.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 05-ZA - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | FY18Q4
732 | Gallagher | Gallagher | Cornell | A1.11.02.06.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 05-ZA: Southeast straight Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | FY18Q3
733 | Gallagher | Gallagher | Cornell | A1.11.02.07.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 06-ZB - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | FY18Q4
734 | Gallagher | Gallagher | Cornell | A1.11.02.07.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 06-ZB: Southwest straight Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | FY18Q3
735 | Gallagher | Gallagher | Cornell | A1.11.02.08.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 07-TB - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | FY18Q4
736 | Gallagher | Gallagher | Cornell | A1.11.02.08.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 07-TB: Southwest Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | FY18Q3
737 | Gallagher | Gallagher | Cornell | A1.11.02.09.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 07-TB - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | FY18Q4
738 | Gallagher | Gallagher | Cornell | A1.11.02.09.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 08-FB: West Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | FY18Q3
739 | Gallagher | Gallagher | Cornell | A1.11.02.10.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 09-RX: Northwest Splitter Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | FY18Q3
740 | Gallagher | Gallagher | Cornell | A1.11.02.11.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 10-BS: Beam stop Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | FY18Q3
741 | Gallagher | Gallagher | Cornell | A1.11.02.11.03.06 |  | A1.11 - System Integration | T-3 | Milestone: Sector 10-BS: Beam stop - Installation Complete | 0 d | 0% | 2018-07-23 | 2018-07-23 |  |  |  |  | FY18Q4
742 | Widger | Ray | Cornell | A1.13.02.01.02.03 |  | A1.13 - Safety | T-3 | Milestone: (MLC) Safety Procurements Received | 0 d | 100% | 2017-03-13 | 2017-03-13 |  |  |  |  | FY17Q2 | FY17Q2(A)
743 | Widger | Ray | Cornell | A1.13.02.01.03.07 |  | A1.13 - Safety | T-3 | Milestone: Safety process complete for MLC Test (5/9) | 0 d | 100% | 2017-04-10 | 2017-04-10 |  |  |  |  | FY17Q3 | FY17Q3(A)
744 | Widger | Ray | Cornell | A1.13.02.02.01.04 |  | A1.13 - Safety | T-3 | Milestone: (FAT) Design approved by safety committee | 0 d | 0% | 2017-12-14 | 2017-12-14 |  |  |  |  | FY18Q1
745 | Widger | Ray | Cornell | A1.13.02.02.02.03 |  | A1.13 - Safety | T-3 | Milestone: (FAT) Safety Procurements Received | 0 d | 0% | 2018-01-02 | 2018-01-02 |  |  |  |  | FY18Q2
746 | Widger | Ray | Cornell | A1.13.02.02.03.08 |  | A1.13 - Safety | T-3 | Milestone: Safety process complete for (FAT) Test | 0 d | 0% | 2018-03-22 | 2018-03-22 |  |  |  |  | FY18Q2
747 | Widger | Ray | Cornell | A1.13.02.03.01.04 |  | A1.13 - Safety | T-3 | Milestone: (SPBT) Design approved by safety committee | 0 d | 0% | 2018-11-21 | 2018-11-21 |  |  |  |  | FY19Q1
748 | Widger | Ray | Cornell | A1.13.02.03.02.03 |  | A1.13 - Safety | T-3 | Milestone: (SPBT) Safety Procurements Received | 0 d | 0% | 2018-12-21 | 2018-12-21 |  |  |  |  | FY19Q1
749 | Widger | Ray | Cornell | A1.13.02.03.03.07 |  | A1.13 - Safety | T-3 | Milestone: Safety process complete for PSS (SPBT) | 0 d | 0% | 2019-04-26 | 2019-04-26 |  |  |  |  | FY19Q3
750 | Widger | Widger | Cornell | A1.13.03.01.01.03 |  | A1.13 - Safety | T-3 | Milestone: (MLC) - Design radiation monitor system Complete/Approved | 0 d | 100% | 2017-03-23 | 2017-03-23 |  |  |  |  | FY17Q2 | FY17Q2(A)
751 | Widger | Ray | Cornell | A1.13.03.01.02.03 |  | A1.13 - Safety | T-3 | Milestone: (MLC) Radiation Monitoring Procurements Received | 0 d | 100% | 2017-04-06 | 2017-04-06 |  |  |  |  | FY17Q3 | FY17Q3(A)
752 | Widger | Widger | Cornell | A1.13.03.01.03.07 |  | A1.13 - Safety | T-3 | Milestone: Radiation Monitor Safety process for MLC Relocate Complete (Link to Commissioning of beam directly) | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | FY17Q3 | FY17Q3(A)
753 | Widger | Widger | Cornell | A1.13.03.02.01.03 |  | A1.13 - Safety | T-3 | Milestone: (FAT) - Design radiation monitor system Complete/Approved | 0 d | 0% | 2017-11-21 | 2017-11-21 |  |  |  |  | FY18Q1
754 | Widger | Ray | Cornell | A1.13.03.02.02.04 |  | A1.13 - Safety | T-3 | Milestone: (FAT) Radiation Monitoring Procurements Received | 0 d | 0% | 2018-01-23 | 2018-01-23 |  |  |  |  | FY18Q2
755 | Widger | Widger | Cornell | A1.13.03.02.03.07 |  | A1.13 - Safety | T-3 | Milestone: Radiation Monitor Safety process for FAT Relocate Complete (Link to Commissioning of beam directly) | 0 d | 0% | 2018-03-13 | 2018-03-13 |  |  |  |  | FY18Q2
756 | Widger | Widger | Cornell | A1.13.03.03.01.03 |  | A1.13 - Safety | T-3 | Milestone: SPBT - Design radiation monitor system Complete/Approved | 0 d | 0% | 2018-10-29 | 2018-10-29 |  |  |  |  | FY19Q1
757 | Widger | Ray | Cornell | A1.13.03.03.02.03 |  | A1.13 - Safety | T-3 | Milestone: (SPBT) Radiation Monitoring Procurements Received | 0 d | 0% | 2018-11-29 | 2018-11-29 |  |  |  |  | FY19Q1

## August 2017 by WBS
hide | hide | hide |  |  | hide | hide |  | ** Quarters are based on BNL's Fiscal Calendar ** T-3s are not reportable milestones | hide | hide | hide | hide | hide | hide | hide | hide | hide |  |  | hide | hide | hide | hide | hide | hide
Calc_ID | Point of Contact L2 | Point of Contact L3 | Responsible Institution | WBS | Old WBS (Month 'YR) | System | Level | CBETA Reportable Milestones | Duration | % Complete | Current Schedule Finish Date | CBETA v0 Baseline Schedule Date (August 2017) | CBETA v1? Baseline (December 2017) | print order | Sorted Current Planned Date | Sorted Original Milestone Date | CBETA v0 Baseline Need by Date | Original Reportable Milestone Date | Current Planned Date (A/F) | Mth 'YR Planned Date | Milestone | Reportable Milestone Sort | Reportable Milestone Level Sort | PCR | Comments
1 | Smolenski/Michnoff | Michnoff | BNL | A1.01.01.01.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): NYSERDA Funding Date Start (Actual 10/31/2016) | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 | FY17Q1 | FY17Q1(A)
2 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.01.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Engineering Documentation Complete | 0 d | 100% | 2017-01-31 | 2017-01-31 |  |  |  |  | 2017-01-31 | FY17Q2 | FY17Q2(A)
3 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.01.03 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Prototype Girder Assembled | 0 d | 100% | 2017-04-30 | 2017-04-30 |  |  |  |  | 2017-04-30 | FY17Q3 | FY17Q3(A)
4 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.01.04 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Magnet Production Approved | 0 d | 100% | 2017-06-30 | 2017-06-30 |  |  |  |  | 2017-06-30 | FY17Q3 | FY17Q3(A)
5 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.01.05 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Beam through Main Linac Cryomodule (MLC) [Actual Finish 6/16/17, Planned Finish 8/31/17] | 0 d | 100% | 2017-08-31 | 2017-08-31 |  |  |  |  | 2017-08-31 | FY17Q4 | FY17Q3(A)
6 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.02.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): First Arc Production Magnet Tested | 0 d | 0% | 2017-12-31 | 2017-12-31 |  |  |  |  | 2017-12-31 | FY18Q1
7 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.02.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Fractional Arc Test: Beam through MLC & Prototype Girder | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | 2018-04-30 | FY18Q3
8 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.03.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Girder Production Run Complete | 0 d | 0% | 2018-11-30 | 2018-11-30 |  |  |  |  | 2018-11-30 | FY19Q1
9 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.03.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Final Assembly & Pre-Beam Commissioning Complete | 0 d | 0% | 2019-02-28 | 2019-02-28 |  |  |  |  | 2019-02-28 | FY19Q2
10 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.03.03 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Single Pass Beam Energy Scan | 0 d | 0% | 2019-06-30 | 2019-06-30 |  |  |  |  | 2019-06-30 | FY19Q3
11 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.04.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Single Pass Beam with Energy Recovery | 0 d | 0% | 2019-10-31 | 2019-10-31 |  |  |  |  | 2019-10-31 | FY20Q1
12 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.04.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Four Pass Beam with Energy Recovery (Low Current) | 0 d | 0% | 2019-12-31 | 2019-12-31 |  |  |  |  | 2019-12-31 | FY20Q1
13 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.04.03 |  | A1.01 - Project Management | T-1 | Milestone (T-1): CBETA Commissioned and Project Complete | 0 d | 0% | 2020-04-30 | 2020-04-30 |  |  |  |  | 2020-04-30 | FY20Q2
501 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.01 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design Activities Starts | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 | FY17Q1 | FY17Q1(A)
502 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.02 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Initial Baseline Lattice Design Complete | 0 d | 100% | 2016-11-17 | 2016-11-17 |  |  |  |  | 2016-11-17 | FY17Q1 | FY17Q1(A)
100 | Hoffstaetter | Trbojevic | BNL | A1.02.01.02.03 |  | A1.02 - Accelerator Physics | T-2 | Milestone: FFAG Halbach Magnet Design Chosen | 0 d | 100% | 2016-12-21 | 2016-12-21 |  |  |  |  | 2016-12-21 | FY17Q1 | FY17Q1(A)
503 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Final Baseline Lattice Design complete | 0 d | 100% | 2017-04-10 | 2017-04-10 |  |  |  |  | 2017-04-10 | FY17Q3 | FY17Q3(A)
101 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.05 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Final Baseline Lattice Design Approved by CBETA Board | 0 d | 100% | 2017-05-15 | 2017-05-15 |  |  |  |  | 2017-05-15 | FY17Q3 | FY17Q3(A)
505 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.07 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Lattice Design Updates/Adjustment for Fractional Arc Test Complete | 0 d | 100% | 2017-06-01 | 2017-06-01 |  |  |  |  | 2017-06-01 | FY17Q3 | FY17Q3(A)
516 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.01 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Lattice Design Updates/Adjustment for SPBT Complete | 0 d | 0% | 2017-06-01 | 2017-06-01 |  |  |  |  | 2017-06-01 | FY17Q3
102 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.08 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Lattice Design Updates/Adjustment for Fractional Arc Test Approved by CBETA Board | 0 d | 100% | 2017-06-14 | 2017-06-14 |  |  |  |  | 2017-06-14 | FY17Q3 | FY17Q3(A)
103 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.02 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Lattice Design Updates/Adjustment for SPBT Approved by CBETA Board | 0 d | 0% | 2017-06-14 | 2017-06-14 |  |  |  |  | 2017-06-14 | FY17Q3
514 | Hoffstaetter | Liu | Cornell | A1.02.01.02.17 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Finalize mechanical coordinates of the lattice - Splitter beam pipe and magnet girders | 0 d | 0% | 2017-06-20 | 2017-06-20 |  |  |  |  | 2017-06-20 | FY17Q3
504 | Hoffstaetter | Berg | Cornell | A1.02.01.02.06 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Finalize mechanical coordinates of the lattice - FFAG beam pipe and magnet girders | 0 d | 0% | 2017-08-24 | 2017-08-24 |  |  |  |  | 2017-08-24 | FY17Q4
500 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.01.06 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY17 - Complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
506 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.09 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics with suitable high-energy septum finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
507 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.10 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics for low-energy septum finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
508 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.11 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design of transition Halbach with reduced QF and BDTs finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
509 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.12 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design lattice for the prototype magnets finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
510 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.13 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design lattice for splitter line to match the full energy range finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
511 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.14 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Simulation of orbit correction for the full energy range complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
512 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.15 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Simulation of aperture measurements with beam-loss monitors complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
513 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.16 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Complete optics for each accelerating and recirculating pass finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
517 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.03 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics from source through MLC(1) with space charge finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
104 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.02.01 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Design optics for two, three, and four ERL loops finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 | FY18Q4
105 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.02.03 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Tracking of beam through full loops and check acceptance at dump complete | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 | FY18Q4
515 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.01.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY18 - Complete | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 | FY18Q4
518 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics for one ERL turn through splitter and FFAG finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 | FY18Q4
519 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.05 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design dump line for maximal energy spread and track beam finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 | FY18Q4
520 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.06 |  | A1.02 - Accelerator Physics | T-3 | Milestone: (SPB) Simulation of beam-loss scenarios, including ions, Touschek, wakes, etc. complete | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 | FY18Q4
522 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.02.02 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design of orbit correction for two, three, and four ERL loops finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 | FY18Q4
521 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.01.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY19 - Complete | 0 d | 0% | 2019-10-07 | 2019-10-07 |  |  |  |  | 2019-10-07 | FY20Q1
524 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.04.02.01 |  | A1.02 - Accelerator Physics | T-3 | Milestone: (4PB) Simulation of beam-loss scenarios, including ions, Touschek, wakes, etc. complete | 0 d | 0% | 2019-10-16 | 2019-10-16 |  |  |  |  | 2019-10-16 | FY20Q1
523 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.04.01.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY20 - Complete | 0 d | 0% | 2020-05-06 | 2020-05-06 |  |  |  |  | 2020-05-06 | FY20Q2
525 | Gulliford | Gulliford | Cornell | A1.03.01.01.01.01.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: Start of DC Gun Conditioning Activities | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 | FY17Q1 | FY17Q1(A)
536 | Gulliford | Gulliford | Cornell | A1.03.04.01.02 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B1 Merger - Transport Line Layout & Drawings Complete | 0 d | 100% | 2017-02-20 | 2017-02-20 |  |  |  |  | 2017-02-20 | FY17Q2 | FY17Q2(A)
537 | Gulliford | Gulliford | Cornell | A1.03.04.02.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - 80x20 Stand/Girders | 0 d | 100% | 2017-03-16 | 2017-03-16 |  |  |  |  | 2017-03-16 | FY17Q2 | FY17Q2(A)
540 | Gulliford | Gulliford | Cornell | A1.03.05.01.01.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 DL - Transport Line Layout & Drawings Complete | 0 d | 100% | 2017-03-22 | 2017-03-22 |  |  |  |  | 2017-03-22 | FY17Q2 | FY17Q2(A)
531 | Gulliford | Cultera | Cornell | A1.03.03.02.01.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: Preliminary Cathode Material Existing and Available @ Cornell | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | 2017-04-03 | FY17Q3 | FY17Q3(A)
543 | Gulliford | Gulliford | Cornell | A1.03.05.02.02.07 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All B2 DL Vacuum Transport Line Materials Received | 0 d | 100% | 2017-04-12 | 2017-04-12 |  |  |  |  | 2017-04-12 | FY17Q3 | FY17Q3(A)
538 | Gulliford | Gulliford | Cornell | A1.03.04.03.08 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B1 Merger Installation Complete | 0 d | 100% | 2017-04-26 | 2017-04-26 |  |  |  |  | 2017-04-26 | FY17Q3 | FY17Q3(A)
539 | Gulliford | Gulliford | Cornell | A1.03.04.04.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B1 Merger Beam Line Instrumentation Integration Complete | 0 d | 100% | 2017-05-02 | 2017-05-02 |  |  |  |  | 2017-05-02 | FY17Q3 | FY17Q3(A)
545 | Gulliford | Gulliford | Cornell | A1.03.05.03.01.05 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 Diagnostic Beam Line (FY17) Installation Complete | 0 d | 100% | 2017-05-04 | 2017-05-04 |  |  |  |  | 2017-05-04 | FY17Q3 | FY17Q3(A)
528 | Gulliford | Bartnik | Cornell | A1.03.02.02.01.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - 43 MHz Laser Parts | 0 d | 100% | 2017-05-05 | 2017-05-05 |  |  |  |  | 2017-05-05 | FY17Q3 | FY17Q3(A)
108 | Gulliford | Gulliford | Cornell | A1.03.05.04.04 |  | A1.03 - DC/Gun Injector | T-2 | Milestone: B2 Diagnostic Beam Line Instrumentation Integration Complete | 0 d | 0% | 2017-06-21 | 2017-06-21 |  |  |  |  | 2017-06-21 | FY17Q3
542 | Gulliford | Gulliford | Cornell | A1.03.05.02.01.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received and Accepted - B2 DL Magnets | 0 d | 100% | 2017-06-26 | 2017-06-26 |  |  |  |  | 2017-06-26 | FY17Q3 | FY17Q3(A)
526 | Gulliford | Bartnik | Cornell | A1.03.02.01.02.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - E/O Modulator | 0 d | 0% | 2017-07-12 | 2017-07-12 |  |  |  |  | 2017-07-12 | FY17Q4
106 | Gulliford | Bartnik | Cornell | A1.03.02.02.02.01 |  | A1.03 - DC/Gun Injector | T-2 | Milestone: Laser Room Move Complete and Ready for Table Setup[Clean Room conditions established | 0 d | 100% | 2017-08-15 | 2017-08-15 |  |  |  |  | 2017-08-15 | FY17Q4 | FY17Q4(A)
532 | Gulliford | Cultera | Cornell | A1.03.03.02.02.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: FAT Cathode Material Available @ Cornell | 0 d | 100% | 2017-08-31 | 2017-08-31 |  |  |  |  | 2017-08-31 | FY17Q4 | FY17Q4(A)
527 | Gulliford | Bartnik | Cornell | A1.03.02.01.03.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: E/O Modulator Software Development Complete | 0 d | 0% | 2017-09-07 | 2017-09-07 |  |  |  |  | 2017-09-07 | FY17Q4
529 | Gulliford | Bartnik | Cornell | A1.03.02.02.02.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: 43 MHz Laser - Modification and Table Set-up Complete | 0 d | 0% | 2017-09-13 | 2017-09-13 |  |  |  |  | 2017-09-13 | FY17Q4
107 | Gulliford | Gulliford | Cornell | A1.03.02.03.04 |  | A1.03 - DC/Gun Injector | T-2 | Milestone: Laser Transport Line - Beam Test (Gun Only) Complete | 0 d | 0% | 2017-09-22 | 2017-09-22 |  |  |  |  | 2017-09-22 | FY17Q4
530 | Gulliford | Cultrera | Cornell | A1.03.03.01.02 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - Cathode Material | 0 d | 0% | 2018-01-25 | 2018-01-25 |  |  |  |  | 2018-01-25 | FY18Q2
541 | Gulliford | Gulliford | Cornell | A1.03.05.01.02.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 DL - Cross Pipe Layout & Drawings Complete | 0 d | 0% | 2018-02-08 | 2018-02-08 |  |  |  |  | 2018-02-08 | FY18Q2
544 | Gulliford | Gulliford | Cornell | A1.03.05.02.03.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All B2 DL Cross Pipe Materials Received | 0 d | 0% | 2018-03-30 | 2018-03-30 |  |  |  |  | 2018-03-30 | FY18Q2
546 | Gulliford | Gulliford | Cornell | A1.03.05.03.02.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 Diagnostic Beam Line (FY18) Installation Complete | 0 d | 0% | 2018-04-10 | 2018-04-10 |  |  |  |  | 2018-04-10 | FY18Q3
533 | Gulliford | Cultera | Cornell | A1.03.03.02.03.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: SPBT Cathode Material Available @ Cornell | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | 2018-04-30 | FY18Q3
534 | Gulliford | Cultera | Cornell | A1.03.03.02.04.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: SPBT-ER Cathode Material Available @ Cornell | 0 d | 0% | 2019-06-30 | 2019-06-30 |  |  |  |  | 2019-06-30 | FY19Q3
535 | Gulliford | Cultera | Cornell | A1.03.03.02.05.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: 4PBT Cathode Material Available @ Cornell | 0 d | 0% | 2019-10-31 | 2019-10-31 |  |  |  |  | 2019-10-31 | FY20Q1
569 | Fumata | Sabol | Cornell | A1.04.05.02.01.01.02 |  | A1.04 - RF Systems | T-3 | Milestone: Design Pump System Layout (#1) Complete | 0 d | 100% | 2016-11-07 | 2016-11-07 |  |  |  |  | 2016-11-07 | FY17Q1 | FY17Q1(A)
556 | Fumata | Quigley | Cornell | A1.04.02.02.06 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Warmed Up and Ready for Disconnects | 0 d | 100% | 2016-11-21 | 2016-11-21 |  |  |  |  | 2016-11-21 | FY17Q1 | FY17Q1(A)
547 | Fumata | Quigley | Cornell | A1.04.01.01.01.01 |  | A1.04 - RF Systems | T-3 | Milestone: MLC ready for CBETA work | 0 d | 100% | 2016-12-01 | 2016-12-01 |  |  |  |  | 2016-12-01 | FY17Q1 | FY17Q1(A)
555 | Fumata | Quigley | Cornell | A1.04.02.01.01 |  | A1.04 - RF Systems | T-3 | Milestone: ICM ready for CBETA work | 0 d | 100% | 2016-12-01 | 2016-12-01 |  |  |  |  | 2016-12-01 | FY17Q1 | FY17Q1(A)
548 | Fumata | Quigley | Cornell | A1.04.01.01.02.06 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Warmed Up and Ready for Disconnects | 0 d | 100% | 2016-12-22 | 2016-12-22 |  |  |  |  | 2016-12-22 | FY17Q1 | FY17Q1(A)
549 | Fumata | Quigley | Cornell | A1.04.01.01.03.03 |  | A1.04 - RF Systems | T-3 | Milestone: MLC in final Location | 0 d | 100% | 2017-01-12 | 2017-01-12 |  |  |  |  | 2017-01-12 | FY17Q2 | FY17Q2(A)
559 | Fumata | Quigley | Cornell | A1.04.03.01.01.05 |  | A1.04 - RF Systems | T-3 | Milestone: FAT - LLRF Design Complete | 0 d | 100% | 2017-02-22 | 2017-02-22 |  |  |  |  | 2017-02-22 | FY17Q2 | FY17Q2(A)
566 | Fumata | Sabol | Cornell | A1.04.05.01.01.01.03.03 |  | A1.04 - RF Systems | T-3 | Milestone: All Cryogenic MLC Transferline Procurements Received and Complete | 0 d | 100% | 2017-02-24 | 2017-02-24 |  |  |  |  | 2017-02-24 | FY17Q2 | FY17Q2(A)
567 | Fumata | Sabol | Cornell | A1.04.05.01.02.02.03 |  | A1.04 - RF Systems | T-3 | Milestone: All Cryogenic MLC Transferline Procurements Received and Complete | 0 d | 100% | 2017-03-10 | 2017-03-10 |  |  |  |  | 2017-03-10 | FY17Q2 | FY17Q2(A)
570 | Fumata | Sabol | Cornell | A1.04.05.02.01.02.07 |  | A1.04 - RF Systems | T-3 | Milestone: Pump Skid #1 - All Procurement Materials Received and Ready for Installation | 0 d | 100% | 2017-03-10 | 2017-03-10 |  |  |  |  | 2017-03-10 | FY17Q2 | FY17Q2(A)
550 | Fumata | Quigley | Cornell | A1.04.01.02.01.04 |  | A1.04 - RF Systems | T-3 | MLC Cool Down #2 - Cool down to 4K (by Apr 3) | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | 2017-04-03 | FY17Q3 | FY17Q3(A)
568 | Fumata | Sabol | Cornell | A1.04.05.01.03.03 |  | A1.04 - RF Systems | T-3 | Milestone: All Cryogenic MLC Transferline Installation & Leak Test Complete | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | 2017-04-03 | FY17Q3 | FY17Q3(A)
551 | Fumata | Quigley | Cornell | A1.04.01.02.01.06 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #2 - Ready for RF Power (by 4/20) | 0 d | 100% | 2017-04-20 | 2017-04-20 |  |  |  |  | 2017-04-20 | FY17Q3 | FY17Q3(A)
557 | Fumata | Quigley | Cornell | A1.04.02.03.01.05 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Cool Down #2 - Ready for RF Power (by 4/20) | 0 d | 100% | 2017-04-20 | 2017-04-20 |  |  |  |  | 2017-04-20 | FY17Q3 | FY17Q3(A)
552 | Fumata | Quigley | Cornell | A1.04.01.02.01.07 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #2 - RF Power Turned On and MLC System Stable by 5/2 | 0 d | 100% | 2017-05-03 | 2017-05-03 |  |  |  |  | 2017-05-03 | FY17Q3 | FY17Q3(A)
558 | Fumata | Quigley | Cornell | A1.04.02.03.01.06 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Cool Down #2 - RF Power Turned On and ICM System Stable by 5/2 | 0 d | 100% | 2017-05-03 | 2017-05-03 |  |  |  |  | 2017-05-03 | FY17Q3 | FY17Q3(A)
565 | Fumata | Quigley | Cornell | A1.04.04.02.02.06 |  | A1.04 - RF Systems | T-3 | Milestone: All Waveguide & Tuner Procurements Received and Complete | 0 d | 0% | 2017-05-08 | 2017-05-08 |  |  |  |  | 2017-05-08 | FY17Q3
112 | Fumata | Quigley | Cornell | A1.04.04.02.01.04 |  | A1.04 - RF Systems | T-2 | Milestone: 1st Article Solid State Amplifiers (SSA) Received @ Cornell (end of August) | 0 d | 0% | 2017-09-06 | 2017-09-06 |  |  |  |  | 2017-09-06 | FY17Q4
573 | Fumata | Sabol | Cornell | A1.04.05.02.02.01.02 |  | A1.04 - RF Systems | T-3 | Milestone: Design Pump System Layout (#2-3-4) Complete | 0 d | 0% | 2017-09-28 | 2017-09-28 |  |  |  |  | 2017-09-28 | FY17Q4
115 | Fumata | Quigley | Cornell | A1.04.04.04.01.03 |  | A1.04 - RF Systems | T-2 | Milestone: RF Systems Ready for Fractional Arc Test (FAT) | 0 d | 0% | 2017-10-05 | 2017-10-05 |  |  |  |  | 2017-10-05 | FY18Q1
560 | Fumata | Quigley | Cornell | A1.04.03.02.01.05 |  | A1.04 - RF Systems | T-3 | Milestone: All LLRF Material/Components (FAT) Complete | 0 d | 0% | 2017-10-10 | 2017-10-10 |  |  |  |  | 2017-10-10 | FY18Q1
576 | Fumata | Sabol | Cornell | A1.04.05.03.01.01.04 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Pump Skids - All Procurement Materials Received and Ready for Installation | 0 d | 0% | 2017-10-10 | 2017-10-10 |  |  |  |  | 2017-10-10 | FY18Q1
577 | Fumata | Sabol | Cornell | A1.04.05.03.01.02.10 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Pump Skids- Installation Complete | 0 d | 0% | 2017-11-27 | 2017-11-27 |  |  |  |  | 2017-11-27 | FY18Q1
562 | Fumata | Quigley | Cornell | A1.04.03.03.01.07 |  | A1.04 - RF Systems | T-3 | Milestone: LLRF (FAT) Installation & Integration Complete | 0 d | 0% | 2017-12-26 | 2017-12-26 |  |  |  |  | 2017-12-26 | FY18Q1
113 | Fumata | Quigley | Cornell | A1.04.04.02.01.05 |  | A1.04 - RF Systems | T-2 | Milestone: 5 Remaining Solid State Amplifiers (SSA) Received @ Cornell (by end of Dec) | 0 d | 0% | 2017-12-29 | 2017-12-29 |  |  |  |  | 2017-12-29 | FY18Q1
564 | Fumata | Quigley | Cornell | A1.04.04.02.01.09 |  | A1.04 - RF Systems | T-3 | Milestone: All RF Amplifier Procurements Received and Complete | 0 d | 0% | 2017-12-29 | 2017-12-29 |  |  |  |  | 2017-12-29 | FY18Q1
574 | Fumata | Sabol | Cornell | A1.04.05.02.02.02.08 |  | A1.04 - RF Systems | T-3 | Milestone: Pump Skid #2-3-4 - All Procurement Materials Received and Ready for Installation | 0 d | 0% | 2018-01-30 | 2018-01-30 |  |  |  |  | 2018-01-30 | FY18Q2
114 | Fumata | Quigley | Cornell | A1.04.04.03.11 |  | A1.04 - RF Systems | T-2 | Milestone - RF Amplifier/Deflector RF Cavity System Installation Complete | 0 d | 0% | 2018-02-21 | 2018-02-21 |  |  |  |  | 2018-02-21 | FY18Q2
575 | Fumata | Sabol | Cornell | A1.04.05.02.02.03.08.02 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Pump Skid #2-3-4 - Vibration Mitigation Complete | 0 d | 0% | 2018-03-15 | 2018-03-15 |  |  |  |  | 2018-03-15 | FY18Q2
117 | Fumata | Sabol | Cornell | A1.04.05.02.02.03.10 |  | A1.04 - RF Systems | T-2 | Milestone: MLC Pump Skid #2-3-4 - Installation Complete | 0 d | 0% | 2018-03-22 | 2018-03-22 |  |  |  |  | 2018-03-22 | FY18Q2
553 | Fumata | Quigley | Cornell | A1.04.01.03.01.04 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #2A - Ready for RF Power | 0 d | 0% | 2018-04-02 | 2018-04-02 |  |  |  |  | 2018-04-02 | FY18Q3
109 | Fumata | Quigley | Cornell | A1.04.01.03.01.05 |  | A1.04 - RF Systems | T-2 | Milestone: MLC Cool Down #2A - RF Power Turned On and MLC System Stable | 0 d | 0% | 2018-04-16 | 2018-04-16 |  |  |  |  | 2018-04-16 | FY18Q3
571 | Fumata | Sabol | Cornell | A1.04.05.02.01.03.09.04 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Pump Skid #1 - Vibration Mitigation Complete | 0 d | 0% | 2018-05-09 | 2018-05-09 |  |  |  |  | 2018-05-09 | FY18Q3
572 | Fumata | Sabol | Cornell | A1.04.05.02.01.03.10 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Pump Skid#1 Installation Complete | 0 d | 0% | 2018-05-09 | 2018-05-09 |  |  |  |  | 2018-05-09 | FY18Q3
111 | Fumata | Quigley | Cornell | A1.04.03.01.02.03 |  | A1.04 - RF Systems | T-2 | Milestone: SPBT - LLRF Design Updates Complete | 0 d | 0% | 2018-06-04 | 2018-06-04 |  |  |  |  | 2018-06-04 | FY18Q3
116 | Fumata | Quigley | Cornell | A1.04.04.04.02.02 |  | A1.04 - RF Systems | T-2 | Milestone: RF Systems Ready for SPBT | 0 d | 0% | 2018-07-10 | 2018-07-10 |  |  |  |  | 2018-07-10 | FY18Q4
561 | Fumata | Quigley | Cornell | A1.04.03.02.02.05 |  | A1.04 - RF Systems | T-3 | Milestone: All LLRF Material/Components (SPBT) Complete | 0 d | 0% | 2018-08-28 | 2018-08-28 |  |  |  |  | 2018-08-28 | FY18Q4
563 | Fumata | Quigley | Cornell | A1.04.03.03.02.05 |  | A1.04 - RF Systems | T-3 | Milestone: LLRF (SPBT) Installation & Integration Complete | 0 d | 0% | 2018-09-26 | 2018-09-26 |  |  |  |  | 2018-09-26 | FY18Q4
110 | Fumata | Quigley | Cornell | A1.04.01.04.02.04 |  | A1.04 - RF Systems | T-2 | Milestone: MLC Cool Down #3 - RF Power Turned On and MLC System Stable | 0 d | 0% | 2019-04-15 | 2019-04-15 |  |  |  |  | 2019-04-15 | FY19Q3
554 | Fumata | Quigley | Cornell | A1.04.01.04.02.03 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #3 - Ready for RF Power | 0 d | 0% | 2019-04-15 | 2019-04-15 |  |  |  |  | 2019-04-15 | FY19Q3
578 | Tuozzolo | Tuozzolo | BNL | A1.05.01.01.01.04 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: PreProd FFAG Magnets - Halbach magnet w/ corrector design complete | 0 d | 100% | 2017-03-01 | 2017-03-01 |  |  |  |  | 2017-03-01 | FY17Q2 | FY17Q2(A)
579 | Tuozzolo | Tuozzolo | BNL | A1.05.01.01.02.03 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: PreProd FFAG Girder - Design Complete | 0 d | 100% | 2017-03-17 | 2017-03-17 |  |  |  |  | 2017-03-17 | FY17Q2 | FY17Q2(A)
118 | Tuozzolo | Tuozzolo | BNL | A1.05.01.02.01.11 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Magnets - Procurements complete | 0 d | 100% | 2017-04-18 | 2017-04-18 |  |  |  |  | 2017-04-18 | FY17Q3 | FY17Q3(A)
580 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.01.02 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: PreProd FFAG Magnets - PMM measurements complete and documented | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | 2017-04-24 | FY17Q3 | FY17Q3(A)
581 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.03.01 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Vacuum Chambers Received from Cornell for Pre-Production FFAG Magnet Assembly as of 4/24 | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | 2017-04-24 | FY17Q3 | FY17Q3(A)
119 | Tuozzolo | Tuozzolo | BNL | A1.05.01.02.02.06 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Girder - Procurements complete | 0 d | 100% | 2017-04-26 | 2017-04-26 |  |  |  |  | 2017-04-26 | FY17Q3 | FY17Q3(A)
120 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.01.06 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Magnets - Assembly complete | 0 d | 100% | 2017-04-27 | 2017-04-27 |  |  |  |  | 2017-04-27 | FY17Q3 | FY17Q3(A)
121 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.02.02 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Girder - Assembly complete | 0 d | 100% | 2017-04-27 | 2017-04-27 |  |  |  |  | 2017-04-27 | FY17Q3 | FY17Q3(A)
122 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.03.03 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Pre-Production Magnet/Vacuum Chamber Assembly on Girders Complete | 0 d | 100% | 2017-05-03 | 2017-05-03 |  |  |  |  | 2017-05-03 | FY17Q3 | FY17Q3(A)
123 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.03.05 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Magnets and Girder - Halbach Magnets & Girder Assembly & Testing complete | 0 d | 100% | 2017-07-07 | 2017-07-07 |  |  |  |  | 2017-07-07 | FY17Q4 | FY17Q4(A)
124 | Tuozzolo | Tuozzolo | BNL | A1.05.02.01.01.05 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets - Halbach w/ corrector design revisions complete | 0 d | 100% | 2017-08-02 | 2017-08-02 |  |  |  |  | 2017-08-02 | FY17Q4 | FY17Q4(A)
125 | Tuozzolo | Tuozzolo | BNL | A1.05.02.01.02.03 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Girders - Design Complete | 0 d | 0% | 2017-08-25 | 2017-08-25 |  |  |  |  | 2017-08-25 | FY17Q4
582 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.08 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - 1st Article Table Top plate Procurement complete and received @ BNL | 0 d | 0% | 2018-01-25 | 2018-01-25 |  |  |  |  | 2018-01-25 | FY18Q2
584 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.10 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - 1st Article Frame/Stand Procurements complete and received @ Cornell in time for FAT | 0 d | 0% | 2018-01-25 | 2018-01-25 |  |  |  |  | 2018-01-25 | FY18Q2
586 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.04.03 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Magnets - Pre-Girder Halbach Magnet Assembly 1st Article tests & documentation complete | 0 d | 0% | 2018-02-26 | 2018-02-26 |  |  |  |  | 2018-02-26 | FY18Q2
129 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.12 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Girders Procurements complete | 0 d | 0% | 2018-03-23 | 2018-03-23 |  |  |  |  | 2018-03-23 | FY18Q2
583 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.09 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - ALL Top plate Procurement complete and received @ BNL | 0 d | 0% | 2018-03-23 | 2018-03-23 |  |  |  |  | 2018-03-23 | FY18Q2
585 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.11 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - ALL Frame/Stand Procurements complete and received @ Cornell | 0 d | 0% | 2018-03-23 | 2018-03-23 |  |  |  |  | 2018-03-23 | FY18Q2
589 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.03 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: FFAG Straight Vacuum Chambers Received from Cornell for Production Magnet Assembly (Remainder) | 0 d | 0% | 2018-03-28 | 2018-03-28 |  |  |  |  | 2018-03-28 | FY18Q2
587 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.01 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Vacuum Chambers Received from Cornell for Production Magnet Assembly (1st Article) - FAGD1 | 0 d | 0% | 2018-04-10 | 2018-04-10 |  |  |  |  | 2018-04-10 | FY18Q3
588 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.02 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: FFAG Arc&Transition Vacuum Chambers Received from Cornell for Production Magnet Assembly (Remainder) (Multiple shipments per diagram on Yulins layout) | 0 d | 0% | 2018-05-18 | 2018-05-18 |  |  |  |  | 2018-05-18 | FY18Q3
126 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.01.03.04 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Vendor Procurement [BNL]: Production FFAG Magnets - Permanent Magnet Blocks -All Lots Received @ BNL | 0 d | 0% | 2018-06-25 | 2018-06-25 |  |  |  |  | 2018-06-25 | FY18Q3
127 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.01.07.04 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets Halbach Magnets Assembly (Magnet, Housing, Windowframe Corrector) - ALL Sectors Received @ BNL [Qty: xx] | 0 d | 0% | 2018-11-27 | 2018-11-27 |  |  |  |  | 2018-11-27 | FY19Q1
128 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.01.08 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets ALL Procurements complete and received from vendor | 0 d | 0% | 2018-11-27 | 2018-11-27 |  |  |  |  | 2018-11-27 | FY19Q1
130 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.03 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: ALL Sectors - Measuring and adjusting Halbach Magnet Assemblies Complete [Qty: xx] | 0 d | 0% | 2018-12-04 | 2018-12-04 |  |  |  |  | 2018-12-04 | FY19Q1
131 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.04.02.07 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: ALL Sectors - Survey & Testing of Halbach Magnet Assemblies Complete [Qty: xx] | 0 d | 0% | 2019-01-04 | 2019-01-04 |  |  |  |  | 2019-01-04 | FY19Q2
134 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.03.03.07 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets and Girders - ALL Sectors - Halbach Magnets & Girder Ship to Cornell complete | 0 d | 0% | 2019-01-24 | 2019-01-24 |  |  |  |  | 2019-01-24 | FY19Q2
133 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.04.02.07 |  | A1.05 - FFAG Magnets & Girders | T-2 | FFAG Production Magnets and Girders - ALL Sectors - ALL Halbach Magnet & Girder Assembly, Survey, Testing, and Documentation Complete [Qty: xx] | 0 d | 0% | 2019-03-08 | 2019-03-08 |  |  |  |  | 2019-03-08 | FY19Q2
132 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.04.04 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets - Pre-Girder Halbach Magnet Assembly tests & documentation complete | 0 d | 0% | 2019-03-12 | 2019-03-12 |  |  |  |  | 2019-03-12 | FY19Q2
150 | Burke | Burke | Cornell | A1.06.02.02.03.03 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets - Beam Stop Table - Assembly Complete | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 | FY17Q1 | [6 empty] | Incorrect dates - kwj
600 | Burke | Burke | Cornell | A1.06.01.02.01.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Electromagnet Table - Procurements complete | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 | FY17Q1
592 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.03.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Dipole Corrector Magnets - Design complete | 0 d | 100% | 2017-01-20 | 2017-01-20 |  |  |  |  | 2017-01-20 | FY17Q2 | FY17Q2(A)
590 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Dipoles - Design complete | 0 d | 100% | 2017-01-27 | 2017-01-27 |  |  |  |  | 2017-01-27 | FY17Q2 | FY17Q2(A)
591 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Quadrupoles - Design complete | 0 d | 100% | 2017-01-27 | 2017-01-27 |  |  |  |  | 2017-01-27 | FY17Q2 | FY17Q2(A)
593 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.05 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Dipoles - Quadrupoles-Correctors - ALL Design complete | 0 d | 100% | 2017-03-13 | 2017-03-13 |  |  |  |  | 2017-03-13 | FY17Q2 | FY17Q2(A)
135 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.03 |  | A1.06 - Splitter Magnets | T-3(2?) | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - Contract Awarded | 0 d | 0% | 2017-04-21 | 2017-04-21 |  |  |  |  | 2017-04-21 | FY17Q3
596 | Burke | Burke | Cornell | A1.06.01.01.01.04.01.05 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Mounts and Stages - ALL Design Complete | 0 d | 0% | 2017-05-17 | 2017-05-17 |  |  |  |  | 2017-05-17 | FY17Q3
611 | Burke | Burke | Cornell | A1.06.02.01.02.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Quadrupoles - Design complete | 0 d | 0% | 2017-05-30 | 2017-05-30 |  |  |  |  | 2017-05-30 | FY17Q3
613 | Burke | Burke | Cornell | A1.06.02.01.03.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Magnet Mounts - Design complete | 0 d | 0% | 2017-05-30 | 2017-05-30 |  |  |  |  | 2017-05-30 | FY17Q3
609 | Burke | Burke | Cornell | A1.06.02.01.01.01.04 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Dipoles - Design complete | 0 d | 0% | 2017-06-07 | 2017-06-07 |  |  |  |  | 2017-06-07 | FY17Q3
612 | Burke | Burke | Cornell | A1.06.02.01.02.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets (Quads) - Contract Awarded | 0 d | 0% | 2017-06-27 | 2017-06-27 |  |  |  |  | 2017-06-27 | FY17Q3
601 | Burke | Burke | Cornell | A1.06.01.02.01.03.09 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets -Electromagnet Table Supporting Hardware - ALL Design Complete | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 | FY17Q4
610 | Burke | Burke | Cornell | A1.06.02.01.01.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets (Dipoles) - Contract Awarded | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 | FY17Q4
143 | Burke | Burke | Cornell | A1.06.01.02.01.01.05 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Electromagnet Table - ALL Design Complete | 0 d | 0% | 2017-07-21 | 2017-07-21 |  |  |  |  | 2017-07-21 | FY17Q4
614 | Burke | Burke | Cornell | A1.06.02.01.03.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Support Hardware Procurements complete | 0 d | 0% | 2017-07-26 | 2017-07-26 |  |  |  |  | 2017-07-26 | FY17Q4
139 | Burke | Burke | Cornell | A1.06.01.01.01.02.01.05 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Common Magnets - Design complete | 0 d | 0% | 2017-08-10 | 2017-08-10 |  |  |  |  | 2017-08-10 | FY17Q4
615 | Burke | Burke | Cornell | A1.06.02.02.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Beam Stop Table - ALL Design Complete | 0 d | 0% | 2017-08-25 | 2017-08-25 |  |  |  |  | 2017-08-25 | FY17Q4
616 | Burke | Burke | Cornell | A1.06.02.02.02.04 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Table Support Hardware - Procurements complete | 0 d | 0% | 2017-09-25 | 2017-09-25 |  |  |  |  | 2017-09-25 | FY17Q4
149 | Burke | Burke | Cornell | A1.06.02.01.03.03.06 |  | A1.06 - Splitter Magnets | T-2 | Milestones: Extraction Line Magnets - Magnets and Mounts Assembled on Stands | 0 d | 0% | 2017-09-26 | 2017-09-26 |  |  |  |  | 2017-09-26 | FY17Q4
597 | Burke | Burke | Cornell | A1.06.01.01.01.04.02.08 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Support Hardware - Procurements complete | 0 d | 0% | 2017-09-26 | 2017-09-26 |  |  |  |  | 2017-09-26 | FY17Q4
140 | Burke | Burke | Cornell | A1.06.01.01.01.03.01.05 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Septa Magnets - Design complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
136 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.15 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - 1st Batch Delivered to Cornell (Sector-SX Northeast) 10/24/17 | 0 d | 0% | 2017-10-26 | 2017-10-26 |  |  |  |  | 2017-10-26 | FY18Q1
148 | Burke | Burke | Cornell | A1.06.02.01.02.02.07 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets - Quads - Procurement complete | 0 d | 0% | 2017-12-27 | 2017-12-27 |  |  |  |  | 2017-12-27 | FY18Q1
147 | Burke | Burke | Cornell | A1.06.02.01.01.02.07 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets - Dipoles - Procurement complete | 0 d | 0% | 2018-01-05 | 2018-01-05 |  |  |  |  | 2018-01-05 | FY18Q2
598 | Burke | Burke | Cornell | A1.06.01.01.01.05.01.08 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Supporting Hardware - Assembly complete for FAT | 0 d | 0% | 2018-01-11 | 2018-01-11 |  |  |  |  | 2018-01-11 | FY18Q2
602 | Burke | Burke | Cornell | A1.06.01.02.01.04.12 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Procurements complete (FAT) | 0 d | 0% | 2018-01-18 | 2018-01-18 |  |  |  |  | 2018-01-18 | FY18Q2
141 | Burke | Burke | Cornell | A1.06.01.01.01.05.02.03 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Magnets & Hardware - Pre-Table Installation Complete (FAT) | 0 d | 0% | 2018-01-26 | 2018-01-26 |  |  |  |  | 2018-01-26 | FY18Q2
599 | Burke | Burke | Cornell | A1.06.01.01.01.05.01.09 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Supporting Hardware - Assembly complete for SPBT and 4PBT | 0 d | 0% | 2018-02-09 | 2018-02-09 |  |  |  |  | 2018-02-09 | FY18Q2
604 | Burke | Burke | Cornell | A1.06.01.02.01.05.09 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Pre-Assembly complete (FAT) | 0 d | 0% | 2018-02-21 | 2018-02-21 |  |  |  |  | 2018-02-21 | FY18Q2
142 | Burke | Burke | Cornell | A1.06.01.01.01.05.02.04 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Magnets & Hardware - Pre-Table Installation Compete (SPBT & 4PBT) | 0 d | 0% | 2018-03-05 | 2018-03-05 |  |  |  |  | 2018-03-05 | FY18Q2
617 | Burke | Burke | Cornell | A1.06.02.03.01.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets and Tables - Assembly (SPBT) - All Material available for Installation | 0 d | 0% | 2018-03-09 | 2018-03-09 |  |  |  |  | 2018-03-09 | FY18Q2
603 | Burke | Burke | Cornell | A1.06.01.02.01.04.13 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Procurements complete (SPBT & 4PBT) | 0 d | 0% | 2018-03-12 | 2018-03-12 |  |  |  |  | 2018-03-12 | FY18Q2
594 | Burke | Burke | Cornell | A1.06.01.01.01.02.02.06 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Common Magnets - Procurement Complete | 0 d | 0% | 2018-03-21 | 2018-03-21 |  |  |  |  | 2018-03-21 | FY18Q2
606 | Burke | Burke | Cornell | A1.06.01.03.01.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets and Tables - Assembly (FAT) - All Material available for Installation (1/8th magnets + 2 tables) | 0 d | 0% | 2018-03-21 | 2018-03-21 |  |  |  |  | 2018-03-21 | FY18Q2
595 | Burke | Burke | Cornell | A1.06.01.01.01.03.02.06 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Septa Magnets - Procurement complete | 0 d | 0% | 2018-04-12 | 2018-04-12 |  |  |  |  | 2018-04-12 | FY18Q3
151 | Burke | Burke | Cornell | A1.06.02.03.01.06 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets and Tables - Assembly (SPBT) - Complete | 0 d | 0% | 2018-04-18 | 2018-04-18 |  |  |  |  | 2018-04-18 | FY18Q3
137 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.16 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - 2nd Batch Delivered to Cornell (Sector-RX - Northwest) 4/20/18 | 0 d | 0% | 2018-04-26 | 2018-04-26 |  |  |  |  | 2018-04-26 | FY18Q3
605 | Burke | Burke | Cornell | A1.06.01.02.01.05.10 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Pre-Assembly complete (SPBT & 4PBT) | 0 d | 0% | 2018-05-30 | 2018-05-30 |  |  |  |  | 2018-05-30 | FY18Q3
144 | Burke | Burke | Cornell | A1.06.01.03.01.08 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets and Tables - Assembly (FAT) - Complete | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 | FY18Q3
607 | Burke | Burke | Cornell | A1.06.01.03.02.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets and Tables - Assembly (SPBT) - All Material available for Installation (? magnets + 2 tables) | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 | FY18Q3
138 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.21 |  | A1.06 - Splitter Magnets | T-2(3?) | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - ALL Procurements complete | 0 d | 0% | 2018-06-14 | 2018-06-14 |  |  |  |  | 2018-06-14 | FY18Q3
145 | Burke | Burke | Cornell | A1.06.01.03.02.08 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets and Tables - Assembly (SPBT) - Complete | 0 d | 0% | 2018-08-15 | 2018-08-15 |  |  |  |  | 2018-08-15 | FY18Q4
608 | Burke | Burke | Cornell | A1.06.01.03.03.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets and Tables - Assembly (4PBT) - All Material available for Installation (3/4 of magnets - remaining) | 0 d | 0% | 2018-08-15 | 2018-08-15 |  |  |  |  | 2018-08-15 | FY18Q4
146 | Burke | Burke | Cornell | A1.06.01.03.03.08 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets and Tables - Assembly (4PBT) - Complete | 0 d | 0% | 2018-10-04 | 2018-10-04 |  |  |  |  | 2018-10-04 | FY19Q1
158 | Barley | Barley | Cornell | A1.07.04.02.02 |  | A1.07 - Power Supplies | T-2 | Milestone: Contract Awarded - FFAG Corrector Power Supplies | 0 d | 0% | 2017-10-27 | 2017-10-27 |  |  |  |  | 2017-10-27 | FY18Q1
152 | Barley | Barley | Cornell | A1.07.01.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Dipole Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2017-11-07 | 2017-11-07 |  |  |  |  | 2017-11-07 | FY18Q1
154 | Barley | Barley | Cornell | A1.07.02.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Quadrupole Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2017-11-08 | 2017-11-08 |  |  |  |  | 2017-11-08 | FY18Q1
156 | Barley | Barley | Cornell | A1.07.03.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Corrector Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2017-11-08 | 2017-11-08 |  |  |  |  | 2017-11-08 | FY18Q1
159 | Barley | Barley | Cornell | A1.07.04.02.08 |  | A1.07 - Power Supplies | T-2 | Milestone: All FFAG Corrector PS Procurement Received | 0 d | 0% | 2018-03-28 | 2018-03-28 |  |  |  |  | 2018-03-28 | FY18Q2
160 | Barley | Barley | Cornell | A1.07.04.03.03.03 |  | A1.07 - Power Supplies | T-2 | Milestone: FFAG Corrector Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2018-04-25 | 2018-04-25 |  |  |  |  | 2018-04-25 | FY18Q3
153 | Barley | Barley | Cornell | A1.07.01.03.03.05 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Dipole Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | 2018-04-30 | FY18Q3
155 | Barley | Barley | Cornell | A1.07.02.03.03.05 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Quadrupole Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | 2018-04-30 | FY18Q3
157 | Barley | Barley | Cornell | A1.07.03.03.03.05 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Corrector Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-05-01 | 2018-05-01 |  |  |  |  | 2018-05-01 | FY18Q3
161 | Barley | Barley | Cornell | A1.07.04.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: FFAG Corrector Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-08-07 | 2018-08-07 |  |  |  |  | 2018-08-07 | FY18Q4
627 | Dobbins | Dobbins | Cornell | A1.08.03.01.01.03 |  | A1.08 - Controls | T-3 | Milestone: File Server Design Complete | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 | FY17Q1 | FY17Q1(A)
628 | Dobbins | Dobbins | Cornell | A1.08.03.01.02.03 |  | A1.08 - Controls | T-3 | Milestone: All File Server Procurements Complete | 0 d | 100% | 2017-01-20 | 2017-01-20 |  |  |  |  | 2017-01-20 | FY17Q2 | FY17Q2(A)
629 | Dobbins | Dobbins | Cornell | A1.08.03.01.03.02 |  | A1.08 - Controls | T-3 | Milestone: File Server Installation and Configuration Complete | 0 d | 100% | 2017-03-17 | 2017-03-17 |  |  |  |  | 2017-03-17 | FY17Q2 | FY17Q2(A)
165 | Dobbins | Dobbins | Cornell | A1.08.03.01.04.02 |  | A1.08 - Controls | T-2 | Milestone: All File Server - Testing Complete | 0 d | 0% | 2017-03-31 | 2017-03-31 |  |  |  |  | 2017-03-31 | FY17Q2
655 | Dobbins | Dobbins | Cornell | A1.08.09.01.01.16 |  | A1.08 - Controls | T-3 | Milestone: MLC Test - Controls EPICS Integration complete | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | 2017-04-03 | FY17Q3 | FY17Q3(A)
656 | Dobbins | Dobbins | Cornell | A1.08.09.01.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: MLC Test - Integrated pre-beam testing for all Controls System Complete | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | 2017-04-24 | FY17Q3 | FY17Q3(A)
657 | Dobbins | Dobbins | Cornell | A1.08.09.01.02.02.16 |  | A1.08 - Controls | T-3 | Milestone: Controls - MLC Test - Commissioning with Beam for all Controls System Complete | 0 d | 100% | 2017-05-05 | 2017-05-05 |  |  |  |  | 2017-05-05 | FY17Q3 | FY17Q3(A)
646 | Dobbins | Dobbins | Cornell | A1.08.07.04.03 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for MLC Test | 0 d | 100% | 2017-05-08 | 2017-05-08 |  |  |  |  | 2017-05-08 | FY17Q3 | FY17Q3(A)
653 | Dobbins | Dobbins | Cornell | A1.08.08.04.03 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System - Installation and Testing - Complete and ready for MLC Test | 0 d | 100% | 2017-05-08 | 2017-05-08 |  |  |  |  | 2017-05-08 | FY17Q3 | FY17Q3(A)
621 | Dobbins | Dobbins | Cornell | A1.08.02.01.01.03 |  | A1.08 - Controls | T-3 | Milestone: IOC Computer Design Complete | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 | FY17Q4
624 | Dobbins | Dobbins | Cornell | A1.08.02.02.01.03 |  | A1.08 - Controls | T-3 | Milestone: Operator Consoles Design Complete | 0 d | 100% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 | FY17Q4 | FY17Q4(A)
630 | Dobbins | Dobbins | Cornell | A1.08.04.01.01.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS Archiver Design Complete | 0 d | 100% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 | FY17Q4 | FY17Q4(A)
636 | Dobbins | Dobbins | Cornell | A1.08.04.03.01.03 |  | A1.08 - Controls | T-3 | Milestone: Configuration Database Design Complete | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 | FY17Q4
633 | Dobbins | Dobbins | Cornell | A1.08.04.02.01.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS Alarm Handler Design Complete | 0 d | 0% | 2017-07-07 | 2017-07-07 |  |  |  |  | 2017-07-07 | FY17Q4
162 | Dobbins | Dobbins | Cornell | A1.08.01.01.04 |  | A1.08 - Controls | T-2 | Milestone: Network Infrastructure Design Complete | 0 d | 0% | 2017-08-10 | 2017-08-10 |  |  |  |  | 2017-08-10 | FY17Q4
638 | Dobbins | Michnoff | BNL | A1.08.05.01.02 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - BPM - Sample hardware available for software development (Rob has the equipment and is bringing it back to CU for testing by the end of June) | 0 d | 100% | 2017-08-15 | 2017-08-15 |  |  |  |  | 2017-08-15 | FY17Q4 | FY17Q4(A)
645 | Dobbins | Dobbins | Cornell | A1.08.07.01.03 |  | A1.08 - Controls | T-3 | Milestone: Timing system - System design complete | 0 d | 0% | 2017-08-18 | 2017-08-18 |  |  |  |  | 2017-08-18 | FY17Q4
622 | Dobbins | Dobbins | Cornell | A1.08.02.01.02.03 |  | A1.08 - Controls | T-3 | Milestone: All IOC Computer Procurements Complete | 0 d | 0% | 2017-09-15 | 2017-09-15 |  |  |  |  | 2017-09-15 | FY17Q4
625 | Dobbins | Dobbins | Cornell | A1.08.02.02.02.03 |  | A1.08 - Controls | T-3 | Milestone: All Operator Consoles Procurements Complete | 0 d | 0% | 2017-09-15 | 2017-09-15 |  |  |  |  | 2017-09-15 | FY17Q4
631 | Dobbins | Dobbins | Cornell | A1.08.04.01.02.03 |  | A1.08 - Controls | T-3 | Milestone: All Archiver Computer Procurements Complete | 0 d | 100% | 2017-09-15 | 2017-09-15 |  |  |  |  | 2017-09-15 | FY17Q4 | FY17Q4(A)
634 | Dobbins | Dobbins | Cornell | A1.08.04.02.02.03 |  | A1.08 - Controls | T-3 | Milestone: All EPICS Alarm Handler Procurements Complete | 0 d | 0% | 2017-09-18 | 2017-09-18 |  |  |  |  | 2017-09-18 | FY17Q4
637 | Dobbins | Dobbins | Cornell | A1.08.04.03.02.02 |  | A1.08 - Controls | T-3 | Milestone: Configuration Database Installation and Configuration Complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 | FY17Q4
618 | Dobbins | Dobbins | Cornell | A1.08.01.02.05 |  | A1.08 - Controls | T-3 | Milestone: All Network Infrastructure Procurements Complete | 0 d | 0% | 2017-10-06 | 2017-10-06 |  |  |  |  | 2017-10-06 | FY18Q1
169 | Dobbins | Michnoff | BNL | A1.08.05.01.05 |  | A1.08 - Controls | T-2 | Milestone: EPICS device support - BPM - Testing Complete | 0 d | 0% | 2017-10-12 | 2017-10-12 |  |  |  |  | 2017-10-12 | FY18Q1
639 | Dobbins | Michnoff | BNL | A1.08.05.02.02 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - BAM - Sample hardware available for software development | 0 d | 0% | 2017-10-16 | 2017-10-16 |  |  |  |  | 2017-10-16 | FY18Q1
177 | Dobbins | Dobbins | Cornell | A1.08.07.02.03 |  | A1.08 - Controls | T-2 | Milestone: All Timing System Procurements Complete | 0 d | 0% | 2017-10-17 | 2017-10-17 |  |  |  |  | 2017-10-17 | FY18Q1
640 | Dobbins | Dobbins | Cornell | A1.08.05.03.01.01 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - Magnet power supplies - Hardware Identified/Specification Complete (Predecessors - All Power Supplies selected) | 0 d | 0% | 2017-10-26 | 2017-10-26 |  |  |  |  | 2017-10-26 | FY18Q1
619 | Dobbins | Dobbins | Cornell | A1.08.01.03.03 |  | A1.08 - Controls | T-3 | Milestone: Network Infrastructure Installation and Configuration Complete | 0 d | 0% | 2017-11-06 | 2017-11-06 |  |  |  |  | 2017-11-06 | FY18Q1
632 | Dobbins | Dobbins | Cornell | A1.08.04.01.03.02 |  | A1.08 - Controls | T-3 | Milestone: EPICS Archiver Installation and Configuration Complete | 0 d | 100% | 2017-11-10 | 2017-11-10 |  |  |  |  | 2017-11-10 | FY18Q1 | FY17Q4(A)
623 | Dobbins | Dobbins | Cornell | A1.08.02.01.03.02 |  | A1.08 - Controls | T-3 | Milestone: IOC Computer Installation and Configuration Complete | 0 d | 0% | 2017-11-14 | 2017-11-14 |  |  |  |  | 2017-11-14 | FY18Q1
626 | Dobbins | Dobbins | Cornell | A1.08.02.02.03.02 |  | A1.08 - Controls | T-3 | Milestone: Operator Consoles Installation and Configuration Complete | 0 d | 0% | 2017-11-14 | 2017-11-14 |  |  |  |  | 2017-11-14 | FY18Q1
641 | Dobbins | Dobbins | Cornell | A1.08.05.03.02.01 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - Magnet power supplies - Sample hardware available for software development (predecessor power supply specs - verify with Karl, successor is FF to at least 1 hardware available - redundant due to #1254?) | 0 d | 0% | 2017-11-20 | 2017-11-20 |  |  |  |  | 2017-11-20 | FY18Q1
166 | Dobbins | Dobbins | Cornell | A1.08.04.01.04.02 |  | A1.08 - Controls | T-2 | Milestone: All EPICS Archiver - Testing Complete | 0 d | 0% | 2017-11-28 | 2017-11-28 |  |  |  |  | 2017-11-28 | FY18Q1
164 | Dobbins | Dobbins | Cornell | A1.08.02.02.04.02 |  | A1.08 - Controls | T-2 | Milestone: All Operator Consoles - Testing Complete | 0 d | 0% | 2017-11-29 | 2017-11-29 |  |  |  |  | 2017-11-29 | FY18Q1
642 | Dobbins | Dobbins | Cornell | A1.08.05.03.02.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - Magnet power supplies - Software development complete | 0 d | 0% | 2017-11-29 | 2017-11-29 |  |  |  |  | 2017-11-29 | FY18Q1
163 | Dobbins | Dobbins | Cornell | A1.08.02.01.04.02 |  | A1.08 - Controls | T-2 | Milestone: All IOC Computers - Testing Complete | 0 d | 0% | 2017-11-30 | 2017-11-30 |  |  |  |  | 2017-11-30 | FY18Q1
168 | Dobbins | Dobbins | Cornell | A1.08.04.03.03.02 |  | A1.08 - Controls | T-2 | Milestone: Configuration Database - Testing Complete | 0 d | 0% | 2017-11-30 | 2017-11-30 |  |  |  |  | 2017-11-30 | FY18Q1
171 | Dobbins | Dobbins | Cornell | A1.08.05.03.03.02 |  | A1.08 - Controls | T-2 | Milestone: EPICS device support - Magnet power supplies - Testing Complete | 0 d | 0% | 2017-11-30 | 2017-11-30 |  |  |  |  | 2017-11-30 | FY18Q1
620 | Dobbins | Dobbins | Cornell | A1.08.01.04.02 |  | A1.08 - Controls | T-3 | Milestone: Network Infrastructure Complete | 0 d | 0% | 2017-12-07 | 2017-12-07 |  |  |  |  | 2017-12-07 | FY18Q1
635 | Dobbins | Dobbins | Cornell | A1.08.04.02.03.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS Alarm Handler Installation and Configuration Complete | 0 d | 0% | 2017-12-15 | 2017-12-15 |  |  |  |  | 2017-12-15 | FY18Q1
167 | Dobbins | Dobbins | Cornell | A1.08.04.02.04.02 |  | A1.08 - Controls | T-2 | Milestone: All EPICS Alarm Handler - Testing Complete | 0 d | 0% | 2018-01-03 | 2018-01-03 |  |  |  |  | 2018-01-03 | FY18Q2
647 | Dobbins | Dobbins | Cornell | A1.08.07.04.06 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for (FAT) Test | 0 d | 0% | 2018-01-23 | 2018-01-23 |  |  |  |  | 2018-01-23 | FY18Q2
650 | Dobbins | Dobbins | Cornell | A1.08.08.02.03 |  | A1.08 - Controls | T-3 | Milestone: All Machine Protection System Procurements Complete | 0 d | 0% | 2018-02-01 | 2018-02-01 |  |  |  |  | 2018-02-01 | FY18Q2
658 | Dobbins | Dobbins | Cornell | A1.08.09.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: Fractional Arc Test - Controls EPICS Integration complete | 0 d | 0% | 2018-02-07 | 2018-02-07 |  |  |  |  | 2018-02-07 | FY18Q2
170 | Dobbins | Michnoff | BNL | A1.08.05.02.05 |  | A1.08 - Controls | T-2 | Milestone: EPICS device support - BAM - Testing Complete | 0 d | 0% | 2018-02-14 | 2018-02-14 |  |  |  |  | 2018-02-14 | FY18Q2
180 | Dobbins | Dobbins | Cornell | A1.08.09.02.02.01.01.16 |  | A1.08 - Controls | T-2 | Milestone: Fractional Arc Test - Integrated pre-beam testing for all Controls System Complete | 0 d | 0% | 2018-02-22 | 2018-02-22 |  |  |  |  | 2018-02-22 | FY18Q2
651 | Dobbins | Dobbins | Cornell | A1.08.08.03.01.04 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System Assembly/Development and initial testing complete (FAT) | 0 d | 0% | 2018-02-23 | 2018-02-23 |  |  |  |  | 2018-02-23 | FY18Q2
659 | Dobbins | Dobbins | Cornell | A1.08.09.02.02.01.02.16 |  | A1.08 - Controls | T-3 | Milestone: Controls - Fractional Arc Test - Commissioning with Beam for all Controls System Complete | 0 d | 0% | 2018-03-08 | 2018-03-08 |  |  |  |  | 2018-03-08 | FY18Q2
178 | Dobbins | Dobbins | Cornell | A1.08.08.04.06 |  | A1.08 - Controls | T-2 | Milestone: Machine Protection System - Installation and Testing - complete and ready for (FAT) Test | 0 d | 0% | 2018-03-13 | 2018-03-13 |  |  |  |  | 2018-03-13 | FY18Q2
643 | Dobbins | Dobbins | Cornell | A1.08.06.01.01.02 |  | A1.08 - Controls | T-3 | Milestone: Orbit Correction - Requirements definition complete | 0 d | 0% | 2018-05-25 | 2018-05-25 |  |  |  |  | 2018-05-25 | FY18Q3
648 | Dobbins | Dobbins | Cornell | A1.08.07.04.09 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for SPBT | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 | FY18Q3
644 | Dobbins | Dobbins | Cornell | A1.08.06.01.01.04 |  | A1.08 - Controls | T-3 | Milestone: Orbit Correction - Software design complete | 0 d | 0% | 2018-06-25 | 2018-06-25 |  |  |  |  | 2018-06-25 | FY18Q3
649 | Dobbins | Dobbins | Cornell | A1.08.07.04.12 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for 4PBT | 0 d | 0% | 2018-07-24 | 2018-07-24 |  |  |  |  | 2018-07-24 | FY18Q4
172 | Dobbins | Dobbins | Cornell | A1.08.06.01.02.02 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - Software development complete | 0 d | 0% | 2018-08-21 | 2018-08-21 |  |  |  |  | 2018-08-21 | FY18Q4
173 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.01.03 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - SPBT hardware installation complete | 0 d | 0% | 2018-09-19 | 2018-09-19 |  |  |  |  | 2018-09-19 | FY18Q4
652 | Dobbins | Dobbins | Cornell | A1.08.08.03.02.04 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System Assembly/Development and initial testing complete (SPBT) | 0 d | 0% | 2019-01-18 | 2019-01-18 |  |  |  |  | 2019-01-18 | FY19Q2
179 | Dobbins | Dobbins | Cornell | A1.08.08.04.09 |  | A1.08 - Controls | T-2 | Milestone: Machine Protection System - Installation and Testing - complete and ready for SPBT | 0 d | 0% | 2019-02-13 | 2019-02-13 |  |  |  |  | 2019-02-13 | FY19Q2
660 | Dobbins | Dobbins | Cornell | A1.08.09.03.01.16 |  | A1.08 - Controls | T-3 | Milestone: SPBT - Controls EPICS Integration complete | 0 d | 0% | 2019-04-03 | 2019-04-03 |  |  |  |  | 2019-04-03 | FY19Q3
661 | Dobbins | Dobbins | Cornell | A1.08.09.03.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: SPBT - Integrated pre-beam testing for all Controls System Complete | 0 d | 0% | 2019-05-01 | 2019-05-01 |  |  |  |  | 2019-05-01 | FY19Q3
174 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.01.06 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - SPBT - commissioning with beam complete | 0 d | 0% | 2019-05-08 | 2019-05-08 |  |  |  |  | 2019-05-08 | FY19Q3
181 | Dobbins | Dobbins | Cornell | A1.08.09.03.02.02.16 |  | A1.08 - Controls | T-2 | Milestone: Controls - SPBT - Commissioning with Beam for all Controls System Complete | 0 d | 0% | 2019-05-08 | 2019-05-08 |  |  |  |  | 2019-05-08 | FY19Q3
662 | Dobbins | Dobbins | Cornell | A1.08.09.04.01.16 |  | A1.08 - Controls | T-3 | Milestone: 4PBT - Controls EPICS Integration complete | 0 d | 0% | 2019-08-26 | 2019-08-26 |  |  |  |  | 2019-08-26 | FY19Q4
175 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.02.01 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - 4PBT hardware installation complete | 0 d | 0% | 2019-10-07 | 2019-10-07 |  |  |  |  | 2019-10-07 | FY20Q1
663 | Dobbins | Dobbins | Cornell | A1.08.09.04.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: 4PBT - Integrated pre-beam testing for all Controls System Complete | 0 d | 0% | 2019-11-14 | 2019-11-14 |  |  |  |  | 2019-11-14 | FY20Q1
654 | Dobbins | Dobbins | Cornell | A1.08.08.04.12 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System - Installation and Testing - complete and ready for 4PBT | 0 d | 0% | 2019-11-18 | 2019-11-18 |  |  |  |  | 2019-11-18 | FY20Q1
182 | Dobbins | Dobbins | Cornell | A1.08.09.04.02.02.16 |  | A1.08 - Controls | T-2 | Milestone: Controls - 4PBT - Commissioning with Beam for all Controls System Complete | 0 d | 0% | 2019-12-02 | 2019-12-02 |  |  |  |  | 2019-12-02 | FY20Q1
176 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.02.04 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - 4PBT - Commissioning with beam complete | 0 d | 0% | 2019-12-20 | 2019-12-20 |  |  |  |  | 2019-12-20 | FY20Q1
186 | Dobbins | Dobbins | Cornell | A1.09.05.03.01 |  | A1.09 - Instrumentation | T-2 | Milestone: BPM Assembly/Development - Pick-up Complete and ready for Final testing | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 | FY17Q1 | [6 empty] | Incorrect dates - kwj
667 | Dobbins | Dobbins | Cornell | A1.09.02.03.01 |  | A1.09 - Instrumentation | T-3 | Milestone: Existing BAMs tested and available for install | 0 d | 100% | 2017-04-28 | 2017-04-28 |  |  |  |  | 2017-04-28 | FY17Q3 | FY17Q3(A)
683 | Dobbins | Dobbins | Cornell | A1.09.05.07.01.01.08 |  | A1.09 - Instrumentation | T-3 | Milestone: MLC Test - Instrumentation System Final Installation Complete | 0 d | 100% | 2017-05-11 | 2017-05-11 |  |  |  |  | 2017-05-11 | FY17Q3 | FY17Q3(A)
684 | Dobbins | Dobbins | Cornell | A1.09.05.07.01.02.02 |  | A1.09 - Instrumentation | T-3 | Milestone: MLC Test - Instrumentation System Testing Complete | 0 d | 100% | 2017-05-12 | 2017-05-12 |  |  |  |  | 2017-05-12 | FY17Q3 | FY17Q3(A)
685 | Dobbins | Dobbins | Cornell | A1.09.05.07.01.03.02 |  | A1.09 - Instrumentation | T-3 | Milestone: MLC Test - Instrumentation Commissioning with Beam Complete | 0 d | 100% | 2017-05-15 | 2017-05-15 |  |  |  |  | 2017-05-15 | FY17Q3 | FY17Q3(A)
672 | Dobbins | Dobbins | Cornell | A1.09.05.01.01.06 |  | A1.09 - Instrumentation | T-3 | Milestone: All System Specifications Finalized/Complete | 0 d | 100% | 2017-08-01 | 2017-08-01 |  |  |  |  | 2017-08-01 | FY17Q4 | FY17Q4(A)
668 | Dobbins | Dobbins | Cornell | A1.09.03.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: BCM Design Complete | 0 d | 0% | 2017-08-10 | 2017-08-10 |  |  |  |  | 2017-08-10 | FY17Q4
680 | Dobbins | Dobbins | Cornell | A1.09.05.06.01.02 |  | A1.09 - Instrumentation | T-3 | Milestone: Develop Beam stop beam-pipe hardware design complete (Vacuum section) | 0 d | 0% | 2017-08-15 | 2017-08-15 |  |  |  |  | 2017-08-15 | FY17Q4
681 | Dobbins | Dobbins | Cornell | A1.09.05.06.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: Beam Stop Design Complete | 0 d | 0% | 2017-08-15 | 2017-08-15 |  |  |  |  | 2017-08-15 | FY17Q4
674 | Dobbins | Dobbins | Cornell | A1.09.05.01.03.08 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM Clock Distribution Design Complete (FAT) | 0 d | 0% | 2017-09-13 | 2017-09-13 |  |  |  |  | 2017-09-13 | FY17Q4
679 | Dobbins | Dobbins | Cornell | A1.09.05.05.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: View Screen Design Complete | 0 d | 0% | 2017-09-14 | 2017-09-14 |  |  |  |  | 2017-09-14 | FY17Q4
664 | Dobbins | Dobbins | Cornell | A1.09.02.01.07 |  | A1.09 - Instrumentation | T-3 | Milestone: BAM Design Complete | 0 d | 0% | 2017-09-15 | 2017-09-15 |  |  |  |  | 2017-09-15 | FY17Q4
670 | Dobbins | Dobbins | Cornell | A1.09.04.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: Beam Loss Monitor Design Complete | 0 d | 0% | 2017-09-22 | 2017-09-22 |  |  |  |  | 2017-09-22 | FY17Q4
682 | Dobbins | Dobbins | Cornell | A1.09.05.06.02.05 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Stop Procurements Complete | 0 d | 0% | 2017-12-05 | 2017-12-05 |  |  |  |  | 2017-12-05 | FY18Q1
665 | Dobbins | Dobbins | Cornell | A1.09.02.02.06 |  | A1.09 - Instrumentation | T-3 | Milestone: 1st Article - V301 Digital Boards Received (Qty: xx [BNL]) (5 mths after order placement??) | 0 d | 0% | 2018-01-24 | 2018-01-24 |  |  |  |  | 2018-01-24 | FY18Q2
671 | Dobbins | Dobbins | Cornell | A1.09.04.02.04 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Loss Monitor Procurements Complete | 0 d | 0% | 2018-01-24 | 2018-01-24 |  |  |  |  | 2018-01-24 | FY18Q2
189 | Dobbins | Dobbins | Cornell | A1.09.05.06.03.02 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Stops Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-02-05 | 2018-02-05 |  |  |  |  | 2018-02-05 | FY18Q2
190 | Dobbins | Dobbins | Cornell | A1.09.05.07.02.01.07 |  | A1.09 - Instrumentation | T-2 | Milestone: FAT - Instrumentation System Testing Complete | 0 d | 0% | 2018-02-20 | 2018-02-20 |  |  |  |  | 2018-02-20 | FY18Q2
686 | Dobbins | Dobbins | Cornell | A1.09.05.07.02.02.03 |  | A1.09 - Instrumentation | T-3 | Milestone: FAT - Instrumentation Commissioning with Beam Complete | 0 d | 0% | 2018-03-27 | 2018-03-27 |  |  |  |  | 2018-03-27 | FY18Q2
188 | Dobbins | Dobbins | Cornell | A1.09.05.05.02.05 |  | A1.09 - Instrumentation | T-2 | Milestone: All View Screen Procurements Complete | 0 d | 0% | 2018-04-04 | 2018-04-04 |  |  |  |  | 2018-04-04 | FY18Q3
183 | Dobbins | Dobbins | Cornell | A1.09.02.03.07 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Arrival Monitors Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-04-12 | 2018-04-12 |  |  |  |  | 2018-04-12 | FY18Q3
673 | Dobbins | Dobbins | Cornell | A1.09.05.01.03.03 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM - DAQ Board Design Complete | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 | FY18Q3
675 | Dobbins | Dobbins | Cornell | A1.09.05.01.03.09 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM Clock Distribution Design Complete (SPBT) | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 | FY18Q3
666 | Dobbins | Dobbins | Cornell | A1.09.02.02.08 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Arrival Monitor Procurements Complete | 0 d | 0% | 2018-06-15 | 2018-06-15 |  |  |  |  | 2018-06-15 | FY18Q3
669 | Dobbins | Dobbins | Cornell | A1.09.03.02.05 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Current Monitor Procurements Complete | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 | FY18Q3
187 | Dobbins | Michnoff | BNL | A1.09.05.03.02.03 |  | A1.09 - Instrumentation | T-2 | Milestone: BPM Assembly/Development - DAQ Electronics Complete and ready for Final testing | 0 d | 0% | 2018-08-21 | 2018-08-21 |  |  |  |  | 2018-08-21 | FY18Q4
185 | Dobbins | Dobbins | Cornell | A1.09.04.03.04 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Loss Monitors Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-08-27 | 2018-08-27 |  |  |  |  | 2018-08-27 | FY18Q4
677 | Dobbins | Dobbins | Cornell | A1.09.05.02.02.05 |  | A1.09 - Instrumentation | T-3 | Milestone: All BPM Clock Distribution Procurements Complete | 0 d | 0% | 2018-10-03 | 2018-10-03 |  |  |  |  | 2018-10-03 | FY19Q1
678 | Dobbins | Dobbins | Cornell | A1.09.05.03.03.04 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM Assembly/Development - BPM Clock Complete and ready for Final testing | 0 d | 0% | 2018-10-03 | 2018-10-03 |  |  |  |  | 2018-10-03 | FY19Q1
184 | Dobbins | Dobbins | Cornell | A1.09.03.03.04 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Current Monitors Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-12-17 | 2018-12-17 |  |  |  |  | 2018-12-17 | FY19Q1
676 | Dobbins | Dobbins | Cornell | A1.09.05.02.01.06 |  | A1.09 - Instrumentation | T-3 | Milestone: All DAQ Electronics Procurements Complete | 0 d | 0% | 2019-04-02 | 2019-04-02 |  |  |  |  | 2019-04-02 | FY19Q3
191 | Dobbins | Dobbins | Cornell | A1.09.05.07.03.01.08 |  | A1.09 - Instrumentation | T-2 | Milestone: SPBT - Instrumentation System Testing Complete | 0 d | 0% | 2019-07-10 | 2019-07-10 |  |  |  |  | 2019-07-10 | FY19Q4
687 | Dobbins | Dobbins | Cornell | A1.09.05.07.03.02.03 |  | A1.09 - Instrumentation | T-3 | Milestone: SPBT - Instrumentation Commissioning with Beam Complete | 0 d | 0% | 2019-09-05 | 2019-09-05 |  |  |  |  | 2019-09-05 | FY19Q4
192 | Dobbins | Dobbins | Cornell | A1.09.05.07.04.01.07 |  | A1.09 - Instrumentation | T-2 | Milestone: 4PBT - Instrumentation System Testing Complete | 0 d | 0% | 2020-01-21 | 2020-01-21 |  |  |  |  | 2020-01-21 | FY20Q2
688 | Dobbins | Dobbins | Cornell | A1.09.05.07.04.02.03 |  | A1.09 - Instrumentation | T-3 | Milestone: 4PBT - Instrumentation Commissioning with Beam Complete | 0 d | 0% | 2020-04-29 | 2020-04-29 |  |  |  |  | 2020-04-29 | FY20Q2
690 | Li | Li | Cornell | A1.10.04.03.02.04 |  | A1.10 - Vacuum Systems | T-3 | Milestone: BPM buttons machining complete and ready for delivery to vendor | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 | FY17Q1
692 | Li | Li | Cornell | A1.10.05.04.01 |  | A1.10 - Vacuum Systems | T-3 | Milestone: BPM buttons machining complete and ready for delivery to vendor (Change) | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 | FY17Q1
691 | Li | Li | Cornell | A1.10.05.01.05 |  | A1.10 - Vacuum Systems | T-3 | Milestone: Vacuum FFAG Straight System - All Designs Complete | 0 d | 0% | 2017-05-09 | 2017-05-09 |  |  |  |  | 2017-05-09 | FY17Q3
194 | Li | Li | Cornell | A1.10.04.01.05 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc System - All Designs Complete | 0 d | 0% | 2017-08-15 | 2017-08-15 |  |  |  |  | 2017-08-15 | FY17Q4
196 | Li | Li | Cornell | A1.10.04.03.09 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc Assemblies Complete for FAT Test | 0 d | 0% | 2018-04-03 | 2018-04-03 |  |  |  |  | 2018-04-03 | FY18Q3
195 | Li | Li | Cornell | A1.10.04.02.06 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc System - All Procurements complete | 0 d | 0% | 2018-05-08 | 2018-05-08 |  |  |  |  | 2018-05-08 | FY18Q3
197 | Li | Li | Cornell | A1.10.04.03.10 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc Assemblies Complete for SPBT/Remainder | 0 d | 0% | 2018-05-11 | 2018-05-11 |  |  |  |  | 2018-05-11 | FY18Q3
689 | Li | Li | Cornell | A1.10.01.03.04 |  | A1.10 - Vacuum Systems | T-3 | Milestone: Global Vacuum System - All assembly/support complete | 0 d | 0% | 2018-05-25 | 2018-05-25 |  |  |  |  | 2018-05-25 | FY18Q3
193 | Li | Li | Cornell | A1.10.01.02.06 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Global Vacuum System - Procurements complete | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 | FY18Q3
693 | Gallagher | Gallagher | Cornell | A1.11.01.01.02 |  | A1.11 - System Integration | T-3 | CBETA ALL DWGS Start | 0 d | 100% | 2016-06-01 | 2016-06-01 |  |  |  |  | 2016-06-01 | FY17Q1 | FY17Q1(A)
694 | Gallagher | Gallagher | Cornell | A1.11.01.01.04 |  | A1.11 - System Integration | T-3 | Milestone: Gun and ICM operational (Sector 00) (10/3/2016) | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 | FY17Q1 | FY17Q1(A)
698 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Final Design/Layout for East RF System Complete | 0 d | 100% | 2017-03-31 | 2017-03-31 |  |  |  |  | 2017-03-31 | FY17Q2 | FY17Q2(A)
695 | Gallagher | Gallagher | Cornell | A1.11.01.01.05 |  | A1.11 - System Integration | T-3 | Milestone: Vacuum Lab ready for Removal activities | 0 d | 100% | 2017-04-01 | 2017-04-01 |  |  |  |  | 2017-04-01 | FY17Q3 | FY17Q3(A)
705 | Gallagher | Gallagher | Cornell | A1.11.01.04.05.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Laser Room Design Complete | 0 d | 100% | 2017-04-11 | 2017-04-11 |  |  |  |  | 2017-04-11 | FY17Q3 | FY17Q3(A)
706 | Gallagher | Gallagher | Cornell | A1.11.01.04.05.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All Laser Room Procurements Complete | 0 d | 0% | 2017-05-23 | 2017-05-23 |  |  |  |  | 2017-05-23 | FY17Q3
202 | Gallagher | Gallagher | Cornell | A1.11.01.03.02.01.09 |  | A1.11 - System Integration | T-2 | Milestone: L0E Vacuum Lab Removal Complete | 0 d | 100% | 2017-06-08 | 2017-06-08 |  |  |  |  | 2017-06-08 | FY17Q3 | FY17Q3(A)
696 | Gallagher | Gallagher | Cornell | A1.11.01.01.06 |  | A1.11 - System Integration | T-3 | Milestone: Water Shut off (by June 30 2017) - 6 weeks | 0 d | 100% | 2017-06-30 | 2017-06-30 |  |  |  |  | 2017-06-30 | FY17Q3 | FY17Q3(A)
699 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All East RF System Relocation Procurements Complete | 0 d | 0% | 2017-08-08 | 2017-08-08 |  |  |  |  | 2017-08-08 | FY17Q4
199 | Gallagher | Gallagher | Cornell | A1.11.01.01.07 |  | A1.11 - System Integration | T-2 | Milestone: Water Turned On - L0E Work continued | 0 d | 0% | 2017-08-11 | 2017-08-11 |  |  |  |  | 2017-08-11 | FY17Q4
721 | Gallagher | Gallagher | Cornell | A1.11.02.02.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 01-LA: North MLC and diagnostics Beam line Ready for System Integration | 0 d | 100% | 2017-08-11 | 2017-08-11 |  |  |  |  | 2017-08-11 | FY17Q4 | FY17Q4(A)
707 | Gallagher | Gallagher | Cornell | A1.11.01.04.05.03.02 |  | A1.11 - System Integration | T-3 | Milestone: Laser Room Fabrication Complete and Table Ready for Set-Up | 0 d | 0% | 2017-08-17 | 2017-08-17 |  |  |  |  | 2017-08-17 | FY17Q4
210 | Gallagher | Gallagher | Cornell | A1.11.02.02.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 01-LA: North MLC and diagnostics Beam line -System Integration Complete | 0 d | 100% | 2017-08-25 | 2017-08-25 |  |  |  |  | 2017-08-25 | FY17Q4 | FY17Q4(A)
200 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.03.01 |  | A1.11 - System Integration | T-2 | Milestone: L0 ERF Testing Complete and ready for L0E ERF Move to L0 | 0 d | 0% | 2017-09-25 | 2017-09-25 |  |  |  |  | 2017-09-25 | FY17Q4
701 | Gallagher | Gallagher | Cornell | A1.11.01.03.03.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All CESR-85F Cooling System Components Procurements Received | 0 d | 0% | 2017-10-27 | 2017-10-27 |  |  |  |  | 2017-10-27 | FY18Q1
700 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.03.04 |  | A1.11 - System Integration | T-3 | Milestone: East RF Systems Install Complete | 0 d | 0% | 2017-11-07 | 2017-11-07 |  |  |  |  | 2017-11-07 | FY18Q1
697 | Gallagher | Gallagher | Cornell | A1.11.01.01.08 |  | A1.11 - System Integration | T-3 | Milestone: Start L0E construction (East-RF move to L0 Pit complete/operational) 12/4/17? | 0 d | 0% | 2017-12-04 | 2017-12-04 |  |  |  |  | 2017-12-04 | FY18Q1
205 | Gallagher | Gallagher | Cornell | A1.11.01.04.02.01 |  | A1.11 - System Integration | T-2 | Milestone: Rack specifications finalized/designed (by 12/31/17 for entire system - SPBT/4PBT) - | 0 d | 0% | 2018-01-09 | 2018-01-09 |  |  |  |  | 2018-01-09 | FY18Q2
714 | Gallagher | Gallagher | Cornell | A1.11.01.04.10.04 |  | A1.11 - System Integration | T-3 | Milestone: Compressed Air System Installation Complete | 0 d | 0% | 2018-01-10 | 2018-01-10 |  |  |  |  | 2018-01-10 | FY18Q2
201 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.04.04 |  | A1.11 - System Integration | T-2 | Milestone: East RF System Relocation Complete | 0 d | 0% | 2018-01-19 | 2018-01-19 |  |  |  |  | 2018-01-19 | FY18Q2
712 | Gallagher | Gallagher | Cornell | A1.11.01.04.09.01.05 |  | A1.11 - System Integration | T-3 | Milestone: Electrical System Design Complete | 0 d | 0% | 2018-02-08 | 2018-02-08 |  |  |  |  | 2018-02-08 | FY18Q2
715 | Gallagher | Gallagher | Cornell | A1.11.01.04.11.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Design of HVAC Upgrade Complete | 0 d | 0% | 2018-02-08 | 2018-02-08 |  |  |  |  | 2018-02-08 | FY18Q2
708 | Gallagher | Gallagher | Cornell | A1.11.01.04.06.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All Mezzanine Procurements Complete | 0 d | 0% | 2018-02-23 | 2018-02-23 |  |  |  |  | 2018-02-23 | FY18Q2
207 | Gallagher | Gallagher | Cornell | A1.11.01.04.07.03.03 |  | A1.11 - System Integration | T-2 | Milestone: East Wall Modifications (Penetrations) Complete | 0 d | 0% | 2018-03-09 | 2018-03-09 |  |  |  |  | 2018-03-09 | FY18Q2
702 | Gallagher | Gallagher | Cornell | A1.11.01.04.03.01.03 |  | A1.11 - System Integration | T-3 | Milestone: All Survey & Alignment Procurements Complete | 0 d | 0% | 2018-04-06 | 2018-04-06 |  |  |  |  | 2018-04-06 | FY18Q3
710 | Gallagher | Gallagher | Cornell | A1.11.01.04.08.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Water Cooling System Design Complete | 0 d | 0% | 2018-04-06 | 2018-04-06 |  |  |  |  | 2018-04-06 | FY18Q3
717 | Gallagher | Gallagher | Cornell | A1.11.01.04.12.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Network and IT Requirements Complete | 0 d | 0% | 2018-04-06 | 2018-04-06 |  |  |  |  | 2018-04-06 | FY18Q3
713 | Gallagher | Gallagher | Cornell | A1.11.01.04.09.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All Electrical System Procurements Complete | 0 d | 0% | 2018-05-04 | 2018-05-04 |  |  |  |  | 2018-05-04 | FY18Q3
718 | Gallagher | Gallagher | Cornell | A1.11.01.04.12.02.02 |  | A1.11 - System Integration | T-3 | Milestone: All Network and IT Support Procurements Complete | 0 d | 0% | 2018-05-04 | 2018-05-04 |  |  |  |  | 2018-05-04 | FY18Q3
709 | Gallagher | Gallagher | Cornell | A1.11.01.04.06.03.02 |  | A1.11 - System Integration | T-3 | Milestone: Mezzanine Installation Complete | 0 d | 0% | 2018-05-18 | 2018-05-18 |  |  |  |  | 2018-05-18 | FY18Q3
716 | Gallagher | Gallagher | Cornell | A1.11.01.04.11.04 |  | A1.11 - System Integration | T-3 | Milestone: Environmental Controls Installation Complete | 0 d | 0% | 2018-06-04 | 2018-06-04 |  |  |  |  | 2018-06-04 | FY18Q3
726 | Gallagher | Gallagher | Cornell | A1.11.02.04.01.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (FAT): East Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 | FY18Q3
728 | Gallagher | Gallagher | Cornell | A1.11.02.04.02.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (SPBT-4PBT): East Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 | FY18Q3
730 | Gallagher | Gallagher | Cornell | A1.11.02.05.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 04-TA: South Southeast arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 | FY18Q3
732 | Gallagher | Gallagher | Cornell | A1.11.02.06.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 05-ZA: Southeast straight Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 | FY18Q3
734 | Gallagher | Gallagher | Cornell | A1.11.02.07.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 06-ZB: Southwest straight Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 | FY18Q3
736 | Gallagher | Gallagher | Cornell | A1.11.02.08.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 07-TB: Southwest Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 | FY18Q3
738 | Gallagher | Gallagher | Cornell | A1.11.02.09.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 08-FB: West Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 | FY18Q3
739 | Gallagher | Gallagher | Cornell | A1.11.02.10.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 09-RX: Northwest Splitter Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 | FY18Q3
740 | Gallagher | Gallagher | Cornell | A1.11.02.11.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 10-BS: Beam stop Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 | FY18Q3
198 | Gallagher | Gallagher | Cornell | A1.11.01.01.01.06 |  | A1.11 - System Integration | T-2 | Milestone: CESR 2018 CHESS-U Commissioning/Startup | 0 d | 0% | 2018-06-27 | 2018-06-27 |  |  |  |  | 2018-06-27 | FY18Q3
722 | Gallagher | Gallagher | Cornell | A1.11.02.03.01.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 02-SX (FAT) Northeast Splitter Ready for System Integration | 0 d | 0% | 2018-06-29 | 2018-06-29 |  |  |  |  | 2018-06-29 | FY18Q3
703 | Gallagher | Gallagher | Cornell | A1.11.01.04.03.02.03 |  | A1.11 - System Integration | T-3 | Milestone: Survey and alignment - Reference system Complete | 0 d | 0% | 2018-07-02 | 2018-07-02 |  |  |  |  | 2018-07-02 | FY18Q4
724 | Gallagher | Gallagher | Cornell | A1.11.02.03.03.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 02-SX (4PBT): Northeast Splitter Ready for System Integration | 0 d | 0% | 2018-07-02 | 2018-07-02 |  |  |  |  | 2018-07-02 | FY18Q4
220 | Gallagher | Gallagher | Cornell | A1.11.02.09.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 08-FB: West Arc -System Integration Complete | 0 d | 0% | 2018-07-09 | 2018-07-09 |  |  |  |  | 2018-07-09 | FY18Q4
211 | Gallagher | Gallagher | Cornell | A1.11.02.03.01.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 02-SX (FAT) Northeast Splitter - System Integration Complete | 0 d | 0% | 2018-07-16 | 2018-07-16 |  |  |  |  | 2018-07-16 | FY18Q4
221 | Gallagher | Gallagher | Cornell | A1.11.02.10.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 09-RX: Northwest Splitter -System Integration Complete | 0 d | 0% | 2018-07-23 | 2018-07-23 |  |  |  |  | 2018-07-23 | FY18Q4
741 | Gallagher | Gallagher | Cornell | A1.11.02.11.03.06 |  | A1.11 - System Integration | T-3 | Milestone: Sector 10-BS: Beam stop - Installation Complete | 0 d | 0% | 2018-07-23 | 2018-07-23 |  |  |  |  | 2018-07-23 | FY18Q4
213 | Gallagher | Gallagher | Cornell | A1.11.02.03.03.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 02-SX (4PBT): Northeast Splitter -System Integration Complete | 0 d | 0% | 2018-07-31 | 2018-07-31 |  |  |  |  | 2018-07-31 | FY18Q4
719 | Gallagher | Gallagher | Cornell | A1.11.01.04.12.03.02 |  | A1.11 - System Integration | T-3 | Milestone: Network and IT Support items installed | 0 d | 0% | 2018-07-31 | 2018-07-31 |  |  |  |  | 2018-07-31 | FY18Q4
216 | Gallagher | Gallagher | Cornell | A1.11.02.05.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 04-TA: South Southeast arc -System Integration Complete | 0 d | 0% | 2018-08-10 | 2018-08-10 |  |  |  |  | 2018-08-10 | FY18Q4
723 | Gallagher | Gallagher | Cornell | A1.11.02.03.02.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 02-SX (SPBT) - Northeast Splitter Ready for System Integration | 0 d | 0% | 2018-08-17 | 2018-08-17 |  |  |  |  | 2018-08-17 | FY18Q4
222 | Gallagher | Gallagher | Cornell | A1.11.02.11.04.07 |  | A1.11 - System Integration | T-2 | Milestone: Sector 10-BS: Beam stop - System Integration Complete | 0 d | 0% | 2018-08-20 | 2018-08-20 |  |  |  |  | 2018-08-20 | FY18Q4
203 | Gallagher | Gallagher | Cornell | A1.11.01.03.03.03.03 |  | A1.11 - System Integration | T-2 | Milestone: CESR-85F Cooling System Relocation Complete | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 | FY18Q4
725 | Gallagher | Gallagher | Cornell | A1.11.02.04.01.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (FAT): East arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 | FY18Q4
727 | Gallagher | Gallagher | Cornell | A1.11.02.04.02.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (SPBT-4PBT): East arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 | FY18Q4
729 | Gallagher | Gallagher | Cornell | A1.11.02.05.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 04-TA - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 | FY18Q4
731 | Gallagher | Gallagher | Cornell | A1.11.02.06.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 05-ZA - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 | FY18Q4
733 | Gallagher | Gallagher | Cornell | A1.11.02.07.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 06-ZB - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 | FY18Q4
735 | Gallagher | Gallagher | Cornell | A1.11.02.08.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 07-TB - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 | FY18Q4
737 | Gallagher | Gallagher | Cornell | A1.11.02.09.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 07-TB - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 | FY18Q4
212 | Gallagher | Gallagher | Cornell | A1.11.02.03.02.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 02-SX (SPBT) - Northeast Splitter - System Integration Complete | 0 d | 0% | 2018-09-17 | 2018-09-17 |  |  |  |  | 2018-09-17 | FY18Q4
214 | Gallagher | Gallagher | Cornell | A1.11.02.04.01.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 03-FA (FAT): East Arc -System Integration Complete | 0 d | 0% | 2018-09-18 | 2018-09-18 |  |  |  |  | 2018-09-18 | FY18Q4
215 | Gallagher | Gallagher | Cornell | A1.11.02.04.02.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 03-FA (SPBT-4PBT): East Arc -System Integration Complete | 0 d | 0% | 2018-09-18 | 2018-09-18 |  |  |  |  | 2018-09-18 | FY18Q4
217 | Gallagher | Gallagher | Cornell | A1.11.02.06.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 05-ZA: Southeast straight -System Integration Complete | 0 d | 0% | 2018-10-09 | 2018-10-09 |  |  |  |  | 2018-10-09 | FY19Q1
204 | Gallagher | Gallagher | Cornell | A1.11.01.04.01.07 |  | A1.11 - System Integration | T-2 | Milestone: CBETA Global Layout Plans Complete | 0 d | 0% | 2018-10-18 | 2018-10-18 |  |  |  |  | 2018-10-18 | FY19Q1
208 | Gallagher | Gallagher | Cornell | A1.11.01.04.09.03.02 |  | A1.11 - System Integration | T-2 | Milestone: Electrical System Installation Complete | 0 d | 0% | 2018-10-25 | 2018-10-25 |  |  |  |  | 2018-10-25 | FY19Q1
218 | Gallagher | Gallagher | Cornell | A1.11.02.07.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 06-ZB: Southwest straight -System Integration Complete | 0 d | 0% | 2018-12-07 | 2018-12-07 |  |  |  |  | 2018-12-07 | FY19Q1
209 | Gallagher | Gallagher | Cornell | A1.11.02.01.01 |  | A1.11 - System Integration | T-2 | Milestone: All BNL Magnets and Hardware Received for Installation in L0E | 0 d | 0% | 2019-01-24 | 2019-01-24 |  |  |  |  | 2019-01-24 | FY19Q2
219 | Gallagher | Gallagher | Cornell | A1.11.02.08.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 07-TB: Southwest Arc -System Integration Complete | 0 d | 0% | 2019-02-07 | 2019-02-07 |  |  |  |  | 2019-02-07 | FY19Q2
704 | Gallagher | Gallagher | Cornell | A1.11.01.04.04.01.03 |  | A1.11 - System Integration | T-3 | Milestone: All New Shielding Wall & Blocks Procurements Complete | 0 d | 0% | 2019-04-16 | 2019-04-16 |  |  |  |  | 2019-04-16 | FY19Q3
711 | Gallagher | Gallagher | Cornell | A1.11.01.04.08.03.04 |  | A1.11 - System Integration | T-3 | Milestone: Water Cooling System Installation Complete | 0 d | 0% | 2019-04-23 | 2019-04-23 |  |  |  |  | 2019-04-23 | FY19Q3
206 | Gallagher | Gallagher | Cornell | A1.11.01.04.04.02.03 |  | A1.11 - System Integration | T-2 | Milestone: Shielding Installation Complete | 0 d | 0% | 2019-10-04 | 2019-10-04 |  |  |  |  | 2019-10-04 | FY20Q1
720 | Gallagher | Gallagher | Cornell | A1.11.02.01.03 |  | A1.11 - System Integration | T-3 | Milestone: All Sectors - System Integration Complete | 0 d | 0% | 2019-10-07 | 2019-10-07 |  |  |  |  | 2019-10-07 | FY20Q1
223 | Bartnik | Bartnik | Cornell | A1.12.01.03 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Gun, ICM, Beam Stop - Commissioning Complete | 0 d | 0% | 2017-01-25 | 2017-01-25 |  |  |  |  | 2017-01-25 | FY17Q2
224 | Bartnik | Bartnik | Cornell | A1.12.02.03 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Diagnostics Line - Commissioning Complete | 0 d | 0% | 2017-02-27 | 2017-02-27 |  |  |  |  | 2017-02-27 | FY17Q2
225 | Bartnik | Bartnik | Cornell | A1.12.03.06 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): MLC - Commissioning Complete | 0 d | 0% | 2017-06-15 | 2017-06-15 |  |  |  |  | 2017-06-15 | FY17Q3
226 | Bartnik | Bartnik | Cornell | A1.12.04.05 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Fractional Arc Test - Commissioning Complete | 0 d | 0% | 2018-07-27 | 2018-07-27 |  |  |  |  | 2018-07-27 | FY18Q4
227 | Bartnik | Bartnik | Cornell | A1.12.05.07 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Single Pass Energy Scan - Commissioning Complete | 0 d | 0% | 2019-09-19 | 2019-09-19 |  |  |  |  | 2019-09-19 | FY19Q4
228 | Bartnik | Bartnik | Cornell | A1.12.06.05 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Single Pass Energy Recovery - Commissioning Complete | 0 d | 0% | 2020-02-04 | 2020-02-04 |  |  |  |  | 2020-02-04 | FY20Q2
229 | Bartnik | Bartnik | Cornell | A1.12.07.05 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Four Pass Energy Recovery - Commissioning Complete | 0 d | 0% | 2020-05-06 | 2020-05-06 |  |  |  |  | 2020-05-06 | FY20Q2
742 | Widger | Ray | Cornell | A1.13.02.01.02.03 |  | A1.13 - Safety | T-3 | Milestone: (MLC) Safety Procurements Received | 0 d | 100% | 2017-03-13 | 2017-03-13 |  |  |  |  | 2017-03-13 | FY17Q2 | FY17Q2(A)
750 | Widger | Widger | Cornell | A1.13.03.01.01.03 |  | A1.13 - Safety | T-3 | Milestone: (MLC) - Design radiation monitor system Complete/Approved | 0 d | 100% | 2017-03-23 | 2017-03-23 |  |  |  |  | 2017-03-23 | FY17Q2 | FY17Q2(A)
751 | Widger | Ray | Cornell | A1.13.03.01.02.03 |  | A1.13 - Safety | T-3 | Milestone: (MLC) Radiation Monitoring Procurements Received | 0 d | 100% | 2017-04-06 | 2017-04-06 |  |  |  |  | 2017-04-06 | FY17Q3 | FY17Q3(A)
743 | Widger | Ray | Cornell | A1.13.02.01.03.07 |  | A1.13 - Safety | T-3 | Milestone: Safety process complete for MLC Test (5/9) | 0 d | 100% | 2017-04-10 | 2017-04-10 |  |  |  |  | 2017-04-10 | FY17Q3 | FY17Q3(A)
231 | Widger | Heltsely | Cornell | A1.13.01.02.05 |  | A1.13 - Safety | T-2 | Milestone: Safety/x-Ray Permit for MLC Beam through Merger Test Approved | 0 d | 100% | 2017-04-20 | 2017-04-20 |  |  |  |  | 2017-04-20 | FY17Q3 | FY17Q3(A)
752 | Widger | Widger | Cornell | A1.13.03.01.03.07 |  | A1.13 - Safety | T-3 | Milestone: Radiation Monitor Safety process for MLC Relocate Complete (Link to Commissioning of beam directly) | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | 2017-04-24 | FY17Q3 | FY17Q3(A)
753 | Widger | Widger | Cornell | A1.13.03.02.01.03 |  | A1.13 - Safety | T-3 | Milestone: (FAT) - Design radiation monitor system Complete/Approved | 0 d | 0% | 2017-11-21 | 2017-11-21 |  |  |  |  | 2017-11-21 | FY18Q1
744 | Widger | Ray | Cornell | A1.13.02.02.01.04 |  | A1.13 - Safety | T-3 | Milestone: (FAT) Design approved by safety committee | 0 d | 0% | 2017-12-14 | 2017-12-14 |  |  |  |  | 2017-12-14 | FY18Q1
745 | Widger | Ray | Cornell | A1.13.02.02.02.03 |  | A1.13 - Safety | T-3 | Milestone: (FAT) Safety Procurements Received | 0 d | 0% | 2018-01-02 | 2018-01-02 |  |  |  |  | 2018-01-02 | FY18Q2
754 | Widger | Ray | Cornell | A1.13.03.02.02.04 |  | A1.13 - Safety | T-3 | Milestone: (FAT) Radiation Monitoring Procurements Received | 0 d | 0% | 2018-01-23 | 2018-01-23 |  |  |  |  | 2018-01-23 | FY18Q2
755 | Widger | Widger | Cornell | A1.13.03.02.03.07 |  | A1.13 - Safety | T-3 | Milestone: Radiation Monitor Safety process for FAT Relocate Complete (Link to Commissioning of beam directly) | 0 d | 0% | 2018-03-13 | 2018-03-13 |  |  |  |  | 2018-03-13 | FY18Q2
746 | Widger | Ray | Cornell | A1.13.02.02.03.08 |  | A1.13 - Safety | T-3 | Milestone: Safety process complete for (FAT) Test | 0 d | 0% | 2018-03-22 | 2018-03-22 |  |  |  |  | 2018-03-22 | FY18Q2
232 | Widger | Heltsely | Cornell | A1.13.01.03.06 |  | A1.13 - Safety | T-2 | Milestone: x-Ray Permit for Fractional Arc Test Approved | 0 d | 0% | 2018-03-30 | 2018-03-30 |  |  |  |  | 2018-03-30 | FY18Q2
230 | Widger | Kostroun | Cornell | A1.13.01.01.05 |  | A1.13 - Safety | T-2 | Milestone: Shielding Calculations/Physics Design Completed | 0 d | 0% | 2018-07-10 | 2018-07-10 |  |  |  |  | 2018-07-10 | FY18Q4
756 | Widger | Widger | Cornell | A1.13.03.03.01.03 |  | A1.13 - Safety | T-3 | Milestone: SPBT - Design radiation monitor system Complete/Approved | 0 d | 0% | 2018-10-29 | 2018-10-29 |  |  |  |  | 2018-10-29 | FY19Q1
747 | Widger | Ray | Cornell | A1.13.02.03.01.04 |  | A1.13 - Safety | T-3 | Milestone: (SPBT) Design approved by safety committee | 0 d | 0% | 2018-11-21 | 2018-11-21 |  |  |  |  | 2018-11-21 | FY19Q1
757 | Widger | Ray | Cornell | A1.13.03.03.02.03 |  | A1.13 - Safety | T-3 | Milestone: (SPBT) Radiation Monitoring Procurements Received | 0 d | 0% | 2018-11-29 | 2018-11-29 |  |  |  |  | 2018-11-29 | FY19Q1
233 | Widger | Heltsely | Cornell | A1.13.01.04.04 |  | A1.13 - Safety | T-2 | Milestone: x-Ray permit for SPBT Approved (No additional permits needed for 4PBT) | 0 d | 0% | 2018-12-19 | 2018-12-19 |  |  |  |  | 2018-12-19 | FY19Q1
748 | Widger | Ray | Cornell | A1.13.02.03.02.03 |  | A1.13 - Safety | T-3 | Milestone: (SPBT) Safety Procurements Received | 0 d | 0% | 2018-12-21 | 2018-12-21 |  |  |  |  | 2018-12-21 | FY19Q1
749 | Widger | Ray | Cornell | A1.13.02.03.03.07 |  | A1.13 - Safety | T-3 | Milestone: Safety process complete for PSS (SPBT) | 0 d | 0% | 2019-04-26 | 2019-04-26 |  |  |  |  | 2019-04-26 | FY19Q3
234 | Widger | Widger | Cornell | A1.13.04.01.09 |  | A1.13 - Safety | T-2 | Milestone: All Radiation Monitoring Procurements Received | 0 d | 0% | 2020-04-29 | 2020-04-29 |  |  |  |  | 2020-04-29 | FY20Q2

## by Date
hide | by | hide |  |  | hide | hide |  | ** Quarters are based on BNL's Fiscal Calendar ** T-3s are not reportable milestones | hide | hide | hide | hide | hide | hide | hide | hide | hide | hide |  |  | hide | hide | hide | hide | hide | hide
Calc_ID | Point of Contact L2 | Point of Contact L3 | Responsible Institution | WBS | Old WBS (Month 'YR) | System | Level | CBETA Reportable Milestones | Duration | % Complete | Current Schedule Finish Date | CBETA v0 Baseline Schedule Date (August 2017) | CBETA v1? Baseline (December 2017) | print order | Sorted Current Planned Date | Sorted Original Milestone Date | CBETA v0 Baseline Schedule Need by Date | New expected Date | Original Reportable Milestone Date | Current Planned Date (A/F) | Mth 'YR Planned Date | Milestone | Reportable Milestone Sort | Reportable Milestone Level Sort | PCR | Comments
693 | Gallagher | Gallagher | Cornell | A1.11.01.01.02 |  | A1.11 - System Integration | T-3 | CBETA ALL DWGS Start | 0 d | 100% | 2016-06-01 | 2016-06-01 |  |  |  |  | 2016-06-01 |  | FY17Q1 | FY17Q1(A)
1 | Smolenski/Michnoff | Michnoff | BNL | A1.01.01.01.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): NYSERDA Funding Date Start (Actual 10/31/2016) | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 |  | FY17Q1 | FY17Q1(A)
501 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.01 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design Activities Starts | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 |  | FY17Q1 | FY17Q1(A)
525 | Gulliford | Gulliford | Cornell | A1.03.01.01.01.01.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: Start of DC Gun Conditioning Activities | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 |  | FY17Q1 | FY17Q1(A)
150 | Burke | Burke | Cornell | A1.06.02.02.03.03 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets - Beam Stop Table - Assembly Complete | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2018-07-01 |  | FY17Q1 | [6 empty] | Incorrect dates - kwj
600 | Burke | Burke | Cornell | A1.06.01.02.01.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Electromagnet Table - Procurements complete | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2017-11-01 |  | FY17Q1
627 | Dobbins | Dobbins | Cornell | A1.08.03.01.01.03 |  | A1.08 - Controls | T-3 | Milestone: File Server Design Complete | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 |  | FY17Q1 | FY17Q1(A)
186 | Dobbins | Dobbins | Cornell | A1.09.05.03.01 |  | A1.09 - Instrumentation | T-2 | Milestone: BPM Assembly/Development - Pick-up Complete and ready for Final testing | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 |  | FY17Q1 | [6 empty] | Incorrect dates - kwj
690 | Li | Li | Cornell | A1.10.04.03.02.04 |  | A1.10 - Vacuum Systems | T-3 | Milestone: BPM buttons machining complete and ready for delivery to vendor | 0 d | 0% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2017-11-01 |  | FY17Q1
692 | Li | Li | Cornell | A1.10.05.04.01 |  | A1.10 - Vacuum Systems | T-3 | Milestone: BPM buttons machining complete and ready for delivery to vendor (Change) | 0 d | 0% | 2016-11-01 | 2016-11-01 | [6 empty] | FY17Q1
694 | Gallagher | Gallagher | Cornell | A1.11.01.01.04 |  | A1.11 - System Integration | T-3 | Milestone: Gun and ICM operational (Sector 00) (10/3/2016) | 0 d | 100% | 2016-11-01 | 2016-11-01 |  |  |  |  | 2016-11-01 |  | FY17Q1 | FY17Q1(A)
569 | Fumata | Sabol | Cornell | A1.04.05.02.01.01.02 |  | A1.04 - RF Systems | T-3 | Milestone: Design Pump System Layout (#1) Complete | 0 d | 100% | 2016-11-07 | 2016-11-07 |  |  |  |  | 2016-11-07 |  | FY17Q1 | FY17Q1(A)
502 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.02 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Initial Baseline Lattice Design Complete | 0 d | 100% | 2016-11-17 | 2016-11-17 |  |  |  |  | 2016-11-17 |  | FY17Q1 | FY17Q1(A)
556 | Fumata | Quigley | Cornell | A1.04.02.02.06 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Warmed Up and Ready for Disconnects | 0 d | 100% | 2016-11-21 | 2016-11-21 |  |  |  |  | 2016-11-21 |  | FY17Q1 | FY17Q1(A)
547 | Fumata | Quigley | Cornell | A1.04.01.01.01.01 |  | A1.04 - RF Systems | T-3 | Milestone: MLC ready for CBETA work | 0 d | 100% | 2016-12-01 | 2016-12-01 |  |  |  |  | 2016-12-01 |  | FY17Q1 | FY17Q1(A)
555 | Fumata | Quigley | Cornell | A1.04.02.01.01 |  | A1.04 - RF Systems | T-3 | Milestone: ICM ready for CBETA work | 0 d | 100% | 2016-12-01 | 2016-12-01 |  |  |  |  | 2016-12-01 |  | FY17Q1 | FY17Q1(A)
100 | Hoffstaetter | Trbojevic | BNL | A1.02.01.02.03 |  | A1.02 - Accelerator Physics | T-2 | Milestone: FFAG Halbach Magnet Design Chosen | 0 d | 100% | 2016-12-21 | 2016-12-21 |  |  |  |  | 2016-12-21 |  | FY17Q1 | FY17Q1(A)
548 | Fumata | Quigley | Cornell | A1.04.01.01.02.06 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Warmed Up and Ready for Disconnects | 0 d | 100% | 2016-12-22 | 2016-12-22 |  |  |  |  | 2016-12-22 |  | FY17Q1 | FY17Q1(A)
549 | Fumata | Quigley | Cornell | A1.04.01.01.03.03 |  | A1.04 - RF Systems | T-3 | Milestone: MLC in final Location | 0 d | 100% | 2017-01-12 | 2017-01-12 |  |  |  |  | 2017-01-12 |  | FY17Q2 | FY17Q2(A)
592 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.03.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Dipole Corrector Magnets - Design complete | 0 d | 100% | 2017-01-20 | 2017-01-20 |  |  |  |  | 2017-01-20 |  | FY17Q2 | FY17Q2(A)
628 | Dobbins | Dobbins | Cornell | A1.08.03.01.02.03 |  | A1.08 - Controls | T-3 | Milestone: All File Server Procurements Complete | 0 d | 100% | 2017-01-20 | 2017-01-20 |  |  |  |  | 2017-01-20 |  | FY17Q2 | FY17Q2(A)
223 | Bartnik | Bartnik | Cornell | A1.12.01.03 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Gun, ICM, Beam Stop - Commissioning Complete | 0 d | 100% | 2017-01-25 | 2017-01-25 |  |  |  |  | 2017-01-25 |  | FY17Q2
590 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Dipoles - Design complete | 0 d | 100% | 2017-01-27 | 2017-01-27 |  |  |  |  | 2017-01-27 |  | FY17Q2 | FY17Q2(A)
591 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Quadrupoles - Design complete | 0 d | 100% | 2017-01-27 | 2017-01-27 |  |  |  |  | 2017-01-27 |  | FY17Q2 | FY17Q2(A)
2 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.01.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Engineering Documentation Complete | 0 d | 100% | 2017-01-31 | 2017-01-31 |  |  |  |  | 2017-01-31 |  | FY17Q2 | FY17Q2(A)
536 | Gulliford | Gulliford | Cornell | A1.03.04.01.02 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B1 Merger - Transport Line Layout & Drawings Complete | 0 d | 100% | 2017-02-20 | 2017-02-20 |  |  |  |  | 2017-02-20 |  | FY17Q2 | FY17Q2(A)
559 | Fumata | Quigley | Cornell | A1.04.03.01.01.05 |  | A1.04 - RF Systems | T-3 | Milestone: FAT - LLRF Design Complete | 0 d | 100% | 2017-02-22 | 2017-02-22 |  |  |  |  | 2017-02-22 |  | FY17Q2 | FY17Q2(A)
566 | Fumata | Sabol | Cornell | A1.04.05.01.01.01.03.03 |  | A1.04 - RF Systems | T-3 | Milestone: All Cryogenic MLC Transferline Procurements Received and Complete | 0 d | 100% | 2017-02-24 | 2017-02-24 |  |  |  |  | 2017-02-24 |  | FY17Q2 | FY17Q2(A)
224 | Bartnik | Bartnik | Cornell | A1.12.02.03 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Diagnostics Line - Commissioning Complete | 0 d | 0% | 2017-02-27 | 2017-02-27 |  |  |  |  | 2017-11-27 |  | FY17Q2
578 | Tuozzolo | Tuozzolo | BNL | A1.05.01.01.01.04 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: PreProd FFAG Magnets - Halbach magnet w/ corrector design complete | 0 d | 100% | 2017-03-01 | 2017-03-01 |  |  |  |  | 2017-03-01 |  | FY17Q2 | FY17Q2(A)
567 | Fumata | Sabol | Cornell | A1.04.05.01.02.02.03 |  | A1.04 - RF Systems | T-3 | Milestone: All Cryogenic MLC Transferline Procurements Received and Complete | 0 d | 100% | 2017-03-10 | 2017-03-10 |  |  |  |  | 2017-03-10 |  | FY17Q2 | FY17Q2(A)
570 | Fumata | Sabol | Cornell | A1.04.05.02.01.02.07 |  | A1.04 - RF Systems | T-3 | Milestone: Pump Skid #1 - All Procurement Materials Received and Ready for Installation | 0 d | 100% | 2017-03-10 | 2017-03-10 |  |  |  |  | 2017-03-10 |  | FY17Q2 | FY17Q2(A)
593 | Burke | Burke | Cornell | A1.06.01.01.01.01.01.05 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Dipoles - Quadrupoles-Correctors - ALL Design complete | 0 d | 100% | 2017-03-13 | 2017-03-13 |  |  |  |  | 2017-03-13 |  | FY17Q2 | FY17Q2(A)
742 | Widger | Ray | Cornell | A1.13.02.01.02.03 |  | A1.13 - Safety | T-3 | Milestone: (MLC) Safety Procurements Received | 0 d | 100% | 2017-03-13 | 2017-03-13 |  |  |  |  | 2017-03-13 |  | FY17Q2 | FY17Q2(A)
537 | Gulliford | Gulliford | Cornell | A1.03.04.02.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - 80x20 Stand/Girders | 0 d | 100% | 2017-03-16 | 2017-03-16 |  |  |  |  | 2017-03-16 |  | FY17Q2 | FY17Q2(A)
579 | Tuozzolo | Tuozzolo | BNL | A1.05.01.01.02.03 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: PreProd FFAG Girder - Design Complete | 0 d | 100% | 2017-03-17 | 2017-03-17 |  |  |  |  | 2017-03-17 |  | FY17Q2 | FY17Q2(A)
629 | Dobbins | Dobbins | Cornell | A1.08.03.01.03.02 |  | A1.08 - Controls | T-3 | Milestone: File Server Installation and Configuration Complete | 0 d | 100% | 2017-03-17 | 2017-03-17 |  |  |  |  | 2017-03-17 |  | FY17Q2 | FY17Q2(A)
540 | Gulliford | Gulliford | Cornell | A1.03.05.01.01.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 DL - Transport Line Layout & Drawings Complete | 0 d | 100% | 2017-03-22 | 2017-03-22 |  |  |  |  | 2017-03-22 |  | FY17Q2 | FY17Q2(A)
750 | Widger | Widger | Cornell | A1.13.03.01.01.03 |  | A1.13 - Safety | T-3 | Milestone: (MLC) - Design radiation monitor system Complete/Approved | 0 d | 100% | 2017-03-23 | 2017-03-23 |  |  |  |  | 2017-03-23 |  | FY17Q2 | FY17Q2(A)
165 | Dobbins | Dobbins | Cornell | A1.08.03.01.04.02 |  | A1.08 - Controls | T-2 | Milestone: All File Server - Testing Complete | 0 d | 0% | 2017-03-31 | 2017-03-31 |  |  |  |  | 2017-03-31 |  | FY17Q2
698 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Final Design/Layout for East RF System Complete | 0 d | 100% | 2017-03-31 | 2017-03-31 |  |  |  |  | 2017-03-31 |  | FY17Q2 | FY17Q2(A)
695 | Gallagher | Gallagher | Cornell | A1.11.01.01.05 |  | A1.11 - System Integration | T-3 | Milestone: Vacuum Lab ready for Removal activities | 0 d | 100% | 2017-04-01 | 2017-04-01 |  |  |  |  | 2017-04-01 |  | FY17Q3 | FY17Q3(A)
531 | Gulliford | Cultera | Cornell | A1.03.03.02.01.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: Preliminary Cathode Material Existing and Available @ Cornell | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | 2017-04-03 |  | FY17Q3 | FY17Q3(A)
550 | Fumata | Quigley | Cornell | A1.04.01.02.01.04 |  | A1.04 - RF Systems | T-3 | MLC Cool Down #2 - Cool down to 4K (by Apr 3) | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | 2017-04-03 |  | FY17Q3 | FY17Q3(A)
568 | Fumata | Sabol | Cornell | A1.04.05.01.03.03 |  | A1.04 - RF Systems | T-3 | Milestone: All Cryogenic MLC Transferline Installation & Leak Test Complete | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | 2017-04-03 |  | FY17Q3 | FY17Q3(A)
655 | Dobbins | Dobbins | Cornell | A1.08.09.01.01.16 |  | A1.08 - Controls | T-3 | Milestone: MLC Test - Controls EPICS Integration complete | 0 d | 100% | 2017-04-03 | 2017-04-03 |  |  |  |  | 2017-04-03 |  | FY17Q3 | FY17Q3(A)
751 | Widger | Ray | Cornell | A1.13.03.01.02.03 |  | A1.13 - Safety | T-3 | Milestone: (MLC) Radiation Monitoring Procurements Received | 0 d | 100% | 2017-04-06 | 2017-04-06 |  |  |  |  | 2017-04-06 |  | FY17Q3 | FY17Q3(A)
503 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Final Baseline Lattice Design complete | 0 d | 100% | 2017-04-10 | 2017-04-10 |  |  |  |  | 2017-04-10 |  | FY17Q3 | FY17Q3(A)
743 | Widger | Ray | Cornell | A1.13.02.01.03.07 |  | A1.13 - Safety | T-3 | Milestone: Safety process complete for MLC Test (5/9) | 0 d | 100% | 2017-04-10 | 2017-04-10 |  |  |  |  | 2017-04-10 |  | FY17Q3 | FY17Q3(A)
705 | Gallagher | Gallagher | Cornell | A1.11.01.04.05.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Laser Room Design Complete | 0 d | 100% | 2017-04-11 | 2017-04-11 |  |  |  |  | 2017-04-11 |  | FY17Q3 | FY17Q3(A)
543 | Gulliford | Gulliford | Cornell | A1.03.05.02.02.07 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All B2 DL Vacuum Transport Line Materials Received | 0 d | 100% | 2017-04-12 | 2017-04-12 |  |  |  |  | 2017-04-12 |  | FY17Q3 | FY17Q3(A)
118 | Tuozzolo | Tuozzolo | BNL | A1.05.01.02.01.11 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Magnets - Procurements complete | 0 d | 100% | 2017-04-18 | 2017-04-18 |  |  |  |  | 2017-04-18 |  | FY17Q3 | FY17Q3(A)
551 | Fumata | Quigley | Cornell | A1.04.01.02.01.06 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #2 - Ready for RF Power (by 4/20) | 0 d | 100% | 2017-04-20 | 2017-04-20 |  |  |  |  | 2017-04-20 |  | FY17Q3 | FY17Q3(A)
557 | Fumata | Quigley | Cornell | A1.04.02.03.01.05 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Cool Down #2 - Ready for RF Power (by 4/20) | 0 d | 100% | 2017-04-20 | 2017-04-20 |  |  |  |  | 2017-04-20 |  | FY17Q3 | FY17Q3(A)
231 | Widger | Heltsely | Cornell | A1.13.01.02.05 |  | A1.13 - Safety | T-2 | Milestone: Safety/x-Ray Permit for MLC Beam through Merger Test Approved | 0 d | 100% | 2017-04-20 | 2017-04-20 |  |  |  |  | 2017-04-20 |  | FY17Q3 | FY17Q3(A)
135 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.03 |  | A1.06 - Splitter Magnets | T-3(2?) | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - Contract Awarded | 0 d | 100% | 2017-04-21 | 2017-04-21 |  |  |  |  | 2017-04-21 |  | FY17Q3
580 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.01.02 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: PreProd FFAG Magnets - PMM measurements complete and documented | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | 2017-04-24 |  | FY17Q3 | FY17Q3(A)
581 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.03.01 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Vacuum Chambers Received from Cornell for Pre-Production FFAG Magnet Assembly as of 4/24 | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | 2017-04-24 |  | FY17Q3 | FY17Q3(A)
656 | Dobbins | Dobbins | Cornell | A1.08.09.01.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: MLC Test - Integrated pre-beam testing for all Controls System Complete | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | 2017-04-24 |  | FY17Q3 | FY17Q3(A)
752 | Widger | Widger | Cornell | A1.13.03.01.03.07 |  | A1.13 - Safety | T-3 | Milestone: Radiation Monitor Safety process for MLC Relocate Complete (Link to Commissioning of beam directly) | 0 d | 100% | 2017-04-24 | 2017-04-24 |  |  |  |  | 2017-04-24 |  | FY17Q3 | FY17Q3(A)
538 | Gulliford | Gulliford | Cornell | A1.03.04.03.08 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B1 Merger Installation Complete | 0 d | 100% | 2017-04-26 | 2017-04-26 |  |  |  |  | 2017-04-26 |  | FY17Q3 | FY17Q3(A)
119 | Tuozzolo | Tuozzolo | BNL | A1.05.01.02.02.06 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Girder - Procurements complete | 0 d | 100% | 2017-04-26 | 2017-04-26 |  |  |  |  | 2017-04-26 |  | FY17Q3 | FY17Q3(A)
120 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.01.06 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Magnets - Assembly complete | 0 d | 100% | 2017-04-27 | 2017-04-27 |  |  |  |  | 2017-04-27 |  | FY17Q3 | FY17Q3(A)
121 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.02.02 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Girder - Assembly complete | 0 d | 100% | 2017-04-27 | 2017-04-27 |  |  |  |  | 2017-04-27 |  | FY17Q3 | FY17Q3(A)
667 | Dobbins | Dobbins | Cornell | A1.09.02.03.01 |  | A1.09 - Instrumentation | T-3 | Milestone: Existing BAMs tested and available for install | 0 d | 100% | 2017-04-28 | 2017-04-28 |  |  |  |  | 2017-04-28 |  | FY17Q3 | FY17Q3(A)
3 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.01.03 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Prototype Girder Assembled | 0 d | 100% | 2017-04-30 | 2017-04-30 |  |  |  |  | 2017-04-30 |  | FY17Q3 | FY17Q3(A)
539 | Gulliford | Gulliford | Cornell | A1.03.04.04.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B1 Merger Beam Line Instrumentation Integration Complete | 0 d | 100% | 2017-05-02 | 2017-05-02 |  |  |  |  | 2017-05-02 |  | FY17Q3 | FY17Q3(A)
552 | Fumata | Quigley | Cornell | A1.04.01.02.01.07 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #2 - RF Power Turned On and MLC System Stable by 5/2 | 0 d | 100% | 2017-05-03 | 2017-05-03 |  |  |  |  | 2017-05-03 |  | FY17Q3 | FY17Q3(A)
558 | Fumata | Quigley | Cornell | A1.04.02.03.01.06 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Cool Down #2 - RF Power Turned On and ICM System Stable by 5/2 | 0 d | 100% | 2017-05-03 | 2017-05-03 |  |  |  |  | 2017-05-03 |  | FY17Q3 | FY17Q3(A)
122 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.03.03 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Pre-Production Magnet/Vacuum Chamber Assembly on Girders Complete | 0 d | 100% | 2017-05-03 | 2017-05-03 |  |  |  |  | 2017-05-03 |  | FY17Q3 | FY17Q3(A)
545 | Gulliford | Gulliford | Cornell | A1.03.05.03.01.05 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 Diagnostic Beam Line (FY17) Installation Complete | 0 d | 100% | 2017-05-04 | 2017-05-04 |  |  |  |  | 2017-05-04 |  | FY17Q3 | FY17Q3(A)
528 | Gulliford | Bartnik | Cornell | A1.03.02.02.01.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - 43 MHz Laser Parts | 0 d | 100% | 2017-05-05 | 2017-05-05 |  |  |  |  | 2017-05-05 |  | FY17Q3 | FY17Q3(A)
657 | Dobbins | Dobbins | Cornell | A1.08.09.01.02.02.16 |  | A1.08 - Controls | T-3 | Milestone: Controls - MLC Test - Commissioning with Beam for all Controls System Complete | 0 d | 100% | 2017-05-05 | 2017-05-05 |  |  |  |  | 2017-05-05 |  | FY17Q3 | FY17Q3(A)
565 | Fumata | Quigley | Cornell | A1.04.04.02.02.06 |  | A1.04 - RF Systems | T-3 | Milestone: All Waveguide & Tuner Procurements Received and Complete | 0 d | 0% | 2017-05-08 | 2017-05-08 |  |  |  |  | 2017-05-08 |  | FY17Q3
646 | Dobbins | Dobbins | Cornell | A1.08.07.04.03 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for MLC Test | 0 d | 100% | 2017-05-08 | 2017-05-08 |  |  |  |  | 2017-05-08 |  | FY17Q3 | FY17Q3(A)
653 | Dobbins | Dobbins | Cornell | A1.08.08.04.03 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System - Installation and Testing - Complete and ready for MLC Test | 0 d | 100% | 2017-05-08 | 2017-05-08 |  |  |  |  | 2017-05-08 |  | FY17Q3 | FY17Q3(A)
691 | Li | Li | Cornell | A1.10.05.01.05 |  | A1.10 - Vacuum Systems | T-3 | Milestone: Vacuum FFAG Straight System - All Designs Complete | 0 d | 0% | 2017-05-09 | 2017-05-09 |  |  |  |  | 2017-05-09 |  | FY17Q3
683 | Dobbins | Dobbins | Cornell | A1.09.05.07.01.01.08 |  | A1.09 - Instrumentation | T-3 | Milestone: MLC Test - Instrumentation System Final Installation Complete | 0 d | 100% | 2017-05-11 | 2017-05-11 |  |  |  |  | 2017-05-11 |  | FY17Q3 | FY17Q3(A)
684 | Dobbins | Dobbins | Cornell | A1.09.05.07.01.02.02 |  | A1.09 - Instrumentation | T-3 | Milestone: MLC Test - Instrumentation System Testing Complete | 0 d | 100% | 2017-05-12 | 2017-05-12 |  |  |  |  | 2017-05-12 |  | FY17Q3 | FY17Q3(A)
101 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.05 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Final Baseline Lattice Design Approved by CBETA Board | 0 d | 100% | 2017-05-15 | 2017-05-15 |  |  |  |  | 2017-05-15 |  | FY17Q3 | FY17Q3(A)
685 | Dobbins | Dobbins | Cornell | A1.09.05.07.01.03.02 |  | A1.09 - Instrumentation | T-3 | Milestone: MLC Test - Instrumentation Commissioning with Beam Complete | 0 d | 100% | 2017-05-15 | 2017-05-15 |  |  |  |  | 2017-05-15 |  | FY17Q3 | FY17Q3(A)
596 | Burke | Burke | Cornell | A1.06.01.01.01.04.01.05 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Mounts and Stages - ALL Design Complete | 0 d | 0% | 2017-05-17 | 2017-05-17 |  |  |  |  | 2017-05-17 |  | FY17Q3
706 | Gallagher | Gallagher | Cornell | A1.11.01.04.05.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All Laser Room Procurements Complete | 0 d | 100% | 2017-05-23 | 2017-05-23 |  |  |  |  | 2017-05-23 |  | FY17Q3
611 | Burke | Burke | Cornell | A1.06.02.01.02.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Quadrupoles - Design complete | 0 d | 0% | 2017-05-30 | 2017-05-30 |  |  |  |  | 2017-05-30 |  | FY17Q3
613 | Burke | Burke | Cornell | A1.06.02.01.03.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Magnet Mounts - Design complete | 0 d | 0% | 2017-05-30 | 2017-05-30 |  |  |  |  | 2017-05-30 |  | FY17Q3
505 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.07 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Lattice Design Updates/Adjustment for Fractional Arc Test Complete | 0 d | 100% | 2017-06-01 | 2017-06-01 |  |  |  |  | 2017-06-01 |  | FY17Q3 | FY17Q3(A)
516 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.01 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Lattice Design Updates/Adjustment for SPBT Complete | 0 d | 0% | 2017-06-01 | 2017-06-01 |  |  |  |  | 2017-06-01 |  | FY17Q3
609 | Burke | Burke | Cornell | A1.06.02.01.01.01.04 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Dipoles - Design complete | 0 d | 0% | 2017-06-07 | 2017-06-07 |  |  |  |  | 2017-06-07 |  | FY17Q3
202 | Gallagher | Gallagher | Cornell | A1.11.01.03.02.01.09 |  | A1.11 - System Integration | T-2 | Milestone: L0E Vacuum Lab Removal Complete | 0 d | 100% | 2017-06-08 | 2017-06-08 |  |  |  |  | 2017-06-08 |  | FY17Q3 | FY17Q3(A)
102 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.08 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Lattice Design Updates/Adjustment for Fractional Arc Test Approved by CBETA Board | 0 d | 100% | 2017-06-14 | 2017-06-14 |  |  |  |  | 2017-06-14 |  | FY17Q3 | FY17Q3(A)
103 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.02 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Lattice Design Updates/Adjustment for SPBT Approved by CBETA Board | 0 d | 0% | 2017-06-14 | 2017-06-14 |  |  |  |  | 2017-06-14 |  | FY17Q3
225 | Bartnik | Bartnik | Cornell | A1.12.03.06 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): MLC - Commissioning Complete | 0 d | 0% | 2017-06-15 | 2017-06-15 |  |  |  |  | 2017-12-01 |  | FY17Q3
514 | Hoffstaetter | Liu | Cornell | A1.02.01.02.17 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Finalize mechanical coordinates of the lattice - Splitter beam pipe and magnet girders | 0 d | 0% | 2017-06-20 | 2017-06-20 |  |  |  |  | 2017-06-20 |  | FY17Q3
108 | Gulliford | Gulliford | Cornell | A1.03.05.04.04 |  | A1.03 - DC/Gun Injector | T-2 | Milestone: B2 Diagnostic Beam Line Instrumentation Integration Complete | 0 d | 100% | 2017-06-21 | 2017-06-21 |  |  |  |  | 2017-06-21 |  | FY17Q3
542 | Gulliford | Gulliford | Cornell | A1.03.05.02.01.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received and Accepted - B2 DL Magnets | 0 d | 100% | 2017-06-26 | 2017-06-26 |  |  |  |  | 2017-06-26 |  | FY17Q3 | FY17Q3(A)
612 | Burke | Burke | Cornell | A1.06.02.01.02.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets (Quads) - Contract Awarded | 0 d | 0% | 2017-06-27 | 2017-06-27 |  |  |  |  | 2017-06-27 |  | FY17Q3
4 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.01.04 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Magnet Production Approved | 0 d | 100% | 2017-06-30 | 2017-06-30 |  |  |  |  | 2017-06-30 |  | FY17Q3 | FY17Q3(A)
696 | Gallagher | Gallagher | Cornell | A1.11.01.01.06 |  | A1.11 - System Integration | T-3 | Milestone: Water Shut off (by June 30 2017) - 6 weeks | 0 d | 100% | 2017-06-30 | 2017-06-30 |  |  |  |  | 2017-06-30 |  | FY17Q3 | FY17Q3(A)
601 | Burke | Burke | Cornell | A1.06.01.02.01.03.09 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets -Electromagnet Table Supporting Hardware - ALL Design Complete | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 |  | FY17Q4
610 | Burke | Burke | Cornell | A1.06.02.01.01.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets (Dipoles) - Contract Awarded (using BNL magnets) | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 |  | FY17Q4
621 | Dobbins | Dobbins | Cornell | A1.08.02.01.01.03 |  | A1.08 - Controls | T-3 | Milestone: IOC Computer Design Complete | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 |  | FY17Q4
624 | Dobbins | Dobbins | Cornell | A1.08.02.02.01.03 |  | A1.08 - Controls | T-3 | Milestone: Operator Consoles Design Complete | 0 d | 100% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 |  | FY17Q4 | FY17Q4(A)
630 | Dobbins | Dobbins | Cornell | A1.08.04.01.01.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS Archiver Design Complete | 0 d | 100% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 |  | FY17Q4 | FY17Q4(A)
636 | Dobbins | Dobbins | Cornell | A1.08.04.03.01.03 |  | A1.08 - Controls | T-3 | Milestone: Configuration Database Design Complete | 0 d | 0% | 2017-07-06 | 2017-07-06 |  |  |  |  | 2017-07-06 |  | FY17Q4
123 | Tuozzolo | Tuozzolo | BNL | A1.05.01.03.03.05 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: PreProd FFAG Magnets and Girder - Halbach Magnets & Girder Assembly & Testing complete | 0 d | 100% | 2017-07-07 | 2017-07-07 |  |  |  |  | 2017-07-07 |  | FY17Q4 | FY17Q4(A)
633 | Dobbins | Dobbins | Cornell | A1.08.04.02.01.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS Alarm Handler Design Complete | 0 d | 0% | 2017-07-07 | 2017-07-07 |  |  |  |  | 2017-07-07 |  | FY17Q4
526 | Gulliford | Bartnik | Cornell | A1.03.02.01.02.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - E/O Modulator | 0 d | 100% ? | 2017-07-12 | 2017-07-12 |  |  |  |  | 2017-07-12 |  | FY17Q4
143 | Burke | Burke | Cornell | A1.06.01.02.01.01.05 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Electromagnet Table - ALL Design Complete | 0 d | 0% | 2017-07-21 | 2017-07-21 |  |  |  |  | 2017-07-21 |  | FY17Q4
614 | Burke | Burke | Cornell | A1.06.02.01.03.02.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Support Hardware Procurements complete | 0 d | 0% | 2017-07-26 | 2017-07-26 |  |  |  |  | 2017-07-26 |  | FY17Q4
672 | Dobbins | Dobbins | Cornell | A1.09.05.01.01.06 |  | A1.09 - Instrumentation | T-3 | Milestone: All System Specifications Finalized/Complete | 0 d | 100% | 2017-08-01 | 2017-08-01 |  |  |  |  | 2017-08-01 |  | FY17Q4 | FY17Q4(A)
124 | Tuozzolo | Tuozzolo | BNL | A1.05.02.01.01.05 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets - Halbach w/ corrector design revisions complete | 0 d | 100% | 2017-08-02 | 2017-08-02 |  |  |  |  | 2017-08-02 |  | FY17Q4 | FY17Q4(A)
699 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All East RF System Relocation Procurements Complete | 0 d | 100% ? | 2017-08-08 | 2017-08-08 |  |  |  |  | 2017-08-08 |  | FY17Q4
139 | Burke | Burke | Cornell | A1.06.01.01.01.02.01.05 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Common Magnets - Design complete | 0 d | 0% | 2017-08-10 | 2017-08-10 |  |  |  |  | 2017-09-14 |  | FY17Q4
162 | Dobbins | Dobbins | Cornell | A1.08.01.01.04 |  | A1.08 - Controls | T-2 | Milestone: Network Infrastructure Design Complete | 0 d | 0% | 2017-08-10 | 2017-08-10 |  |  |  |  | 2017-08-10 |  | FY17Q4
668 | Dobbins | Dobbins | Cornell | A1.09.03.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: BCM Design Complete (no BCM is planned at this time, 9/2017) | 0 d | 0% | 2017-08-10 | 2017-08-10 |  |  |  |  | 2017-08-10 |  | FY17Q4
199 | Gallagher | Gallagher | Cornell | A1.11.01.01.07 |  | A1.11 - System Integration | T-2 | Milestone: Water Turned On - L0E Work continued | 0 d | 100% | 2017-08-11 | 2017-08-11 |  |  |  |  | 2017-08-11 |  | FY17Q4
721 | Gallagher | Gallagher | Cornell | A1.11.02.02.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 01-LA: North MLC and diagnostics Beam line Ready for System Integration | 0 d | 100% | 2017-08-11 | 2017-08-11 |  |  |  |  | 2017-08-11 |  | FY17Q4 | FY17Q4(A)
106 | Gulliford | Bartnik | Cornell | A1.03.02.02.02.01 |  | A1.03 - DC/Gun Injector | T-2 | Milestone: Laser Room Move Complete and Ready for Table Setup[Clean Room conditions established | 0 d | 100% | 2017-08-15 | 2017-08-15 |  |  |  |  | 2017-08-15 |  | FY17Q4 | FY17Q4(A)
638 | Dobbins | Michnoff | BNL | A1.08.05.01.02 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - BPM - Sample hardware available for software development (Rob has the equipment and is bringing it back to CU for testing by the end of June) | 0 d | 100% | 2017-08-15 | 2017-08-15 |  |  |  |  | 2017-08-15 |  | FY17Q4 | FY17Q4(A)
680 | Dobbins | Dobbins | Cornell | A1.09.05.06.01.02 |  | A1.09 - Instrumentation | T-3 | Milestone: Develop Beam stop beam-pipe hardware design complete (Vacuum section) | 0 d | 0% | 2017-08-15 | 2017-08-15 |  |  |  |  | 2017-08-15 |  | FY17Q4
681 | Dobbins | Dobbins | Cornell | A1.09.05.06.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: Beam Stop Design Complete | 0 d | 0% | 2017-08-15 | 2017-08-15 |  |  |  |  | 2017-08-15 |  | FY17Q4
194 | Li | Li | Cornell | A1.10.04.01.05 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc System - All Designs Complete | 0 d | 0% | 2017-08-15 | 2017-08-15 |  |  |  |  | 2017-08-15 |  | FY17Q4
707 | Gallagher | Gallagher | Cornell | A1.11.01.04.05.03.02 |  | A1.11 - System Integration | T-3 | Milestone: Laser Room Fabrication Complete and Table Ready for Set-Up | 0 d | 0% | 2017-08-17 | 2017-08-17 |  |  |  |  | 2017-08-17 |  | FY17Q4
645 | Dobbins | Dobbins | Cornell | A1.08.07.01.03 |  | A1.08 - Controls | T-3 | Milestone: Timing system - System design complete | 0 d | 0% | 2017-08-18 | 2017-08-18 |  |  |  |  | 2017-08-18 |  | FY17Q4
504 | Hoffstaetter | Berg | Cornell | A1.02.01.02.06 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Finalize mechanical coordinates of the lattice - FFAG beam pipe and magnet girders | 0 d | 0% | 2017-08-24 | 2017-08-24 |  |  |  |  | 2017-08-24 |  | FY17Q4
125 | Tuozzolo | Tuozzolo | BNL | A1.05.02.01.02.03 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Girders - Design Complete | 0 d | 0% | 2017-08-25 | 2017-08-25 |  |  |  |  | 2017-08-25 |  | FY17Q4
615 | Burke | Burke | Cornell | A1.06.02.02.01.03 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Beam Stop Table - ALL Design Complete | 0 d | 0% | 2017-08-25 | 2017-08-25 |  |  |  |  | 2017-08-25 |  | FY17Q4
210 | Gallagher | Gallagher | Cornell | A1.11.02.02.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 01-LA: North MLC and diagnostics Beam line -System Integration Complete | 0 d | 100% | 2017-08-25 | 2017-08-25 |  |  |  |  | 2017-08-25 |  | FY17Q4 | FY17Q4(A)
5 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.01.05 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Beam through Main Linac Cryomodule (MLC) [Actual Finish 6/16/17, Planned Finish 8/31/17] | 0 d | 100% | 2017-08-31 | 2017-08-31 |  |  |  |  | 2017-08-31 |  | FY17Q4 | FY17Q3(A)
532 | Gulliford | Cultera | Cornell | A1.03.03.02.02.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: FAT Cathode Material Available @ Cornell | 0 d | 100% | 2017-08-31 | 2017-08-31 |  |  |  |  | 2017-08-31 |  | FY17Q4 | FY17Q4(A)
112 | Fumata | Quigley | Cornell | A1.04.04.02.01.04 |  | A1.04 - RF Systems | T-2 | Milestone: 1st Article Solid State Amplifiers (SSA) Received @ Cornell (end of August) | 0 d | 0% | 2017-09-06 | 2017-09-06 |  |  |  |  | 2017-10-25 |  | FY17Q4
527 | Gulliford | Bartnik | Cornell | A1.03.02.01.03.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: E/O Modulator Software Development Complete | 0 d | 0% | 2017-09-07 | 2017-09-07 |  |  |  |  | 2017-09-07 |  | FY17Q4
529 | Gulliford | Bartnik | Cornell | A1.03.02.02.02.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: 43 MHz Laser - Modification and Table Set-up Complete | 0 d | 0% | 2017-09-13 | 2017-09-13 |  |  |  |  | 2017-09-13 |  | FY17Q4
674 | Dobbins | Dobbins | Cornell | A1.09.05.01.03.08 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM Clock Distribution Design Complete (FAT) | 0 d | 0% | 2017-09-13 | 2017-09-13 |  |  |  |  | 2017-09-13 |  | FY17Q4
679 | Dobbins | Dobbins | Cornell | A1.09.05.05.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: View Screen Design Complete | 0 d | 0% | 2017-09-14 | 2017-09-14 |  |  |  |  | 2017-09-14 |  | FY17Q4
622 | Dobbins | Dobbins | Cornell | A1.08.02.01.02.03 |  | A1.08 - Controls | T-3 | Milestone: All IOC Computer Procurements Complete | 0 d | 0% | 2017-09-15 | 2017-09-15 |  |  |  |  | 2017-09-15 |  | FY17Q4
625 | Dobbins | Dobbins | Cornell | A1.08.02.02.02.03 |  | A1.08 - Controls | T-3 | Milestone: All Operator Consoles Procurements Complete | 0 d | 0% | 2017-09-15 | 2017-09-15 |  |  |  |  | 2017-09-15 |  | FY17Q4
631 | Dobbins | Dobbins | Cornell | A1.08.04.01.02.03 |  | A1.08 - Controls | T-3 | Milestone: All Archiver Computer Procurements Complete | 0 d | 100% | 2017-09-15 | 2017-09-15 |  |  |  |  | 2017-09-15 |  | FY17Q4 | FY17Q4(A)
664 | Dobbins | Dobbins | Cornell | A1.09.02.01.07 |  | A1.09 - Instrumentation | T-3 | Milestone: BAM Design Complete | 0 d | 0% | 2017-09-15 | 2017-09-15 |  |  |  |  | 2017-09-15 |  | FY17Q4
634 | Dobbins | Dobbins | Cornell | A1.08.04.02.02.03 |  | A1.08 - Controls | T-3 | Milestone: All EPICS Alarm Handler Procurements Complete | 0 d | 0% | 2017-09-18 | 2017-09-18 |  |  |  |  | 2017-09-18 |  | FY17Q4
107 | Gulliford | Gulliford | Cornell | A1.03.02.03.04 |  | A1.03 - DC/Gun Injector | T-2 | Milestone: Laser Transport Line - Beam Test (Gun Only) Complete | 0 d | 0% | 2017-09-22 | 2017-09-22 |  |  |  |  | 2017-09-22 |  | FY17Q4
670 | Dobbins | Dobbins | Cornell | A1.09.04.01.03 |  | A1.09 - Instrumentation | T-3 | Milestone: Beam Loss Monitor Design Complete | 0 d | 0% | 2017-09-22 | 2017-09-22 |  |  |  |  | 2017-09-22 |  | FY17Q4
616 | Burke | Burke | Cornell | A1.06.02.02.02.04 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets - Table Support Hardware - Procurements complete | 0 d | 0% | 2017-09-25 | 2017-09-25 |  |  |  |  | 2017-09-25 |  | FY17Q4
200 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.03.01 |  | A1.11 - System Integration | T-2 | Milestone: L0 ERF Testing Complete and ready for L0E ERF Move to L0 | 0 d | 100% | 2017-09-25 | 2017-09-25 |  |  |  |  | 2017-09-25 |  | FY17Q4
149 | Burke | Burke | Cornell | A1.06.02.01.03.03.06 |  | A1.06 - Splitter Magnets | T-2 | Milestones: Extraction Line Magnets - Magnets and Mounts Assembled on Stands | 0 d | 0% | 2017-09-26 | 2017-09-26 |  |  |  |  | 2017-09-26 |  | FY17Q4
597 | Burke | Burke | Cornell | A1.06.01.01.01.04.02.08 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Support Hardware - Procurements complete | 0 d | 0% | 2017-09-26 | 2017-09-26 |  |  |  |  | 2017-09-26 |  | FY17Q4
573 | Fumata | Sabol | Cornell | A1.04.05.02.02.01.02 |  | A1.04 - RF Systems | T-3 | Milestone: Design Pump System Layout (#2-3-4) Complete | 0 d | 0% ? | 2017-09-28 | 2017-09-28 |  |  |  |  | 2017-09-28 |  | FY17Q4
500 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.01.06 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY17 - Complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
506 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.09 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics with suitable high-energy septum finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
507 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.10 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics for low-energy septum finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
508 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.11 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design of transition Halbach with reduced QF and BDTs finalized | 0 d | 100% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
509 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.12 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design lattice for the prototype magnets finalized | 0 d | 100% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
510 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.13 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design lattice for splitter line to match the full energy range finalized | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
511 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.14 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Simulation of orbit correction for the full energy range complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
512 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.15 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Simulation of aperture measurements with beam-loss monitors complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
513 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.01.02.16 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Complete optics for each accelerating and recirculating pass finalized | 0 d | 100% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
517 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.03 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics from source through MLC(1) with space charge finalized | 0 d | 100% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
140 | Burke | Burke | Cornell | A1.06.01.01.01.03.01.05 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Septa Magnets - Design complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
637 | Dobbins | Dobbins | Cornell | A1.08.04.03.02.02 |  | A1.08 - Controls | T-3 | Milestone: Configuration Database Installation and Configuration Complete | 0 d | 0% | 2017-09-29 | 2017-09-29 |  |  |  |  | 2017-09-29 |  | FY17Q4
115 | Fumata | Quigley | Cornell | A1.04.04.04.01.03 |  | A1.04 - RF Systems | T-2 | Milestone: RF Systems Ready for Fractional Arc Test (FAT) | 0 d | 0% | 2017-10-05 | 2017-10-05 |  |  |  |  | 2018-01-02 |  | FY18Q1
618 | Dobbins | Dobbins | Cornell | A1.08.01.02.05 |  | A1.08 - Controls | T-3 | Milestone: All Network Infrastructure Procurements Complete | 0 d | 0% | 2017-10-06 | 2017-10-06 |  |  |  |  | 2017-10-06 |  | FY18Q1
560 | Fumata | Quigley | Cornell | A1.04.03.02.01.05 |  | A1.04 - RF Systems | T-3 | Milestone: All LLRF Material/Components (FAT) Complete | 0 d | 0% | 2017-10-10 | 2017-10-10 |  |  |  |  | 2017-10-10 |  | FY18Q1
576 | Fumata | Sabol | Cornell | A1.04.05.03.01.01.04 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Pump Skids - All Procurement Materials Received and Ready for Installation | 0 d | 0% | 2017-10-10 | 2017-10-10 |  |  |  |  | 2017-10-10 |  | FY18Q1
169 | Dobbins | Michnoff | BNL | A1.08.05.01.05 |  | A1.08 - Controls | T-2 | Milestone: EPICS device support - BPM - Testing Complete | 0 d | 0% | 2017-10-12 | 2017-10-12 |  |  |  |  | 2017-10-12 |  | FY18Q1
639 | Dobbins | Michnoff | BNL | A1.08.05.02.02 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - BAM - Sample hardware available for software development | 0 d | 0% | 2017-10-16 | 2017-10-16 |  |  |  |  | 2017-10-16 |  | FY18Q1
177 | Dobbins | Dobbins | Cornell | A1.08.07.02.03 |  | A1.08 - Controls | T-2 | Milestone: All Timing System Procurements Complete | 0 d | 0% | 2017-10-17 | 2017-10-17 |  |  |  |  | 2017-10-17 |  | FY18Q1
136 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.15 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - 1st Batch Delivered to Cornell (Sector-SX Northeast) 10/24/17 | 0 d | 0% | 2017-10-26 | 2017-10-26 |  |  |  |  | 2017-10-26 |  | FY18Q1
640 | Dobbins | Dobbins | Cornell | A1.08.05.03.01.01 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - Magnet power supplies - Hardware Identified/Specification Complete (Predecessors - All Power Supplies selected) | 0 d | 0% | 2017-10-26 | 2017-10-26 |  |  |  |  | 2017-10-26 |  | FY18Q1
158 | Barley | Barley | Cornell | A1.07.04.02.02 |  | A1.07 - Power Supplies | T-2 | Milestone: Contract Awarded - FFAG Corrector Power Supplies | 0 d | 100% | 2017-10-27 | 2017-10-27 |  |  |  |  | 2017-10-27 |  | FY18Q1
701 | Gallagher | Gallagher | Cornell | A1.11.01.03.03.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All CESR-85F Cooling System Components Procurements Received | 0 d | 0% | 2017-10-27 | 2017-10-27 |  |  |  |  | 2017-10-27 |  | FY18Q1
619 | Dobbins | Dobbins | Cornell | A1.08.01.03.03 |  | A1.08 - Controls | T-3 | Milestone: Network Infrastructure Installation and Configuration Complete | 0 d | 0% | 2017-11-06 | 2017-11-06 |  |  |  |  | 2017-11-06 |  | FY18Q1
152 | Barley | Barley | Cornell | A1.07.01.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Dipole Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2017-11-07 | 2017-11-07 |  |  |  |  | 2017-11-07 |  | FY18Q1
700 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.03.04 |  | A1.11 - System Integration | T-3 | Milestone: East RF Systems Install Complete | 0 d | 0% | 2017-11-07 | 2017-11-07 |  |  |  |  | 2017-11-07 |  | FY18Q1
154 | Barley | Barley | Cornell | A1.07.02.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Quadrupole Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2017-11-08 | 2017-11-08 |  |  |  |  | 2017-11-08 |  | FY18Q1
156 | Barley | Barley | Cornell | A1.07.03.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Corrector Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2017-11-08 | 2017-11-08 |  |  |  |  | 2017-11-08 |  | FY18Q1
632 | Dobbins | Dobbins | Cornell | A1.08.04.01.03.02 |  | A1.08 - Controls | T-3 | Milestone: EPICS Archiver Installation and Configuration Complete | 0 d | 100% | 2017-11-10 | 2017-11-10 |  |  |  |  | 2017-11-10 |  | FY18Q1 | FY17Q4(A)
623 | Dobbins | Dobbins | Cornell | A1.08.02.01.03.02 |  | A1.08 - Controls | T-3 | Milestone: IOC Computer Installation and Configuration Complete | 0 d | 0% | 2017-11-14 | 2017-11-14 |  |  |  |  | 2017-11-14 |  | FY18Q1
626 | Dobbins | Dobbins | Cornell | A1.08.02.02.03.02 |  | A1.08 - Controls | T-3 | Milestone: Operator Consoles Installation and Configuration Complete | 0 d | 0% | 2017-11-14 | 2017-11-14 |  |  |  |  | 2017-11-14 |  | FY18Q1
641 | Dobbins | Dobbins | Cornell | A1.08.05.03.02.01 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - Magnet power supplies - Sample hardware available for software development (predecessor power supply specs - verify with Karl, successor is FF to at least 1 hardware available - redundant due to #1254?) | 0 d | 0% | 2017-11-20 | 2017-11-20 |  |  |  |  | 2017-11-20 |  | FY18Q1
753 | Widger | Widger | Cornell | A1.13.03.02.01.03 |  | A1.13 - Safety | T-3 | Milestone: (FAT) - Design radiation monitor system Complete/Approved | 0 d | 0% | 2017-11-21 | 2017-11-21 |  |  |  |  | 2017-11-21 |  | FY18Q1
577 | Fumata | Sabol | Cornell | A1.04.05.03.01.02.10 |  | A1.04 - RF Systems | T-3 | Milestone: ICM Pump Skids- Installation Complete | 0 d | 0% | 2017-11-27 | 2017-11-27 |  |  |  |  | 2017-11-27 |  | FY18Q1
166 | Dobbins | Dobbins | Cornell | A1.08.04.01.04.02 |  | A1.08 - Controls | T-2 | Milestone: All EPICS Archiver - Testing Complete | 0 d | 0% | 2017-11-28 | 2017-11-28 |  |  |  |  | 2017-11-28 |  | FY18Q1
164 | Dobbins | Dobbins | Cornell | A1.08.02.02.04.02 |  | A1.08 - Controls | T-2 | Milestone: All Operator Consoles - Testing Complete | 0 d | 0% | 2017-11-29 | 2017-11-29 |  |  |  |  | 2017-11-29 |  | FY18Q1
642 | Dobbins | Dobbins | Cornell | A1.08.05.03.02.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS device support - Magnet power supplies - Software development complete | 0 d | 0% | 2017-11-29 | 2017-11-29 |  |  |  |  | 2017-11-29 |  | FY18Q1
163 | Dobbins | Dobbins | Cornell | A1.08.02.01.04.02 |  | A1.08 - Controls | T-2 | Milestone: All IOC Computers - Testing Complete | 0 d | 0% | 2017-11-30 | 2017-11-30 |  |  |  |  | 2017-11-30 |  | FY18Q1
168 | Dobbins | Dobbins | Cornell | A1.08.04.03.03.02 |  | A1.08 - Controls | T-2 | Milestone: Configuration Database - Testing Complete | 0 d | 0% | 2017-11-30 | 2017-11-30 |  |  |  |  | 2017-11-30 |  | FY18Q1
171 | Dobbins | Dobbins | Cornell | A1.08.05.03.03.02 |  | A1.08 - Controls | T-2 | Milestone: EPICS device support - Magnet power supplies - Testing Complete | 0 d | 0% | 2017-11-30 | 2017-11-30 |  |  |  |  | 2017-11-30 |  | FY18Q1
697 | Gallagher | Gallagher | Cornell | A1.11.01.01.08 |  | A1.11 - System Integration | T-3 | Milestone: Start L0E construction (East-RF move to L0 Pit complete/operational) 12/4/17? | 0 d | 0% | 2017-12-04 | 2017-12-04 |  |  |  |  | 2017-12-04 |  | FY18Q1
682 | Dobbins | Dobbins | Cornell | A1.09.05.06.02.05 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Stop Procurements Complete | 0 d | 0% | 2017-12-05 | 2017-12-05 |  |  |  |  | 2017-12-05 |  | FY18Q1
620 | Dobbins | Dobbins | Cornell | A1.08.01.04.02 |  | A1.08 - Controls | T-3 | Milestone: Network Infrastructure Complete | 0 d | 0% | 2017-12-07 | 2017-12-07 |  |  |  |  | 2017-12-07 |  | FY18Q1
744 | Widger | Ray | Cornell | A1.13.02.02.01.04 |  | A1.13 - Safety | T-3 | Milestone: (FAT) Design approved by safety committee | 0 d | 0% | 2017-12-14 | 2017-12-14 |  |  |  |  | 2017-10-06 |  | FY18Q1
635 | Dobbins | Dobbins | Cornell | A1.08.04.02.03.03 |  | A1.08 - Controls | T-3 | Milestone: EPICS Alarm Handler Installation and Configuration Complete | 0 d | 0% | 2017-12-15 | 2017-12-15 |  |  |  |  | 2017-12-15 |  | FY18Q1
562 | Fumata | Quigley | Cornell | A1.04.03.03.01.07 |  | A1.04 - RF Systems | T-3 | Milestone: LLRF (FAT) Installation & Integration Complete | 0 d | 0% | 2017-12-26 | 2017-12-26 |  |  |  |  | 2017-12-26 |  | FY18Q1
148 | Burke | Burke | Cornell | A1.06.02.01.02.02.07 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets - Quads - Procurement complete | 0 d | 0% | 2017-12-27 | 2017-12-27 |  |  |  |  | 2017-12-27 |  | FY18Q1
113 | Fumata | Quigley | Cornell | A1.04.04.02.01.05 |  | A1.04 - RF Systems | T-2 | Milestone: 5 Remaining Solid State Amplifiers (SSA) Received @ Cornell (by end of Dec) | 0 d | 0% | 2017-12-29 | 2017-12-29 |  |  |  |  | 2017-12-29 |  | FY18Q1
564 | Fumata | Quigley | Cornell | A1.04.04.02.01.09 |  | A1.04 - RF Systems | T-3 | Milestone: All RF Amplifier Procurements Received and Complete | 0 d | 0% | 2017-12-29 | 2017-12-29 |  |  |  |  | 2017-12-29 |  | FY18Q1
6 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.02.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): First Arc Production Magnet Tested | 0 d | 0% | 2017-12-31 | 2017-12-31 |  |  |  |  | 2017-12-31 |  | FY18Q1
745 | Widger | Ray | Cornell | A1.13.02.02.02.03 |  | A1.13 - Safety | T-3 | Milestone: (FAT) Safety Procurements Received | 0 d | 0% | 2018-01-02 | 2018-01-02 |  |  |  |  | 2018-01-02 |  | FY18Q2
167 | Dobbins | Dobbins | Cornell | A1.08.04.02.04.02 |  | A1.08 - Controls | T-2 | Milestone: All EPICS Alarm Handler - Testing Complete | 0 d | 0% | 2018-01-03 | 2018-01-03 |  |  |  |  | 2018-01-03 |  | FY18Q2
147 | Burke | Burke | Cornell | A1.06.02.01.01.02.07 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets - Dipoles - Procurement complete | 0 d | 0% | 2018-01-05 | 2018-01-05 |  |  |  |  | 2018-01-05 |  | FY18Q2
205 | Gallagher | Gallagher | Cornell | A1.11.01.04.02.01 |  | A1.11 - System Integration | T-2 | Milestone: Rack specifications finalized/designed (by 12/31/17 for entire system - SPBT/4PBT) - | 0 d | 0% | 2018-01-09 | 2018-01-09 |  |  |  |  | 2018-01-09 |  | FY18Q2
714 | Gallagher | Gallagher | Cornell | A1.11.01.04.10.04 |  | A1.11 - System Integration | T-3 | Milestone: Compressed Air System Installation Complete | 0 d | 0% | 2018-01-10 | 2018-01-10 |  |  |  |  | 2018-01-10 |  | FY18Q2
598 | Burke | Burke | Cornell | A1.06.01.01.01.05.01.08 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Supporting Hardware - Assembly complete for FAT | 0 d | 0% | 2018-01-11 | 2018-01-11 |  |  |  |  | 2018-01-11 |  | FY18Q2
602 | Burke | Burke | Cornell | A1.06.01.02.01.04.12 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Procurements complete (FAT) | 0 d | 0% | 2018-01-18 | 2018-01-18 |  |  |  |  | 2018-01-18 |  | FY18Q2
201 | Gallagher | Gallagher | Cornell | A1.11.01.03.01.04.04 |  | A1.11 - System Integration | T-2 | Milestone: East RF System Relocation Complete | 0 d | 0% | 2018-01-19 | 2018-01-19 |  |  |  |  | 2018-01-19 |  | FY18Q2
647 | Dobbins | Dobbins | Cornell | A1.08.07.04.06 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for (FAT) Test | 0 d | 0% | 2018-01-23 | 2018-01-23 |  |  |  |  | 2018-01-23 |  | FY18Q2
754 | Widger | Ray | Cornell | A1.13.03.02.02.04 |  | A1.13 - Safety | T-3 | Milestone: (FAT) Radiation Monitoring Procurements Received | 0 d | 0% | 2018-01-23 | 2018-01-23 |  |  |  |  | 2018-01-23 |  | FY18Q2
665 | Dobbins | Dobbins | Cornell | A1.09.02.02.06 |  | A1.09 - Instrumentation | T-3 | Milestone: 1st Article - V301 Digital Boards Received (Qty: xx [BNL]) (5 mths after order placement??) | 0 d | 0% | 2018-01-24 | 2018-01-24 |  |  |  |  | 2018-01-24 |  | FY18Q2
671 | Dobbins | Dobbins | Cornell | A1.09.04.02.04 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Loss Monitor Procurements Complete | 0 d | 0% | 2018-01-24 | 2018-01-24 |  |  |  |  | 2018-01-24 |  | FY18Q2
530 | Gulliford | Cultrera | Cornell | A1.03.03.01.02 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All Procurements Received - Cathode Material | 0 d | 0% | 2018-01-25 | 2018-01-25 |  |  |  |  | 2018-01-25 |  | FY18Q2
582 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.08 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - 1st Article Table Top plate Procurement complete and received @ BNL | 0 d | 0% | 2018-01-25 | 2018-01-25 |  |  |  |  | 2018-01-25 |  | FY18Q2
584 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.10 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - 1st Article Frame/Stand Procurements complete and received @ Cornell in time for FAT | 0 d | 0% | 2018-01-25 | 2018-01-25 |  |  |  |  | 2018-01-31 |  | FY18Q2
141 | Burke | Burke | Cornell | A1.06.01.01.01.05.02.03 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Magnets & Hardware - Pre-Table Installation Complete (FAT) | 0 d | 0% | 2018-01-26 | 2018-01-26 |  |  |  |  | 2018-01-26 |  | FY18Q2
574 | Fumata | Sabol | Cornell | A1.04.05.02.02.02.08 |  | A1.04 - RF Systems | T-3 | Milestone: Pump Skid #2-3-4 - All Procurement Materials Received and Ready for Installation | 0 d | 0% | 2018-01-30 | 2018-01-30 |  |  |  |  | 2018-01-30 |  | FY18Q2
650 | Dobbins | Dobbins | Cornell | A1.08.08.02.03 |  | A1.08 - Controls | T-3 | Milestone: All Machine Protection System Procurements Complete | 0 d | 0% | 2018-02-01 | 2018-02-01 |  |  |  |  | 2018-02-01 |  | FY18Q2
189 | Dobbins | Dobbins | Cornell | A1.09.05.06.03.02 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Stops Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-02-05 | 2018-02-05 |  |  |  |  | 2018-02-05 |  | FY18Q2
658 | Dobbins | Dobbins | Cornell | A1.08.09.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: Fractional Arc Test - Controls EPICS Integration complete | 0 d | 0% | 2018-02-07 | 2018-02-07 |  |  |  |  | 2018-02-07 |  | FY18Q2
541 | Gulliford | Gulliford | Cornell | A1.03.05.01.02.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 DL - Cross Pipe Layout & Drawings Complete | 0 d | 0% | 2018-02-08 | 2018-02-08 |  |  |  |  | 2018-02-08 |  | FY18Q2
712 | Gallagher | Gallagher | Cornell | A1.11.01.04.09.01.05 |  | A1.11 - System Integration | T-3 | Milestone: Electrical System Design Complete | 0 d | 0% | 2018-02-08 | 2018-02-08 |  |  |  |  | 2018-02-08 |  | FY18Q2
715 | Gallagher | Gallagher | Cornell | A1.11.01.04.11.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Design of HVAC Upgrade Complete | 0 d | 0% | 2018-02-08 | 2018-02-08 |  |  |  |  | 2018-02-08 |  | FY18Q2
599 | Burke | Burke | Cornell | A1.06.01.01.01.05.01.09 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Supporting Hardware - Assembly complete for SPBT and 4PBT | 0 d | 0% | 2018-02-09 | 2018-02-09 |  |  |  |  | 2018-02-09 |  | FY18Q2
170 | Dobbins | Michnoff | BNL | A1.08.05.02.05 |  | A1.08 - Controls | T-2 | Milestone: EPICS device support - BAM - Testing Complete | 0 d | 0% | 2018-02-14 | 2018-02-14 |  |  |  |  | 2018-02-14 |  | FY18Q2
190 | Dobbins | Dobbins | Cornell | A1.09.05.07.02.01.07 |  | A1.09 - Instrumentation | T-2 | Milestone: FAT - Instrumentation System Testing Complete | 0 d | 0% | 2018-02-20 | 2018-02-20 |  |  |  |  | 2018-02-20 |  | FY18Q2
114 | Fumata | Quigley | Cornell | A1.04.04.03.11 |  | A1.04 - RF Systems | T-2 | Milestone - RF Amplifier/Deflector RF Cavity System Installation Complete | 0 d | 0% | 2018-02-21 | 2018-02-21 |  |  |  |  | 2018-02-21 |  | FY18Q2
604 | Burke | Burke | Cornell | A1.06.01.02.01.05.09 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Pre-Assembly complete (FAT) | 0 d | 0% | 2018-02-21 | 2018-02-21 |  |  |  |  | 2018-02-21 |  | FY18Q2
180 | Dobbins | Dobbins | Cornell | A1.08.09.02.02.01.01.16 |  | A1.08 - Controls | T-2 | Milestone: Fractional Arc Test - Integrated pre-beam testing for all Controls System Complete | 0 d | 0% | 2018-02-22 | 2018-02-22 |  |  |  |  | 2018-02-22 |  | FY18Q2
651 | Dobbins | Dobbins | Cornell | A1.08.08.03.01.04 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System Assembly/Development and initial testing complete (FAT) | 0 d | 0% | 2018-02-23 | 2018-02-23 |  |  |  |  | 2018-02-23 |  | FY18Q2
708 | Gallagher | Gallagher | Cornell | A1.11.01.04.06.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All Mezzanine Procurements Complete | 0 d | 0% | 2018-02-23 | 2018-02-23 |  |  |  |  | 2018-02-23 |  | FY18Q2
586 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.04.03 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Magnets - Pre-Girder Halbach Magnet Assembly 1st Article tests & documentation complete | 0 d | 0% | 2018-02-26 | 2018-02-26 |  |  |  |  | 2018-02-26 |  | FY18Q2
142 | Burke | Burke | Cornell | A1.06.01.01.01.05.02.04 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets - Magnets & Hardware - Pre-Table Installation Compete (SPBT & 4PBT) | 0 d | 0% | 2018-03-05 | 2018-03-05 |  |  |  |  | 2018-03-05 |  | FY18Q2
659 | Dobbins | Dobbins | Cornell | A1.08.09.02.02.01.02.16 |  | A1.08 - Controls | T-3 | Milestone: Controls - Fractional Arc Test - Commissioning with Beam for all Controls System Complete | 0 d | 0% | 2018-03-08 | 2018-03-08 |  |  |  |  | 2018-03-08 |  | FY18Q2
617 | Burke | Burke | Cornell | A1.06.02.03.01.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Extraction Line Magnets and Tables - Assembly (SPBT) - All Material available for Installation | 0 d | 0% | 2018-03-09 | 2018-03-09 |  |  |  |  | 2018-03-09 |  | FY18Q2
207 | Gallagher | Gallagher | Cornell | A1.11.01.04.07.03.03 |  | A1.11 - System Integration | T-2 | Milestone: East Wall Modifications (Penetrations) Complete | 0 d | 0% | 2018-03-09 | 2018-03-09 |  |  |  |  | 2018-03-09 |  | FY18Q2
603 | Burke | Burke | Cornell | A1.06.01.02.01.04.13 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Procurements complete (SPBT & 4PBT) | 0 d | 0% | 2018-03-12 | 2018-03-12 |  |  |  |  | 2018-03-12 |  | FY18Q2
178 | Dobbins | Dobbins | Cornell | A1.08.08.04.06 |  | A1.08 - Controls | T-2 | Milestone: Machine Protection System - Installation and Testing - complete and ready for (FAT) Test | 0 d | 0% | 2018-03-13 | 2018-03-13 |  |  |  |  | 2018-03-13 |  | FY18Q2
755 | Widger | Widger | Cornell | A1.13.03.02.03.07 |  | A1.13 - Safety | T-3 | Milestone: Radiation Monitor Safety process for FAT Relocate Complete (Link to Commissioning of beam directly) | 0 d | 0% | 2018-03-13 | 2018-03-13 |  |  |  |  | 2018-03-13 |  | FY18Q2
575 | Fumata | Sabol | Cornell | A1.04.05.02.02.03.08.02 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Pump Skid #2-3-4 - Vibration Mitigation Complete | 0 d | 0% | 2018-03-15 | 2018-03-15 |  |  |  |  | 2018-03-15 |  | FY18Q2
594 | Burke | Burke | Cornell | A1.06.01.01.01.02.02.06 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Common Magnets - Procurement Complete | 0 d | 0% | 2018-03-21 | 2018-03-21 |  |  |  |  | 2018-03-21 |  | FY18Q2
606 | Burke | Burke | Cornell | A1.06.01.03.01.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets and Tables - Assembly (FAT) - All Material available for Installation (1/8th magnets + 2 tables) | 0 d | 0% | 2018-03-21 | 2018-03-21 |  |  |  |  | 2018-03-21 |  | FY18Q2
117 | Fumata | Sabol | Cornell | A1.04.05.02.02.03.10 |  | A1.04 - RF Systems | T-2 | Milestone: MLC Pump Skid #2-3-4 - Installation Complete | 0 d | 0% | 2018-03-22 | 2018-03-22 |  |  |  |  | 2018-03-22 |  | FY18Q2
746 | Widger | Ray | Cornell | A1.13.02.02.03.08 |  | A1.13 - Safety | T-3 | Milestone: Safety process complete for (FAT) Test | 0 d | 0% | 2018-03-22 | 2018-03-22 |  |  |  |  | 2018-03-22 |  | FY18Q2
129 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.12 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Girders Procurements complete | 0 d | 0% | 2018-03-23 | 2018-03-23 |  |  |  |  | 2018-03-23 |  | FY18Q2
583 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.09 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - ALL Top plate Procurement complete and received @ BNL | 0 d | 0% | 2018-03-23 | 2018-03-23 |  |  |  |  | 2018-03-23 |  | FY18Q2
585 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.02.11 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Production FFAG Girders - ALL Frame/Stand Procurements complete and received @ Cornell | 0 d | 0% | 2018-03-23 | 2018-03-23 |  |  |  |  | 2018-03-23 |  | FY18Q2
686 | Dobbins | Dobbins | Cornell | A1.09.05.07.02.02.03 |  | A1.09 - Instrumentation | T-3 | Milestone: FAT - Instrumentation Commissioning with Beam Complete | 0 d | 0% | 2018-03-27 | 2018-03-27 |  |  |  |  | 2018-03-27 |  | FY18Q2
589 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.03 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: FFAG Straight Vacuum Chambers Received from Cornell for Production Magnet Assembly (Remainder) | 0 d | 0% | 2018-03-28 | 2018-03-28 |  |  |  |  | 2018-03-28 |  | FY18Q2
159 | Barley | Barley | Cornell | A1.07.04.02.08 |  | A1.07 - Power Supplies | T-2 | Milestone: All FFAG Corrector PS Procurement Received | 0 d | 0% | 2018-03-28 | 2018-03-28 |  |  |  |  | 2018-03-28 |  | FY18Q2
544 | Gulliford | Gulliford | Cornell | A1.03.05.02.03.03 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: All B2 DL Cross Pipe Materials Received | 0 d | 0% | 2018-03-30 | 2018-03-30 |  |  |  |  | 2018-03-30 |  | FY18Q2
232 | Widger | Heltsely | Cornell | A1.13.01.03.06 |  | A1.13 - Safety | T-2 | Milestone: x-Ray Permit for Fractional Arc Test Approved | 0 d | 0% | 2018-03-30 | 2018-03-30 |  |  |  |  | 2018-03-30 |  | FY18Q2
553 | Fumata | Quigley | Cornell | A1.04.01.03.01.04 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #2A - Ready for RF Power | 0 d | 0% | 2018-04-02 | 2018-04-02 |  |  |  |  | 2018-04-02 |  | FY18Q3
196 | Li | Li | Cornell | A1.10.04.03.09 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc Assemblies Complete for FAT Test | 0 d | 0% | 2018-04-03 | 2018-04-03 |  |  |  |  | 2017-12-20 |  | FY18Q3
188 | Dobbins | Dobbins | Cornell | A1.09.05.05.02.05 |  | A1.09 - Instrumentation | T-2 | Milestone: All View Screen Procurements Complete | 0 d | 0% | 2018-04-04 | 2018-04-04 |  |  |  |  | 2018-01-15 |  | FY18Q3
702 | Gallagher | Gallagher | Cornell | A1.11.01.04.03.01.03 |  | A1.11 - System Integration | T-3 | Milestone: All Survey & Alignment Procurements Complete | 0 d | 0% | 2018-04-06 | 2018-04-06 |  |  |  |  | 2018-01-07 |  | FY18Q3
710 | Gallagher | Gallagher | Cornell | A1.11.01.04.08.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Water Cooling System Design Complete | 0 d | 0% | 2018-04-06 | 2018-04-06 |  |  |  |  | 2018-04-06 |  | FY18Q3
717 | Gallagher | Gallagher | Cornell | A1.11.01.04.12.01.03 |  | A1.11 - System Integration | T-3 | Milestone: Network and IT Requirements Complete | 0 d | 0% | 2018-04-06 | 2018-04-06 |  |  |  |  | 2018-04-06 |  | FY18Q3
546 | Gulliford | Gulliford | Cornell | A1.03.05.03.02.04 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: B2 Diagnostic Beam Line (FY18) Installation Complete | 0 d | 0% | 2018-04-10 | 2018-04-10 |  |  |  |  | 2018-03-01 |  | FY18Q3
587 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.01 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: Vacuum Chambers Received from Cornell for Production Magnet Assembly (1st Article) - FAGD1 | 0 d | 0% | 2018-04-10 | 2018-04-10 |  |  |  |  | 2018-01-05 |  | FY18Q3
595 | Burke | Burke | Cornell | A1.06.01.01.01.03.02.06 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Septa Magnets - Procurement complete | 0 d | 0% | 2018-04-12 | 2018-04-12 |  |  |  |  | 2018-04-12 |  | FY18Q3
183 | Dobbins | Dobbins | Cornell | A1.09.02.03.07 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Arrival Monitors Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-04-12 | 2018-04-12 |  |  |  |  | 2018-04-12 |  | FY18Q3
109 | Fumata | Quigley | Cornell | A1.04.01.03.01.05 |  | A1.04 - RF Systems | T-2 | Milestone: MLC Cool Down #2A - RF Power Turned On and MLC System Stable | 0 d | 0% | 2018-04-16 | 2018-04-16 |  |  |  |  | 2018-04-16 |  | FY18Q3
151 | Burke | Burke | Cornell | A1.06.02.03.01.06 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Extraction Line Magnets and Tables - Assembly (SPBT) - Complete | 0 d | 0% | 2018-04-18 | 2018-04-18 |  |  |  |  | 2018-04-18 |  | FY18Q3
160 | Barley | Barley | Cornell | A1.07.04.03.03.03 |  | A1.07 - Power Supplies | T-2 | Milestone: FFAG Corrector Power Supplies ready for System Integration (FAT) | 0 d | 0% | 2018-04-25 | 2018-04-25 |  |  |  |  | 2018-02-01 |  | FY18Q3
137 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.16 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - 2nd Batch Delivered to Cornell (Sector-RX - Northwest) 4/20/18 | 0 d | 0% | 2018-04-26 | 2018-04-26 |  |  |  |  | 2018-04-26 |  | FY18Q3
7 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.02.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Fractional Arc Test: Beam through MLC & Prototype Girder | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | 2018-04-30 |  | FY18Q3
533 | Gulliford | Cultera | Cornell | A1.03.03.02.03.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: SPBT Cathode Material Available @ Cornell | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | 2018-04-30 |  | FY18Q3
153 | Barley | Barley | Cornell | A1.07.01.03.03.05 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Dipole Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | 2018-04-30 |  | FY18Q3
155 | Barley | Barley | Cornell | A1.07.02.03.03.05 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Quadrupole Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-04-30 | 2018-04-30 |  |  |  |  | 2018-04-30 |  | FY18Q3
157 | Barley | Barley | Cornell | A1.07.03.03.03.05 |  | A1.07 - Power Supplies | T-2 | Milestone: Splitter Corrector Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-05-01 | 2018-05-01 |  |  |  |  | 2018-05-01 |  | FY18Q3
713 | Gallagher | Gallagher | Cornell | A1.11.01.04.09.02.03 |  | A1.11 - System Integration | T-3 | Milestone: All Electrical System Procurements Complete | 0 d | 0% | 2018-05-04 | 2018-05-04 |  |  |  |  | 2018-05-04 |  | FY18Q3
718 | Gallagher | Gallagher | Cornell | A1.11.01.04.12.02.02 |  | A1.11 - System Integration | T-3 | Milestone: All Network and IT Support Procurements Complete | 0 d | 0% | 2018-05-04 | 2018-05-04 |  |  |  |  | 2018-05-04 |  | FY18Q3
195 | Li | Li | Cornell | A1.10.04.02.06 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc System - All Procurements complete | 0 d | 0% | 2018-05-08 | 2018-05-08 |  |  |  |  | 2018-05-08 |  | FY18Q3
571 | Fumata | Sabol | Cornell | A1.04.05.02.01.03.09.04 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Pump Skid #1 - Vibration Mitigation Complete | 0 d | 0% | 2018-05-09 | 2018-05-09 |  |  |  |  | 2018-05-09 |  | FY18Q3
572 | Fumata | Sabol | Cornell | A1.04.05.02.01.03.10 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Pump Skid#1 Installation Complete | 0 d | 0% | 2018-05-09 | 2018-05-09 |  |  |  |  | 2018-05-09 |  | FY18Q3
197 | Li | Li | Cornell | A1.10.04.03.10 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Vacuum FFAG Arc Assemblies Complete for SPBT/Remainder | 0 d | 0% | 2018-05-11 | 2018-05-11 |  |  |  |  | 2018-05-11 |  | FY18Q3
588 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.02 |  | A1.05 - FFAG Magnets & Girders | T-3 | Milestone: FFAG Arc&Transition Vacuum Chambers Received from Cornell for Production Magnet Assembly (Remainder) (Multiple shipments per diagram on Yulins layout) | 0 d | 0% | 2018-05-18 | 2018-05-18 |  |  |  |  | 2018-05-18 |  | FY18Q3
709 | Gallagher | Gallagher | Cornell | A1.11.01.04.06.03.02 |  | A1.11 - System Integration | T-3 | Milestone: Mezzanine Installation Complete | 0 d | 0% | 2018-05-18 | 2018-05-18 |  |  |  |  | 2018-05-18 |  | FY18Q3
643 | Dobbins | Dobbins | Cornell | A1.08.06.01.01.02 |  | A1.08 - Controls | T-3 | Milestone: Orbit Correction - Requirements definition complete | 0 d | 0% | 2018-05-25 | 2018-05-25 |  |  |  |  | 2018-05-25 |  | FY18Q3
689 | Li | Li | Cornell | A1.10.01.03.04 |  | A1.10 - Vacuum Systems | T-3 | Milestone: Global Vacuum System - All assembly/support complete | 0 d | 0% | 2018-05-25 | 2018-05-25 |  |  |  |  | 2018-05-25 |  | FY18Q3
605 | Burke | Burke | Cornell | A1.06.01.02.01.05.10 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets - Table Support Hardware - Pre-Assembly complete (SPBT & 4PBT) | 0 d | 0% | 2018-05-30 | 2018-05-30 |  |  |  |  | 2018-05-30 |  | FY18Q3
111 | Fumata | Quigley | Cornell | A1.04.03.01.02.03 |  | A1.04 - RF Systems | T-2 | Milestone: SPBT - LLRF Design Updates Complete | 0 d | 0% | 2018-06-04 | 2018-06-04 |  |  |  |  | 2018-06-04 |  | FY18Q3
716 | Gallagher | Gallagher | Cornell | A1.11.01.04.11.04 |  | A1.11 - System Integration | T-3 | Milestone: Environmental Controls Installation Complete | 0 d | 0% | 2018-06-04 | 2018-06-04 |  |  |  |  | 2018-06-04 |  | FY18Q3
144 | Burke | Burke | Cornell | A1.06.01.03.01.08 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets and Tables - Assembly (FAT) - Complete | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-02-01 |  | FY18Q3
607 | Burke | Burke | Cornell | A1.06.01.03.02.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets and Tables - Assembly (SPBT) - All Material available for Installation (? magnets + 2 tables) | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 |  | FY18Q3
648 | Dobbins | Dobbins | Cornell | A1.08.07.04.09 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for SPBT | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 |  | FY18Q3
673 | Dobbins | Dobbins | Cornell | A1.09.05.01.03.03 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM - DAQ Board Design Complete | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 |  | FY18Q3
675 | Dobbins | Dobbins | Cornell | A1.09.05.01.03.09 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM Clock Distribution Design Complete (SPBT) | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 |  | FY18Q3
193 | Li | Li | Cornell | A1.10.01.02.06 |  | A1.10 - Vacuum Systems | T-2 | Milestone: Global Vacuum System - Procurements complete | 0 d | 0% | 2018-06-11 | 2018-06-11 |  |  |  |  | 2018-06-11 |  | FY18Q3
138 | Burke | Burke | Cornell | A1.06.01.01.01.01.02.21 |  | A1.06 - Splitter Magnets | T-2(3?) | Milestone: Splitter Magnets (Dipoles-Quads-Correctors) - ALL Procurements complete | 0 d | 0% | 2018-06-14 | 2018-06-14 |  |  |  |  | 2018-06-14 |  | FY18Q3
666 | Dobbins | Dobbins | Cornell | A1.09.02.02.08 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Arrival Monitor Procurements Complete | 0 d | 0% | 2018-06-15 | 2018-06-15 |  |  |  |  | 2018-06-15 |  | FY18Q3
669 | Dobbins | Dobbins | Cornell | A1.09.03.02.05 |  | A1.09 - Instrumentation | T-3 | Milestone: All Beam Current Monitor Procurements Complete | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 |  | FY18Q3
726 | Gallagher | Gallagher | Cornell | A1.11.02.04.01.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (FAT): East Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-02-01 |  | FY18Q3
728 | Gallagher | Gallagher | Cornell | A1.11.02.04.02.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (SPBT-4PBT): East Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 |  | FY18Q3
730 | Gallagher | Gallagher | Cornell | A1.11.02.05.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 04-TA: South Southeast arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 |  | FY18Q3
732 | Gallagher | Gallagher | Cornell | A1.11.02.06.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 05-ZA: Southeast straight Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 |  | FY18Q3
734 | Gallagher | Gallagher | Cornell | A1.11.02.07.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 06-ZB: Southwest straight Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 |  | FY18Q3
736 | Gallagher | Gallagher | Cornell | A1.11.02.08.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 07-TB: Southwest Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 |  | FY18Q3
738 | Gallagher | Gallagher | Cornell | A1.11.02.09.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 08-FB: West Arc Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 |  | FY18Q3
739 | Gallagher | Gallagher | Cornell | A1.11.02.10.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 09-RX: Northwest Splitter Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 |  | FY18Q3
740 | Gallagher | Gallagher | Cornell | A1.11.02.11.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 10-BS: Beam stop Ready for System Integration | 0 d | 0% | 2018-06-22 | 2018-06-22 |  |  |  |  | 2018-06-22 |  | FY18Q3
126 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.01.03.04 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Vendor Procurement [BNL]: Production FFAG Magnets - Permanent Magnet Blocks -All Lots Received @ BNL | 0 d | 0% | 2018-06-25 | 2018-06-25 |  |  |  |  | 2018-06-25 |  | FY18Q3
644 | Dobbins | Dobbins | Cornell | A1.08.06.01.01.04 |  | A1.08 - Controls | T-3 | Milestone: Orbit Correction - Software design complete | 0 d | 0% | 2018-06-25 | 2018-06-25 |  |  |  |  | 2018-06-25 |  | FY18Q3
198 | Gallagher | Gallagher | Cornell | A1.11.01.01.01.06 |  | A1.11 - System Integration | T-2 | Milestone: CESR 2018 CHESS-U Commissioning/Startup | 0 d | 0% | 2018-06-27 | 2018-06-27 |  |  |  |  | 2018-06-27 |  | FY18Q3
722 | Gallagher | Gallagher | Cornell | A1.11.02.03.01.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 02-SX (FAT) Northeast Splitter Ready for System Integration | 0 d | 0% | 2018-06-29 | 2018-06-29 |  |  |  |  | 2018-02-01 |  | FY18Q3
703 | Gallagher | Gallagher | Cornell | A1.11.01.04.03.02.03 |  | A1.11 - System Integration | T-3 | Milestone: Survey and alignment - Reference system Complete | 0 d | 0% | 2018-07-02 | 2018-07-02 |  |  |  |  | 2018-07-02 |  | FY18Q4
724 | Gallagher | Gallagher | Cornell | A1.11.02.03.03.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 02-SX (4PBT): Northeast Splitter Ready for System Integration | 0 d | 0% | 2018-07-02 | 2018-07-02 |  |  |  |  | 2018-07-02 |  | FY18Q4
220 | Gallagher | Gallagher | Cornell | A1.11.02.09.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 08-FB: West Arc -System Integration Complete | 0 d | 0% | 2018-07-09 | 2018-07-09 |  |  |  |  | 2018-07-09 |  | FY18Q4
116 | Fumata | Quigley | Cornell | A1.04.04.04.02.02 |  | A1.04 - RF Systems | T-2 | Milestone: RF Systems Ready for SPBT | 0 d | 0% | 2018-07-10 | 2018-07-10 |  |  |  |  | 2018-07-10 |  | FY18Q4
230 | Widger | Kostroun | Cornell | A1.13.01.01.05 |  | A1.13 - Safety | T-2 | Milestone: Shielding Calculations/Physics Design Completed | 0 d | 0% | 2018-07-10 | 2018-07-10 |  |  |  |  | 2018-07-10 |  | FY18Q4
211 | Gallagher | Gallagher | Cornell | A1.11.02.03.01.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 02-SX (FAT) Northeast Splitter - System Integration Complete | 0 d | 0% | 2018-07-16 | 2018-07-16 |  |  |  |  | 2018-02-15 |  | FY18Q4
221 | Gallagher | Gallagher | Cornell | A1.11.02.10.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 09-RX: Northwest Splitter -System Integration Complete | 0 d | 0% | 2018-07-23 | 2018-07-23 |  |  |  |  | 2018-07-23 |  | FY18Q4
741 | Gallagher | Gallagher | Cornell | A1.11.02.11.03.06 |  | A1.11 - System Integration | T-3 | Milestone: Sector 10-BS: Beam stop - Installation Complete | 0 d | 0% | 2018-07-23 | 2018-07-23 |  |  |  |  | 2018-07-23 |  | FY18Q4
649 | Dobbins | Dobbins | Cornell | A1.08.07.04.12 |  | A1.08 - Controls | T-3 | Milestone: Timing System - complete and ready for 4PBT | 0 d | 0% | 2018-07-24 | 2018-07-24 |  |  |  |  | 2018-07-24 |  | FY18Q4
226 | Bartnik | Bartnik | Cornell | A1.12.04.05 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Fractional Arc Test - Commissioning Complete | 0 d | 0% | 2018-07-27 | 2018-07-27 |  |  |  |  | 2018-04-20 |  | FY18Q4
213 | Gallagher | Gallagher | Cornell | A1.11.02.03.03.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 02-SX (4PBT): Northeast Splitter -System Integration Complete | 0 d | 0% | 2018-07-31 | 2018-07-31 |  |  |  |  | 2018-07-31 |  | FY18Q4
719 | Gallagher | Gallagher | Cornell | A1.11.01.04.12.03.02 |  | A1.11 - System Integration | T-3 | Milestone: Network and IT Support items installed | 0 d | 0% | 2018-07-31 | 2018-07-31 |  |  |  |  | 2018-07-31 |  | FY18Q4
161 | Barley | Barley | Cornell | A1.07.04.03.03.04 |  | A1.07 - Power Supplies | T-2 | Milestone: FFAG Corrector Power Supplies ready for System Integration (SPBT) | 0 d | 0% | 2018-08-07 | 2018-08-07 |  |  |  |  | 2018-08-07 |  | FY18Q4
216 | Gallagher | Gallagher | Cornell | A1.11.02.05.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 04-TA: South Southeast arc -System Integration Complete | 0 d | 0% | 2018-08-10 | 2018-08-10 |  |  |  |  | 2018-08-10 |  | FY18Q4
145 | Burke | Burke | Cornell | A1.06.01.03.02.08 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets and Tables - Assembly (SPBT) - Complete | 0 d | 0% | 2018-08-15 | 2018-08-15 |  |  |  |  | 2018-08-15 |  | FY18Q4
608 | Burke | Burke | Cornell | A1.06.01.03.03.01 |  | A1.06 - Splitter Magnets | T-3 | Milestone: Splitter Magnets and Tables - Assembly (4PBT) - All Material available for Installation (3/4 of magnets - remaining) | 0 d | 0% | 2018-08-15 | 2018-08-15 |  |  |  |  | 2018-08-15 |  | FY18Q4
723 | Gallagher | Gallagher | Cornell | A1.11.02.03.02.03.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 02-SX (SPBT) - Northeast Splitter Ready for System Integration | 0 d | 0% | 2018-08-17 | 2018-08-17 |  |  |  |  | 2018-08-17 |  | FY18Q4
222 | Gallagher | Gallagher | Cornell | A1.11.02.11.04.07 |  | A1.11 - System Integration | T-2 | Milestone: Sector 10-BS: Beam stop - System Integration Complete | 0 d | 0% | 2018-08-20 | 2018-08-20 |  |  |  |  | 2018-08-20 |  | FY18Q4
172 | Dobbins | Dobbins | Cornell | A1.08.06.01.02.02 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - Software development complete | 0 d | 0% | 2018-08-21 | 2018-08-21 |  |  |  |  | 2018-08-21 |  | FY18Q4
187 | Dobbins | Michnoff | BNL | A1.09.05.03.02.03 |  | A1.09 - Instrumentation | T-2 | Milestone: BPM Assembly/Development - DAQ Electronics Complete and ready for Final testing | 0 d | 0% | 2018-08-21 | 2018-08-21 |  |  |  |  | 2018-08-21 |  | FY18Q4
185 | Dobbins | Dobbins | Cornell | A1.09.04.03.04 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Loss Monitors Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-08-27 | 2018-08-27 |  |  |  |  | 2018-08-27 |  | FY18Q4
561 | Fumata | Quigley | Cornell | A1.04.03.02.02.05 |  | A1.04 - RF Systems | T-3 | Milestone: All LLRF Material/Components (SPBT) Complete | 0 d | 0% | 2018-08-28 | 2018-08-28 |  |  |  |  | 2018-08-28 |  | FY18Q4
203 | Gallagher | Gallagher | Cornell | A1.11.01.03.03.03.03 |  | A1.11 - System Integration | T-2 | Milestone: CESR-85F Cooling System Relocation Complete | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 |  | FY18Q4
725 | Gallagher | Gallagher | Cornell | A1.11.02.04.01.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (FAT): East arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-02-01 |  | FY18Q4
727 | Gallagher | Gallagher | Cornell | A1.11.02.04.02.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 03-FA (SPBT-4PBT): East arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 |  | FY18Q4
729 | Gallagher | Gallagher | Cornell | A1.11.02.05.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 04-TA - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 |  | FY18Q4
731 | Gallagher | Gallagher | Cornell | A1.11.02.06.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 05-ZA - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 |  | FY18Q4
733 | Gallagher | Gallagher | Cornell | A1.11.02.07.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 06-ZB - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 |  | FY18Q4
735 | Gallagher | Gallagher | Cornell | A1.11.02.08.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 07-TB - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 |  | FY18Q4
737 | Gallagher | Gallagher | Cornell | A1.11.02.09.02.01 |  | A1.11 - System Integration | T-3 | Milestone: Sector 07-TB - South Southeast arc Ready for System Installation | 0 d | 0% | 2018-08-29 | 2018-08-29 |  |  |  |  | 2018-08-29 |  | FY18Q4
212 | Gallagher | Gallagher | Cornell | A1.11.02.03.02.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 02-SX (SPBT) - Northeast Splitter - System Integration Complete | 0 d | 0% | 2018-09-17 | 2018-09-17 |  |  |  |  | 2018-09-17 |  | FY18Q4
214 | Gallagher | Gallagher | Cornell | A1.11.02.04.01.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 03-FA (FAT): East Arc -System Integration Complete | 0 d | 0% | 2018-09-18 | 2018-09-18 |  |  |  |  | 2018-02-15 |  | FY18Q4
215 | Gallagher | Gallagher | Cornell | A1.11.02.04.02.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 03-FA (SPBT-4PBT): East Arc -System Integration Complete | 0 d | 0% | 2018-09-18 | 2018-09-18 |  |  |  |  | 2018-09-18 |  | FY18Q4
173 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.01.03 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - SPBT hardware installation complete | 0 d | 0% | 2018-09-19 | 2018-09-19 |  |  |  |  | 2018-09-19 |  | FY18Q4
563 | Fumata | Quigley | Cornell | A1.04.03.03.02.05 |  | A1.04 - RF Systems | T-3 | Milestone: LLRF (SPBT) Installation & Integration Complete | 0 d | 0% | 2018-09-26 | 2018-09-26 |  |  |  |  | 2018-09-26 |  | FY18Q4
104 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.02.01 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Design optics for two, three, and four ERL loops finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 |  | FY18Q4
105 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.02.03 |  | A1.02 - Accelerator Physics | T-2 | Milestone: Tracking of beam through full loops and check acceptance at dump complete | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 |  | FY18Q4
515 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.01.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY18 - Complete | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 |  | FY18Q4
518 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design optics for one ERL turn through splitter and FFAG finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 |  | FY18Q4
519 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.05 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design dump line for maximal energy spread and track beam finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 |  | FY18Q4
520 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.02.02.06 |  | A1.02 - Accelerator Physics | T-3 | Milestone: (SPB) Simulation of beam-loss scenarios, including ions, Touschek, wakes, etc. complete | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 |  | FY18Q4
522 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.02.02 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Design of orbit correction for two, three, and four ERL loops finalized | 0 d | 0% | 2018-09-28 | 2018-09-28 |  |  |  |  | 2018-09-28 |  | FY18Q4
677 | Dobbins | Dobbins | Cornell | A1.09.05.02.02.05 |  | A1.09 - Instrumentation | T-3 | Milestone: All BPM Clock Distribution Procurements Complete | 0 d | 0% | 2018-10-03 | 2018-10-03 |  |  |  |  | 2018-10-03 |  | FY19Q1
678 | Dobbins | Dobbins | Cornell | A1.09.05.03.03.04 |  | A1.09 - Instrumentation | T-3 | Milestone: BPM Assembly/Development - BPM Clock Complete and ready for Final testing | 0 d | 0% | 2018-10-03 | 2018-10-03 |  |  |  |  | 2018-10-03 |  | FY19Q1
146 | Burke | Burke | Cornell | A1.06.01.03.03.08 |  | A1.06 - Splitter Magnets | T-2 | Milestone: Splitter Magnets and Tables - Assembly (4PBT) - Complete | 0 d | 0% | 2018-10-04 | 2018-10-04 |  |  |  |  | 2018-10-04 |  | FY19Q1
217 | Gallagher | Gallagher | Cornell | A1.11.02.06.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 05-ZA: Southeast straight -System Integration Complete | 0 d | 0% | 2018-10-09 | 2018-10-09 |  |  |  |  | 2018-10-09 |  | FY19Q1
204 | Gallagher | Gallagher | Cornell | A1.11.01.04.01.07 |  | A1.11 - System Integration | T-2 | Milestone: CBETA Global Layout Plans Complete | 0 d | 0% | 2018-10-18 | 2018-10-18 |  |  |  |  | 2018-10-18 |  | FY19Q1
208 | Gallagher | Gallagher | Cornell | A1.11.01.04.09.03.02 |  | A1.11 - System Integration | T-2 | Milestone: Electrical System Installation Complete | 0 d | 0% | 2018-10-25 | 2018-10-25 |  |  |  |  | 2018-10-25 |  | FY19Q1
756 | Widger | Widger | Cornell | A1.13.03.03.01.03 |  | A1.13 - Safety | T-3 | Milestone: SPBT - Design radiation monitor system Complete/Approved | 0 d | 0% | 2018-10-29 | 2018-10-29 |  |  |  |  | 2018-10-29 |  | FY19Q1
747 | Widger | Ray | Cornell | A1.13.02.03.01.04 |  | A1.13 - Safety | T-3 | Milestone: (SPBT) Design approved by safety committee | 0 d | 0% | 2018-11-21 | 2018-11-21 |  |  |  |  | 2018-11-21 |  | FY19Q1
127 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.01.07.04 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets Halbach Magnets Assembly (Magnet, Housing, Windowframe Corrector) - ALL Sectors Received @ BNL [Qty: xx] | 0 d | 0% | 2018-11-27 | 2018-11-27 |  |  |  |  | 2018-11-27 |  | FY19Q1
128 | Tuozzolo | Tuozzolo | BNL | A1.05.02.02.01.08 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets ALL Procurements complete and received from vendor | 0 d | 0% | 2018-11-27 | 2018-11-27 |  |  |  |  | 2018-11-27 |  | FY19Q1
757 | Widger | Ray | Cornell | A1.13.03.03.02.03 |  | A1.13 - Safety | T-3 | Milestone: (SPBT) Radiation Monitoring Procurements Received | 0 d | 0% | 2018-11-29 | 2018-11-29 |  |  |  |  | 2018-11-29 |  | FY19Q1
8 | Smolenski/Michnoff | Tuozzolo | BNL | A1.01.01.03.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Girder Production Run Complete | 0 d | 0% | 2018-11-30 | 2018-11-30 |  |  |  |  | 2018-11-30 |  | FY19Q1
130 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.03 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: ALL Sectors - Measuring and adjusting Halbach Magnet Assemblies Complete [Qty: xx] | 0 d | 0% | 2018-12-04 | 2018-12-04 |  |  |  |  | 2018-12-04 |  | FY19Q1
218 | Gallagher | Gallagher | Cornell | A1.11.02.07.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 06-ZB: Southwest straight -System Integration Complete | 0 d | 0% | 2018-12-07 | 2018-12-07 |  |  |  |  | 2018-12-07 |  | FY19Q1
184 | Dobbins | Dobbins | Cornell | A1.09.03.03.04 |  | A1.09 - Instrumentation | T-2 | Milestone: Beam Current Monitors Assembly/Development Complete and ready for Final testing | 0 d | 0% | 2018-12-17 | 2018-12-17 |  |  |  |  | 2018-12-17 |  | FY19Q1
233 | Widger | Heltsely | Cornell | A1.13.01.04.04 |  | A1.13 - Safety | T-2 | Milestone: x-Ray permit for SPBT Approved (No additional permits needed for 4PBT) | 0 d | 0% | 2018-12-19 | 2018-12-19 |  |  |  |  | 2018-12-19 |  | FY19Q1
748 | Widger | Ray | Cornell | A1.13.02.03.02.03 |  | A1.13 - Safety | T-3 | Milestone: (SPBT) Safety Procurements Received | 0 d | 0% | 2018-12-21 | 2018-12-21 |  |  |  |  | 2018-12-21 |  | FY19Q1
131 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.04.02.07 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: ALL Sectors - Survey & Testing of Halbach Magnet Assemblies Complete [Qty: xx] | 0 d | 0% | 2019-01-04 | 2019-01-04 |  |  |  |  | 2019-01-04 |  | FY19Q2
652 | Dobbins | Dobbins | Cornell | A1.08.08.03.02.04 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System Assembly/Development and initial testing complete (SPBT) | 0 d | 0% | 2019-01-18 | 2019-01-18 |  |  |  |  | 2019-01-18 |  | FY19Q2
134 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.03.03.07 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets and Girders - ALL Sectors - Halbach Magnets & Girder Ship to Cornell complete | 0 d | 0% | 2019-01-24 | 2019-01-24 |  |  |  |  | 2019-01-24 |  | FY19Q2
209 | Gallagher | Gallagher | Cornell | A1.11.02.01.01 |  | A1.11 - System Integration | T-2 | Milestone: All BNL Magnets and Hardware Received for Installation in L0E | 0 d | 0% | 2019-01-24 | 2019-01-24 |  |  |  |  | 2019-01-24 |  | FY19Q2
219 | Gallagher | Gallagher | Cornell | A1.11.02.08.03.08 |  | A1.11 - System Integration | T-2 | Milestone: Sector 07-TB: Southwest Arc -System Integration Complete | 0 d | 0% | 2019-02-07 | 2019-02-07 |  |  |  |  | 2019-02-07 |  | FY19Q2
179 | Dobbins | Dobbins | Cornell | A1.08.08.04.09 |  | A1.08 - Controls | T-2 | Milestone: Machine Protection System - Installation and Testing - complete and ready for SPBT | 0 d | 0% | 2019-02-13 | 2019-02-13 |  |  |  |  | 2019-02-13 |  | FY19Q2
9 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.03.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Final Assembly & Pre-Beam Commissioning Complete | 0 d | 0% | 2019-02-28 | 2019-02-28 |  |  |  |  | 2019-02-28 |  | FY19Q2
133 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.02.04.02.07 |  | A1.05 - FFAG Magnets & Girders | T-2 | FFAG Production Magnets and Girders - ALL Sectors - ALL Halbach Magnet & Girder Assembly, Survey, Testing, and Documentation Complete [Qty: xx] | 0 d | 0% | 2019-03-08 | 2019-03-08 |  |  |  |  | 2019-03-08 |  | FY19Q2
132 | Tuozzolo | Tuozzolo | BNL | A1.05.02.03.01.01.04.04 |  | A1.05 - FFAG Magnets & Girders | T-2 | Milestone: Production FFAG Magnets - Pre-Girder Halbach Magnet Assembly tests & documentation complete | 0 d | 0% | 2019-03-12 | 2019-03-12 |  |  |  |  | 2019-03-12 |  | FY19Q2
676 | Dobbins | Dobbins | Cornell | A1.09.05.02.01.06 |  | A1.09 - Instrumentation | T-3 | Milestone: All DAQ Electronics Procurements Complete | 0 d | 0% | 2019-04-02 | 2019-04-02 |  |  |  |  | 2018-10-01 |  | FY19Q3
660 | Dobbins | Dobbins | Cornell | A1.08.09.03.01.16 |  | A1.08 - Controls | T-3 | Milestone: SPBT - Controls EPICS Integration complete | 0 d | 0% | 2019-04-03 | 2019-04-03 |  |  |  |  | 2018-12-31 |  | FY19Q3
110 | Fumata | Quigley | Cornell | A1.04.01.04.02.04 |  | A1.04 - RF Systems | T-2 | Milestone: MLC Cool Down #3 - RF Power Turned On and MLC System Stable | 0 d | 0% | 2019-04-15 | 2019-04-15 |  |  |  |  | 2019-04-15 |  | FY19Q3
554 | Fumata | Quigley | Cornell | A1.04.01.04.02.03 |  | A1.04 - RF Systems | T-3 | Milestone: MLC Cool Down #3 - Ready for RF Power | 0 d | 0% | 2019-04-15 | 2019-04-15 |  |  |  |  | 2019-04-15 |  | FY19Q3
704 | Gallagher | Gallagher | Cornell | A1.11.01.04.04.01.03 |  | A1.11 - System Integration | T-3 | Milestone: All New Shielding Wall & Blocks Procurements Complete | 0 d | 0% | 2019-04-16 | 2019-04-16 |  |  |  |  | 2019-04-16 |  | FY19Q3
711 | Gallagher | Gallagher | Cornell | A1.11.01.04.08.03.04 |  | A1.11 - System Integration | T-3 | Milestone: Water Cooling System Installation Complete | 0 d | 0% | 2019-04-23 | 2019-04-23 |  |  |  |  | 2019-04-23 |  | FY19Q3
749 | Widger | Ray | Cornell | A1.13.02.03.03.07 |  | A1.13 - Safety | T-3 | Milestone: Safety process complete for PSS (SPBT) | 0 d | 0% | 2019-04-26 | 2019-04-26 |  |  |  |  | 2018-02-01 |  | FY19Q3
661 | Dobbins | Dobbins | Cornell | A1.08.09.03.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: SPBT - Integrated pre-beam testing for all Controls System Complete | 0 d | 0% | 2019-05-01 | 2019-05-01 |  |  |  |  | 2019-01-20 |  | FY19Q3
174 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.01.06 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - SPBT - commissioning with beam complete | 0 d | 0% | 2019-05-08 | 2019-05-08 |  |  |  |  | 2019-03-10 |  | FY19Q3
181 | Dobbins | Dobbins | Cornell | A1.08.09.03.02.02.16 |  | A1.08 - Controls | T-2 | Milestone: Controls - SPBT - Commissioning with Beam for all Controls System Complete | 0 d | 0% | 2019-05-08 | 2019-05-08 |  |  |  |  | 2019-03-10 |  | FY19Q3
10 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.03.03 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Single Pass Beam Energy Scan | 0 d | 0% | 2019-06-30 | 2019-06-30 |  |  |  |  | 2019-06-30 |  | FY19Q3
534 | Gulliford | Cultera | Cornell | A1.03.03.02.04.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: SPBT-ER Cathode Material Available @ Cornell | 0 d | 0% | 2019-06-30 | 2019-06-30 |  |  |  |  | 2019-02-25 |  | FY19Q3
191 | Dobbins | Dobbins | Cornell | A1.09.05.07.03.01.08 |  | A1.09 - Instrumentation | T-2 | Milestone: SPBT - Instrumentation System Testing Complete | 0 d | 0% | 2019-07-10 | 2019-07-10 |  |  |  |  | 2019-01-20 |  | FY19Q4
662 | Dobbins | Dobbins | Cornell | A1.08.09.04.01.16 |  | A1.08 - Controls | T-3 | Milestone: 4PBT - Controls EPICS Integration complete | 0 d | 0% | 2019-08-26 | 2019-08-26 |  |  |  |  | 2019-08-01 |  | FY19Q4
687 | Dobbins | Dobbins | Cornell | A1.09.05.07.03.02.03 |  | A1.09 - Instrumentation | T-3 | Milestone: SPBT - Instrumentation Commissioning with Beam Complete | 0 d | 0% | 2019-09-05 | 2019-09-05 |  |  |  |  | 2019-03-10 |  | FY19Q4
227 | Bartnik | Bartnik | Cornell | A1.12.05.07 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Single Pass Energy Scan - Commissioning Complete | 0 d | 0% | 2019-09-19 | 2019-09-19 |  |  |  |  | 2019-04-30 | This needs to be done earlier than NYSDERA milestone schedule to allow early start of SPBT | FY19Q4
206 | Gallagher | Gallagher | Cornell | A1.11.01.04.04.02.03 |  | A1.11 - System Integration | T-2 | Milestone: Shielding Installation Complete | 0 d | 0% | 2019-10-04 | 2019-10-04 |  |  |  |  | 2019-02-15 |  | FY20Q1
521 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.03.01.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY19 - Complete | 0 d | 0% | 2019-10-07 | 2019-10-07 |  |  |  |  | 2019-10-07 |  | FY20Q1
175 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.02.01 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - 4PBT hardware installation complete | 0 d | 0% | 2019-10-07 | 2019-10-07 |  |  |  |  | 2019-08-01 |  | FY20Q1
720 | Gallagher | Gallagher | Cornell | A1.11.02.01.03 |  | A1.11 - System Integration | T-3 | Milestone: All Sectors - System Integration Complete | 0 d | 0% | 2019-10-07 | 2019-10-07 |  |  |  |  | 2019-01-31 |  | FY20Q1
524 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.04.02.01 |  | A1.02 - Accelerator Physics | T-3 | Milestone: (4PB) Simulation of beam-loss scenarios, including ions, Touschek, wakes, etc. complete | 0 d | 0% | 2019-10-16 | 2019-10-16 |  |  |  |  | 2019-10-16 |  | FY20Q1
11 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.04.01 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Single Pass Beam with Energy Recovery | 0 d | 0% | 2019-10-31 | 2019-10-31 |  |  |  |  | 2019-07-31 | This needs to be done early to allow reconfiguration for 4PBT and early 4PBT start | FY20Q1
535 | Gulliford | Cultera | Cornell | A1.03.03.02.05.01 |  | A1.03 - DC/Gun Injector | T-3 | Milestone: 4PBT Cathode Material Available @ Cornell | 0 d | 0% | 2019-10-31 | 2019-10-31 |  |  |  |  | 2019-10-31 |  | FY20Q1
663 | Dobbins | Dobbins | Cornell | A1.08.09.04.02.01.16 |  | A1.08 - Controls | T-3 | Milestone: 4PBT - Integrated pre-beam testing for all Controls System Complete | 0 d | 0% | 2019-11-14 | 2019-11-14 |  |  |  |  | 2019-08-01 |  | FY20Q1
654 | Dobbins | Dobbins | Cornell | A1.08.08.04.12 |  | A1.08 - Controls | T-3 | Milestone: Machine Protection System - Installation and Testing - complete and ready for 4PBT | 0 d | 0% | 2019-11-18 | 2019-11-18 |  |  |  |  | 2019-08-01 |  | FY20Q1
182 | Dobbins | Dobbins | Cornell | A1.08.09.04.02.02.16 |  | A1.08 - Controls | T-2 | Milestone: Controls - 4PBT - Commissioning with Beam for all Controls System Complete | 0 d | 0% | 2019-12-02 | 2019-12-02 |  |  |  |  | 2019-08-15 |  | FY20Q1
176 | Dobbins | Dobbins | Cornell | A1.08.06.01.03.02.04 |  | A1.08 - Controls | T-2 | Milestone: Orbit Correction - 4PBT - Commissioning with beam complete | 0 d | 0% | 2019-12-20 | 2019-12-20 |  |  |  |  | 2019-08-15 |  | FY20Q1
12 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.04.02 |  | A1.01 - Project Management | T-1 | Milestone (T-1): Four Pass Beam with Energy Recovery (Low Current) | 0 d | 0% | 2019-12-31 | 2019-12-31 |  |  |  |  | 2019-12-31 |  | FY20Q1
192 | Dobbins | Dobbins | Cornell | A1.09.05.07.04.01.07 |  | A1.09 - Instrumentation | T-2 | Milestone: 4PBT - Instrumentation System Testing Complete | 0 d | 0% | 2020-01-21 | 2020-01-21 |  |  |  |  | 2019-08-01 |  | FY20Q2
228 | Bartnik | Bartnik | Cornell | A1.12.06.05 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Single Pass Energy Recovery - Commissioning Complete | 0 d | 0% | 2020-02-04 | 2020-02-04 |  |  |  |  | 2019-07-31 |  | FY20Q2
688 | Dobbins | Dobbins | Cornell | A1.09.05.07.04.02.03 |  | A1.09 - Instrumentation | T-3 | Milestone: 4PBT - Instrumentation Commissioning with Beam Complete | 0 d | 0% | 2020-04-29 | 2020-04-29 |  |  |  |  | 2019-08-15 |  | FY20Q2
234 | Widger | Widger | Cornell | A1.13.04.01.09 |  | A1.13 - Safety | T-2 | Milestone: All Radiation Monitoring Procurements Received | 0 d | 0% | 2020-04-29 | 2020-04-29 |  |  |  |  | 2020-04-29 | This needs to be much earlier - need new date from Karl | FY20Q2
13 | Smolenski/Michnoff | Smolenski | Cornell | A1.01.01.04.03 |  | A1.01 - Project Management | T-1 | Milestone (T-1): CBETA Commissioned and Project Complete | 0 d | 0% | 2020-04-30 | 2020-04-30 |  |  |  |  | 2020-04-30 |  | FY20Q2
523 | Hoffstaetter | Hoffstaetter | Cornell | A1.02.04.01.04 |  | A1.02 - Accelerator Physics | T-3 | Milestone: Accelerator Design - Scientific Support, FY20 - Complete | 0 d | 0% | 2020-05-06 | 2020-05-06 |  |  |  |  | 2020-05-06 |  | FY20Q2
229 | Bartnik | Bartnik | Cornell | A1.12.07.05 |  | A1.12 - Beam Commissioning | T-2 | Milestone (T-2): Four Pass Energy Recovery - Commissioning Complete | 0 d | 0% | 2020-05-06 | 2020-05-06 |  |  |  |  | 2019-12-31 |  | FY20Q2